## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Providing Functional Household Tap Connection in connection with Jalswapna near 18 no. line 15 no. line and allied areas for Hope T.G. PWSS under Jalpaiguri Division, PHE Dte. (Part-B) |  | Junior Engineer | ORD/000549/2021-2022 | 1049/JSSD | 24/01/2022 | 08/02/2022 | GOUTAM DAS | 4.75 | 4.75 | 99.97 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Hope Tea Garden under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000132/2022-2023 | 1467/JD | 25/07/2022 | 24/08/2022 | PROSENJIT BASAK | 13.84 | 13.14 | 94.99 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Repairing of 2 nos. of pump house (1st site & 2nd site) 3 nos. Boundary wall (Head work site, 1st site & 2nd site) with sanitary & plumbing arrangement and other allied works at Hope T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000547/2021-2022 | 1065/JSSD | 24/02/2022 | 26/03/2022 | GOUTAM DAS | 4.08 | 4.03 | 98.79 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Urgent Retrofitting works at LW Bungalow back side under Hope T.G. Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000261/2022-2023 | 187/JSSD | 31/08/2022 | 30/09/2022 | NARAYAN CHANDRA ADHIKARY | 1.91 | 1.89 | 99.08 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Disconnecting illegeal connections and street stand posts with repairing of distribution line at Rejuvenation of Chalsa (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000390/2022-2023 | 363/JD | 20/02/2023 | 06/03/2023 | ALICK DATTA | 2.91 | 2.9 | 99.82 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Construction of 2 nos. Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement and 2 nos. boundary wall with gate,drain and pathway for 3rd & 4th tubewell site of Hope TG piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000430/2022-2023 | 632/JD | 13/03/2023 | 12/05/2023 | PRADIP KUMAR SHIL | 16.98 | 17.3 | 101.84 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | EMERGENT REPAIRING OF PIPE LINE INSTALLATION OF VALVE ALONG WITH OTHER ALLIED WORKS RELATED TO PIPELINE UNDER HOPE TG PIPE WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000350/2023-2024 | 299/JSSD | 27/09/2023 | 11/11/2023 | GOUTAM DAS | 3.37 | 3.37 | 99.95 | 100
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Infrastructure Cost for HOPE TEA GARDEN,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 100000072368, Reference ID : 860263628] |  |  | BILL/00754/2022-2023 | BP/22-23/157 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | New Service Connection Charge for HOPE TEA GARDEN,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 4003097490, Reference ID : 402966973] |  |  | BILL/00753/2022-2023 | BP/22-23/157 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | New Service Connection Charge for HOPE TEA GARDEN,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 4003097475, Reference ID : 402966977] |  |  | BILL/00755/2022-2023 | BP/22-23/157 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Infrastructure Cost for HOPE TEA GARDEN,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 100000072607, Reference ID : 860263637] |  |  | BILL/00756/2022-2023 | BP/22-23/157 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.56 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Providing Functional Household Tap Connection 257 Nos. in connection with Jal Jeevan Mission at Hope Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000347/2023-2024 | 293/JSSD | 27/09/2023 | 27/10/2023 | GOUTAM DAS | 9.47 | 7.29 | 76.89 | 91
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza | SM/09862 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HOPE T.G PWSS, TW No III and IV in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000023/2023-2024 | 465/NMD | 25/04/2023 | 25/05/2023 | M/S P.P. ELECTRICALS | 21.6 | 21.5 | 99.55 | 100
Total | [13 empty] | 86.52 | 76.17 | 88.04