## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Sinking of Deep Tube well by Odex - 165 Method of drilling at 3rd tube well site for Rejuvenation of Nayasily Tea Garden Piped water Supply scheme under Jalpaiguri Division, P.H.E. Dte." |  | Junior Engineer | ORD/000773/2021-2022 | 837/JD | 31/03/2022 | 21/04/2022 | M/S S. G. ENTERPRISE | 7.61 | 6.14 | 80.68 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Sinking of Deep Tube Well by Odex -165 Method of drilling at 4th tube well site for Rejuvenation of Nayasily Tea Garden Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte." |  | Junior Engineer | ORD/000774/2021-2022 | 838/JD | 31/03/2022 | 21/04/2022 | M/S S. G. ENTERPRISE | 7.62 | 6.05 | 79.49 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Soil Investigation work for 200 CuM Over Head Reservoir (OHR) for Nayasaily T.G. PWSS under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000693/2021-2022 | .1065/JSSD | 24/01/2022 | 13/02/2022 | R.B TESTING | 2.01 | 2.01 | 99.92 | 100
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 3rd tube-well site of Rejuvenation of Nayasaily Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  |  | ORD/001001/2021-2022 | 1260/JSSD | 25/03/2022 | 14/04/2022 | ROY CONSTRUCTION | 4.79 | 3.57 | 74.58 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Providing Tap Water Supply Connection in Connection with Jaldhara /Jalswapna in School, ICDS Centre and Health Centre at Hope TG,Naya Sily TG, Jiti TG,Nagrakata & Nagrakata TG Water Supply Scheme at Nagrakata Block under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000111/2022-2023 | 88/JSSD | 22/07/2022 | 01/08/2022 | GOUTAM DAS | 3.64 | 3.63 | 99.97 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Construction of Pump House (3.60 m x 2.40m) size with sanitary and plumbing arrangement at 3rd tubewell site for Rejuvenation of Water Supply of Nayasaily Tea Garden Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000125/2022-2023 | 24/JSSD | 21/06/2022 | 05/08/2022 | SANJIT SARKAR | 4.76 | 4.76 | 100 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Construction of boundary wall with gate, drain and pathway for 4th tube-well site for Rejuvenation of Nayasaily Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000311/2022-2023 | 64/JSSD | 19/07/2022 | 08/08/2022 | N.M. CONSTRUCTION | 4.77 | 3.39 | 71.01 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size including sanitary & plumbing arrangement at 4th tube well site for Rejuvenation of Nayasaily Tea Garden Water Supply Scheme for under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2022-2023 | 63/JSSD | 19/07/2022 | 02/09/2022 | N.M. CONSTRUCTION | 4.75 | 4.75 | 100 | 100
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Infrastructure Cost for NAYASYLEE,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 100000072608, Reference ID : 860263638] |  |  | BILL/00764/2022-2023 | BP/22-23/158 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.51 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Infrastructure Cost for NAYASAILY,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 100000072600, Reference ID : 860263630] |  |  | BILL/00758/2022-2023 | BP/22-23/158 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | New Service Connection Charge for NAYASAILY,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 4003097516, Reference ID : 402966975] |  |  | BILL/00757/2022-2023 | BP/22-23/158 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | New Service Connection Charge for NAYASYLEE,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 4003098584, Reference ID : 402967280] |  |  | BILL/00763/2022-2023 | BP/22-23/158 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | 200 Cum OHR as per Departmental Design & Drawing for Rejuvenation of Nayasaily Tea Garden Area Piped Water Supply Scheme Block- Nagrakata, District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000043/2022-2023 | 1081/JD | 29/04/2022 | 26/10/2022 | SABITA ENTERPRISE | 55.26 | 33.84 | 61.24 | 100
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAYASAILY TEA GARDEN PWSS,TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000869/2022-2023 | 334/NMD | 29/03/2023 | 28/04/2023 | HARA PROSAD DAS | 21.5 | 20.77 | 96.59 | 70
15 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Balance work in connection with providing Functional Household Tap Connection (FHTC) i.c.w. Jal Jeevan Mission under the command area of Rejuvenation of Nayasayli T.G. Area Piped W/S Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. (Phase-IV). | Assistant Engineer | Junior Engineer | ORD/000138/2024-2025 | 1527/JD | 01/10/2024 | 21/10/2024 | GAP ENGINEERS ENTERPRISES | 14.48 | 12.05 | 83.22 | 90
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Replacement of UPVC pipeline with other allied works at Jungle Busty area i.c.w. Rejuvenation of Nayasaili Piped W/S Scheme under JJM at Nagrakata BLOCK, under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2024-2025 | 266/JSSD | 25/09/2024 | 02/11/2024 | NEW KUNDU ENTERPRISE | 2.24 | 2.24 | 99.94 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 2110/JD | 25/11/2024 | 25/11/2024 | Resource Division | 5.22 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Sinking of a Rig Bored Tubewell by ODEX-165 method of drilling along with pump connection and other allied works at Champaguri Bazar area (5th TW Site) in connection with Jal Jeevan Mission of Rejuvenation of Naya Saily TG Piped Water Supply Scheme, Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000624/2024-2025 | 463/JD | 11/03/2025 | 10/04/2025 | NARESH SEN | 10.09 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Balance work in connection with laying rising main with other allied works for Rejuvenation of Nayasayli Tea Garden Piped W/S Scheme under JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000146/2024-2025 | 259/JSSD | 25/09/2024 | 02/07/2025 | GOLDEN KEY ENTERPRISE | 7.07 | 0 | 0 | 75
20 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.23 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme | SM/09863 | Augmentation | Laying Rising Main for Rejuvenation of Nayasaily Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000480/2022-2023 | 799/JD.. | 29/03/2023 | 02/10/2024 | GOLDEN KEY ENTERPRISE | 2.66 | 1.48 | 55.42 | 100
Total | [13 empty] | 172.94 | 104.69 | 60.54