## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Repairing of Pump House (2nd T/W Site) and extension of pipeline repairing of pipeline under Purba Batabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000560/2020-2021 | 169/JSSD | 13/08/2020 | 12/09/2020 | BIMAN DAS | 4.77 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Construction of boundary wall with gate, drain, culvert, Pipe line for H/W site of Purba Batabari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001010/2021-2022 | 1332/JD | 23/08/2021 | 22/09/2021 | R.S CONSTRUCTION | 15.53 | 14.66 | 94.46 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Sinking of 1 No. 250mm x 150mm x 132m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000011/2022-2023 | 872/JD | 04/04/2022 | 25/04/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 7.8 | 7.58 | 97.17 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | AUG PURBA BATABARI |  |  | VCH/001080/2021-2022 | BP-2021-22-169 | 14/01/2022 | 14/01/2022 | BIMAN DAS | 4.36 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | RESTORATION OF PIPE LINE PURBA BATABARI PWSS |  |  | VCH/001275/2021-2022 | BP-2021-22-508 | 30/03/2022 | 30/03/2022 | BIMAN DAS | 2.99 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | PROVIDING DRINKING ARRANGEMENT AWC MAL SUB-DIVISION |  |  | VCH/001363/2021-2022 | BP-2021-22-541 | 31/03/2022 | 31/03/2022 | DREAM CONSTRUCTION | 4.61 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | New Service Connection Charge for PURBO BATABARI NEAR DIGHIR PAR W/S SCHEME, T/W No. III, under MATELLI CCC, [APPLICATION NO. 4002964283, Reference ID :402851945] |  |  | VCH/000979/2022-2023 | BP/22-23/91 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | SINKING OF TUBEWELL FOR LATAGURI |  |  | VCH/001403/2021-2022 | BP-2021-22-542 | 31/03/2022 | 31/03/2022 | DREAM CONSTRUCTION | 7.63 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | PREPARATION OF DPR PURBA BATABARI PWSS |  |  | VCH/001281/2021-2022 | BP-2021-22-489 | 29/03/2022 | 29/03/2022 | SUBHANKAR GHOSH | 1.57 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Installation of Infrastructure COST at PURBO BATABARI NEAR DIGHIR PAR W/S SCHEME, T/W No. III, under MATELLI CCC, [APPLICATION NO. 100000059481, Reference ID : 860249201] |  |  | VCH/000980/2022-2023 | BP/22-23/91 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | RENOVATION OF B-WALL SOUTH BERUBARI |  |  | VCH/000088/2022-2023 | BP-2022-2023-46 | 24/05/2022 | 24/05/2022 | A.P CONSTRUCTION | 2.2 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Restoration of pipeline at Purba Batabari PWSS (damaged part) under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000551/2021-2022 | 991/JSSD | 03/01/2022 | 13/01/2022 | BIMAN DAS | 2.99 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Construction of paver block approach road with land development, inside drain etc. and fixing R.B.T. in boundary wall at H/W Site for Batabari Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000531/2021-2022 | 134/JD | 14/01/2022 | 29/01/2022 | SUNIL ROY | 4.46 | 3.52 | 78.84 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Laying Rising Main from 1st & 2nd Tubewell site to OHR for Augmentation of Purba Batabari PWSS in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000404/2023-2024 | 388/JSSD | 09/11/2023 | 09/12/2023 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 3.64 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size including Sanitary and Plumbing works at 3rd TubeWell site for Augmentation of Purbba Batabari Piped Water Supply Scheme under Jalpaiguri Division PHE.Dte. |  |  | ORD/000830/2021-2022 | 1108/W/JSSD | 27/01/2022 | 13/03/2022 | N S CONSTRUCTION & SUPPLIER | 4.75 | 4.75 | 100 | 100
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  |  | ORD/000124/2022-2023 | 84/JSSD | 22/07/2022 | 11/08/2022 | N S CONSTRUCTION & SUPPLIER | 4.57 | 4.51 | 98.62 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Soil Investigation work for 300 CuM OHR for Augmentation of Purba Batabari PWSS under Jalpaiguri Diviion, P.H.E. Dte. |  | Junior Engineer | ORD/001066/2021-2022 | 1064/JSSD | 24/01/2022 | 13/02/2022 | G. TECH INDIA | 1.83 | 0.74 | 40.28 | 0
18 | JALPAIGURI |  | Northern Mechanical | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA BATABARI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000768/2022-2023 | 74/NMD | 27/01/2023 | 26/02/2023 | M/S MATRI CONSTRUCTION | 10.98 | 10.98 | 100 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Construction of Sluice valve Chamber and GI line over culvert for Batabari Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001047/2021-2022 | 1931/JD | 29/11/2021 | 14/12/2021 | SUNIL ROY | 1.63 | 1.58 | 97.23 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | HIRE CHARGES |  |  | VCH/000663/2022-2023 | BP-2022-23-344 | 09/12/2022 | 09/12/2022 | APIKUL ALI | 0.34 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | HIRE CHARGES |  |  | VCH/000664/2022-2023 | BP-2022-23-344 | 09/12/2022 | 09/12/2022 | RAKESH SARKAR | 0.33 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Estimate for the Construction of Box Culvert for making approach to Purba Batabari HW Site under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000551/2023-2024 | 499/JSSD | 02/01/2024 | 01/02/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 0 | 0 | NAN | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Estimate for the Construction of Box Culvert for making approach to Purba Batabari HW Site under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000552/2023-2024 | 499/JSSD | 02/01/2024 | 01/02/2024 | TIRTHANKAR CHOWDHURY | 2.8 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Supplying and Installation of 24 nos. Display Board at different piped water supply scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2024-2025 | 89/JSSD | 20/06/2024 | 30/06/2024 | GURUKUL INFOTECH | 4.46 | 4.43 | 99.23 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Supplying and Installation of 77 nos Display Board at different piped water supply scheme in connection with JJM under Jalpaiguri Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000014/2024-2025 | 88/JSSD | 20/06/2024 | 30/06/2024 | GOUTAM DAS | 14.3 | 14.25 | 99.64 | 100
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jalswapna for Augmentation of Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000788/2021-2022 | 667/JD | 09/03/2022 | 01/01/2026 | BOSE ENTERPRISE | 221.99 | 176.41 | 79.46 | 90
28 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with land development works for Augmentation of Purbba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000160/2023-2024 | 793/JD | 24/07/2023 | 20/01/2024 | TIRTHANKAR CHOWDHURY | 91.24 | 40.38 | 44.26 | 70
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 4th TW including Delivery main for Augmentation of Purba Batabari PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000461/2024-2025 | 108/JD | 16/01/2025 | 17/03/2025 | M/S. S.D. ENTERPRISE | 19.96 | 0 | 0 | 0
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Providing Sluice Valves at Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2024-2025 | 331/JSSD | 10/09/2024 | 17/09/2024 | SWAPAN SAHA | 0.55 | 0 | 0 | 100
31 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | Assistant Engineer | Junior Engineer | ORD/000153/2025-2026 | 1734/JD | 31/07/2025 | 30/09/2025 | APIKUL ALI | 0.8 | 0 | 0 | 0
32 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | Assistant Engineer | Junior Engineer | ORD/000474/2025-2026 | 2405/JD | 19/11/2025 | 19/12/2025 | APIKUL ALI | 0.4 | 0 | 0 | 0
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme | SM/09864 | Augmentation | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | Assistant Engineer | Junior Engineer | ORD/000201/2025-2026 | 2000/JD | 25/09/2025 | 25/11/2025 | APIKUL ALI | 0.8 | 0 | 0 | 0
Total | [13 empty] | 475.78 | 283.78 | 59.65