## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Repairing of 2 nos of Pump House (1st site & 2nd site ), 2Nos boundary wall (1st site & 2nd site) and other Allied works at Jiti TG Piped Water Supply Scheme under Jalpaiguri Division .P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000308/2022-2023 | 90/JSSD | 22/07/2022 | 06/08/2022 | SOUVIK SAHA | 4.7 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | SINKING 250MX150 MM DIA PURBASALBARI PWSS |  |  | VCH/001307/2021-2022 | BP-2021-22- 470 | 28/03/2022 | 28/03/2022 | ABHIJIT SARKAR | 7.92 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | lds jabarmali pwss |  |  | VCH/000542/2022-2023 | BP-2021-22-170 | 29/09/2022 | 29/09/2022 | BOSE ENTERPRISE | 2.43 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | RETROFITTING WORKS BHANGARHAT PWSS |  |  | VCH/001289/2021-2022 | BP-2021-22-500 | 29/03/2022 | 29/03/2022 | MRINMOY KANTI DUTTA | 1.55 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Sinking of Tow Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme of Jiti Tea Garden under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2022-2023 | 1222/JD | 31/05/2022 | 30/06/2022 | M/S BABUN BISWAS | 13.84 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of JITI pipe water supply scheme at Nagrakata Block under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2022-2023 | 82/JSSD | 22/07/2022 | 11/08/2022 | ARUP SARKAR | 4.85 | 0 | 0 | 100
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Retrofitting works and installation of valerelated to Functional Household Tap Connection(FHTC)inconnection with JJM/Jalswapna under command area of Jiti pipe watersupply scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000117/2022-2023 | 94/JSSD | 22/07/2022 | 21/08/2022 | ARUP SARKAR | 3.25 | 0 | 0 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 1374/JD | 27/09/2023 | 27/09/2023 | Resource Division | 9.21 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Construction of Pump House (3.60 M x 2.40 M) size with sanitary & Plumbing arrangement at 3rd Tube well site for Jiti T.G. PWSS under Jalpaiguri Division, | Assistant Engineer | Junior Engineer | ORD/000597/2021-2022 | 1055/JSSD | 24/01/2022 | 10/03/2022 | ADWIJA CONSTRUCTION | 4.64 | 0 | 0 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Construction of boundary wall with gate drain and pathway for 3rd tube well site of Jiti T.G. P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000707/2021-2022 | 1044/JSSD | 24/01/2022 | 13/02/2022 | ADWIJA CONSTRUCTION | 3.76 | 0 | 0 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Sinking of 2 Nos. Big dia Tube Well by Modified DTH-ODEX method at 3rd & 4th tube well site in connection with Jal Jeevan Mission of JITI Tea Garden piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000299/2023-2024 | 1356/JD | 26/09/2023 | 26/10/2023 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 32.57 | 0 | 0 | 100
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. IV, under MAL CCC [APPLICATION NO. 100000099256 ; Reference ID : 860291236] |  |  | BILL/02019/2023-2024 | BP/23-24/309 | 16/02/2024 | 16/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.8 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. IV, under MAL CCC [APPLICATION NO. 4003330215 ; Reference ID : 403155155] |  |  | BILL/02021/2023-2024 | BP/23-24/309 | 16/02/2024 | 16/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | New Service Connection Charge for REJU JITI TEA GARDEN, T/W No. III, under MAL CCC [APPLICATION NO. 403330231 ; Reference ID : 403155154] |  |  | BILL/02020/2023-2024 | BP/23-24/309 | 16/02/2024 | 16/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
15 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. III, under MAL CCC [APPLICATION NO. 100000099255 ; Reference ID : 860291235] |  |  | BILL/02018/2023-2024 | BP/23-24/309 | 16/02/2024 | 16/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.56 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Laying Rising Main for Rejuvenation of Jiti Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000482/2022-2023 | 801/JD.. | 29/03/2023 | 28/09/2025 | KSMC CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION | 2.48 | 0 | 0 | 100
17 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.23 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza | SM/09865 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JITI T.G. PWSS, TW No III and IV in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000884/2022-2023 | 367/NMD | 29/03/2023 | 16/02/2025 | MIHIR SARKAR | 25.02 | 0 | 0 | 90
Total | [13 empty] | 126.28 | 0 | 0