## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-I, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000060/2022-2023 | 435/NMD | 14/06/2022 | 05/07/2022 | SANJIB SAHA | 2.77 | 0 | 0 | 0
2 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. |  |  | ORD/000302/2022-2023 | 2191/JD | 11/11/2022 | 11/12/2022 | M/S MILLENNIUM FUEL CENTRE | 2.17 | 2.17 | 100 | 1
3 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. |  |  | ORD/000300/2022-2023 | 2189/JD | 11/11/2022 | 11/12/2022 | M/S MILLENNIUM FUEL CENTRE | 2.5 | 2.5 | 100 | 1
4 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-II, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000062/2022-2023 | 437/NMD | 14/06/2022 | 05/07/2022 | SAIKAT SINHA | 2.39 | 2.39 | 100 | 0
5 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | New Service Connection Charge for BHAGATPUR T.G. W/S SCHEME, T/W No. II, Zone-I, [APPLICATION NO. 4002950622, Reference ID : 402840877] |  |  | VCH/000844/2022-2023 | BP/22-23/44 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.56 | 0 | 0 | 0
6 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Proposal for Approval W.O & E.O for New Three Phase Connection Work MII.R.O BHAGATPOORN DEEPA LINE, TW NO. 02 at BHAGATPUR T.G., [APPLICATION NO. 100000055158, Reference ID : 860244738] |  |  | VCH/000863/2022-2023 | BP/22-23/44 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.58 | 0 | 0 | 0
7 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Infrustructure cost for New Service Connection Charge for TW-II, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000053301,Reference ID : 402838302 |  |  | VCH/000320/2022-2023 | BP/2022-23/32 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0 | 0
8 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | shifting of pipe line pwd nagrakata |  |  | VCH/000580/2022-2023 | 342/22-23 | 15/09/2022 | 15/09/2022 | PRADIP SAHA | 0.04 | 0 | 0 | 0
9 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Infrustructure cost for New Service Connection Charge for TW-I, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000053303,Reference ID : 402830565 |  |  | VCH/000318/2022-2023 | BP/2022-23/32 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.8 | 0 | 0 | 0
10 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | New Service Connection Charge for TW-I, ZONE-I of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 4002953412,Reference ID : 860244395 |  |  | VCH/000321/2022-2023 | BP/2022-23/32 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.06 | 0 | 0 | 0
11 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | New Service Connection Charge for TW-II, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 4002939102,Reference ID : 860242791 |  |  | VCH/000319/2022-2023 | BP/2022-23/32 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0 | 0
12 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | New Service Connection Charge for TW-I, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC , APPLICATION NO. 4002939096 , Reference ID : 860242793 |  |  | VCH/000317/2022-2023 | BP/2022-23/32 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.05 | 0 | 0 | 0
13 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Infrastructure cost for New Service Connection Charge for TW-I, ZONE-I of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000055565, Reference ID : 860244395 |  |  | VCH/000322/2022-2023 | BP/2022-23/32 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0 | 0
14 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Laying distribution system with Rising Main Connection, of Bhagatpur Piped water Supply Scheme , Zone-II at Nagrakata Block under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000337/2021-2022 | 212/JD | 24/01/2022 | 25/03/2022 | LOKNATH CONSTRUCTION | 93.12 | 87.08 | 93.52 | 100
15 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Resistivity Test for Four Nos.Tube Well for Bhagatpur Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000495/2021-2022 | 1938/JD | 29/11/2021 | 14/12/2021 | PARAMJYOTI ENTERPRISE | 0.6 | 0.6 | 100 | 0
16 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Carrying out Development works and Yield Test for a RBTW (BDTW) at Shyamdhan W/S Scheme (H/W Site) & (2nd Site), Replacement TW, G.P.- Raniganj Panisali, Block - Kharibari, Dist- Darjeeling and Bhagatpur TG PWSS (Zone-I), TW-I (H/W Site) & TW-II (2nd Site), Block - Nagrakata, Dist- Jalpaiguri and Naxalbari RH W/S Scheme, Block - Naxalbari, Dist- Darjeeling, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000779/2021-2022 | 262/DSD | 22/12/2021 | 12/01/2022 | ALPHA ENTERPRISE | 0.53 | 0.53 | 100 | 100
17 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-II, TW No. I in the dist. of Jalpaiguri under under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000061/2022-2023 | 436/NMD | 14/06/2022 | 05/07/2022 | BLUE PINE | 2.39 | 1.82 | 76.11 | 70
18 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Bhagatpur T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000226/2022-2023 | 1855/JD | 16/09/2022 | 31/10/2022 | ADITRI ENTERPRISE | 4.65 | 4.75 | 102.12 | 1
19 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-I, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000125/2022-2023 | 867/NMD | 20/07/2022 | 19/08/2022 | ANUP BASU | 10.29 | 9.77 | 94.99 | 0
20 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-II, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000077/2022-2023 | 535/NMD | 08/07/2022 | 07/08/2022 | RIPON DAS | 9.99 | 9.99 | 100 | 100
21 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Bhagatpur T.G. P.W.S.S. zone-II under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000225/2022-2023 | 1854/JD | 16/09/2022 | 31/10/2022 | RANA DEY | 4.65 | 4.77 | 102.42 | 1
22 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Construction of approach road including development of the approach way for the Head works site of Bhagatpur T.G. Piped water supply Scheme Zone -II under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000208/2022-2023 | 1798/JD | 14/09/2022 | 05/10/2022 | ASIT PAUL | 2.84 | 2.83 | 99.5 | 0
23 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-I, TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Driller-in-Charge | Junior Engineer | ORD/000059/2022-2023 | 434/NMD | 14/06/2022 | 05/07/2022 | MIHIR SARKAR | 2.77 | 2.19 | 79.32 | 70
24 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-I, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000075/2022-2023 | 533/NMD | 08/07/2022 | 07/08/2022 | CHOWDHURY AND BASU ENTERPRISE | 10.3 | 6.91 | 67.1 | 50
25 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
26 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Laying distribution system and construction of Boundary Wall ,Foot Path, Drain at HW site of Bhagatpur Zone-II PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000011/2024-2025 | 427/JD | 13/06/2024 | 13/07/2024 | LOKNATH CONSTRUCTION | 34.67 | 4.96 | 14.31 | 45
27 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig unit 32B-R-1302, by Odex-165 method of drilling at TW-II (2nd Site) under Bhagatpur TG PWSS (Zone-II), Block - Nagrakata, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. |  |  | ORD/000778/2021-2022 | 257/DSD | 17/12/2021 | 01/01/2022 | RUDOLF DIESEL ENGINEERING SERVICE | 0.49 | 0.49 | 100 | 100
28 | JALPAIGURI | Nagrakata | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-II, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000076/2022-2023 | 534/NMD | 08/07/2022 | 07/08/2022 | SUBODH KUMAR BANIK | 10.02 | 9.02 | 89.99 | 100
29 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 2060/JD | 10/01/2024 | 10/01/2024 | Resource Division | 11.74 | 0 | 0 | 0
30 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Construction of 150 Cu.M. Capacity R.C.C. Over Head Reservoir of 17 Mtr. Staging Height, Construction of One No Pump House (5.40m x 3.60m) Boundary wall for the Head Works Site Zone-II of Bhagatpur PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000023/2022-2023 | 1055/JD | 27/04/2022 | 01/07/2025 | LOKNATH CONSTRUCTION | 63.09 | 24.54 | 38.9 | 50
31 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Providing Functional Household Tap Connection in connection with Jal Jeeven Mission under Bhagatpur Piped Water Supply Scheme Zone-II Command area under Jalpaiguri Division P.H.E. Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000328/2022-2023 | 2458/JD | 22/12/2022 | 31/07/2025 | UDAYAN BOSE | 23.71 | 17.05 | 71.92 | 100
32 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Rising Main and FHTC at Bhagatpur PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000164/2025-2026 | 1953/JD | 18/09/2025 | 01/04/2026 | ADITRI ENTERPRISE | 14.59 | 0 | 0 | 30
33 | JALPAIGURI | Nagrakata | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. | SM/09975 | New | Restoration of existing damaged pipeline near railway crossing at Jhahaji line in connection with Jal Jeevan Mission under Bhagatpur Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000012/2024-2025 | 428/JD | 13/06/2024 | 31/05/2026 | LOKNATH CONSTRUCTION | 25.24 | 0 | 0 | 25
Total | [13 empty] | 381.94 | 194.38 | 50.89