## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-B) |  | Junior Engineer | ORD/000343/2021-2022 | 207/JD | 24/01/2022 | 25/03/2022 | M/S A.B.G. CONSTRUCTION | 239.47 | 196.16 | 81.91 | 70
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000344/2021-2022 | 209/JD | 24/01/2022 | 24/04/2022 | M/S SIBU DEY AND CO. | 130.99 | 94.27 | 71.97 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Shifting of pipeline due to widening and strengthening of PWD road from Jhak Para Petrol Pump towards Head Work Site Pump House at Kranti zone- I Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000593/2021-2022 | 993/JSSD | 03/01/2022 | 23/01/2022 | NARAYAN CHANDRA ADHIKARY | 3.96 | 3.9 | 98.52 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Emergent Laying Distribution System for inter connection to main line at Bhujari Para and Cana bridge at Kranti zone-II P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000550/2021-2022 | 1050/JSSD | 24/01/2022 | 08/02/2022 | BARUN KUMAR DUTTA | 4.71 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Laying Distribution System providing With Functional Household Tap Connection (FHTC) in connection with Jalswapna/JJM for Augmentation of Kranti (Zone-II) Piped Water supply scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2022-2023 | 914/JD | 07/04/2022 | 05/08/2022 | M/S A.B.G. CONSTRUCTION | 468.36 | 328.8 | 70.2 | 70
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No. WB71B-8742) | Assistant Engineer | Junior Engineer | ORD/000078/2022-2023 | 1416/JD | 14/07/2022 | 14/07/2023 | RAKESH SARKAR | 0.15 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) | Assistant Engineer | Junior Engineer | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 14/07/2023 | RAKESH SARKAR | 1.76 | 0.74 | 41.9 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-C) |  | Junior Engineer | ORD/000345/2021-2022 | 210/JD | 24/01/2022 | 24/04/2022 | BOSE ENTERPRISE | 156.83 | 107.43 | 68.5 | 80
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Sinking of 1 No. 200mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling at 3rd Site for Augmentation of Kranti (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000610/2021-2022 | 410/JD | 15/02/2022 | 08/03/2022 | LOKNATH CONSTRUCTION | 7.62 | 7.49 | 98.36 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Sinking of 1 No. 200mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling at 3rd Site for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2021-2022 | 411/JD | 15/02/2022 | 08/03/2022 | LOKNATH CONSTRUCTION | 7.62 | 7.38 | 96.91 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Emergent restoration of pipeline at Kodalkati area under Kranti GP and construction of periferial boundary including retaining structure at H/W Site for Augmentation of Kranti zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2022-2023 | 1033/JD | 27/04/2022 | 27/05/2022 | D. S. ENTERPRISE | 29.73 | 30.17 | 101.46 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Laying of pipeline near at Debijhora High School towards Kranti Bazar including Jhora Crossing under Kranti Zone-II Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000592/2021-2022 | 992/JSSD | 03/01/2022 | 18/01/2022 | NARAYAN CHANDRA ADHIKARY | 2.5 | 2.14 | 85.77 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | DPR PREPARATION FOR ANGRABHASA PWSS |  |  | VCH/001411/2021-2022 | BP-2021-22-547 | 31/03/2022 | 31/03/2022 | SUBHANKAR GHOSH | 1.05 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Installation of Infrastructure COST at KRANTI W/S SCHEME, T/W No. II, under KRANTI CCC, [APPLICATION NO. 100000059310, Reference ID : 860248970] |  |  | VCH/000905/2022-2023 | BP/22-23/94 | 18/11/2022 | 18/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | LDS FHTC PURBA DURAMARI |  |  | VCH/001287/2021-2022 | BP-2021-22-493 | 29/03/2022 | 29/03/2022 | SUKES BASU MAJUMDAR | 46.78 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | LDS FHTC AUG MONDALGHAT |  |  | VCH/001418/2021-2022 | BP-2021-22-462 | 27/03/2022 | 27/03/2022 | M/S R.N. TRADERS | 38.53 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | New Service Connection Charge for KRANTI W/S SCHEME, T/W No. II, under KRANTI CCC, [APPLICATION NO. 400295553, Reference ID : 402862646] |  |  | VCH/000904/2022-2023 | BP/22-23/94 | 18/11/2022 | 18/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Construction of Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at 2(two) Nos. Head Works sites for Augmentation works of Kranti (Zone-I and II) Piped Water Supply Scheme under Jal Jeevan Mission, Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 797/JD. | 24/07/2023 | 01/04/2026 | MD HAKIMUDDIN | 291.65 | 64.39 | 22.08 | 50
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Construction of approach for Head Works Site for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000386/2022-2023 | 361/JD | 20/02/2023 | 27/02/2023 | LOKNATH CONSTRUCTION | 0.61 | 0.61 | 99.65 | 100
20 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KRANTI PWSS, ZONE-I ,TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000875/2022-2023 | 339/NMD | 29/03/2023 | 01/02/2025 | SAIKAT SINHA | 10.85 | 7.39 | 68.16 | 80
21 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KRANTI PWSS, ZONE-II ,TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000876/2022-2023 | 340/NMD | 29/03/2023 | 28/04/2023 | SAIKAT SINHA | 10.18 | 10.14 | 99.61 | 90
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Emergent repairing of 3rd T/W site Pump House with Sanitary and Plumbing arrangement for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000020/2023-2024 | 253/JD | 10/05/2023 | 31/05/2023 | NARAYAN CHANDRA ADHIKARY | 2.34 | 2.32 | 98.99 | 100
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Construction of Guard Wall at pond side for existing Boundary Wall and joining the pipeline at Kodalkati for Augmentation of Kranti Zone - II Piped Water Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2023-2024 | 291/JSSD | 26/09/2023 | 26/10/2023 | D. S. ENTERPRISE | 1.55 | 1.49 | 96.15 | 100
24 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | New Service Connection Charge for AUGMENTATION OF KRANTI, ZONE-II, T/W No. I, under KRANTI CCC, [APPLICATION NO. 4003266348, Reference ID : 403105518] |  |  | BILL/01277/2023-2024 | 23-24/154&171 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
25 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Infrastructure Cost for AUGMENTATION OF KRANTI, ZONE-II, T/W No. I, under KRANTI CCC, [APPLICATION NO. 100000093177, Reference ID : 860284827] |  |  | BILL/01278/2023-2024 | 23-24/154&171 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.78 | 0 | 0 | 0
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | supply of fuel |  |  | BILL/00395/2022-2023 | BP-2022-23-557 | 29/03/2023 | 29/03/2023 | FILL & SMILE | 0.36 | 0 | 0 | 0
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | fuel charges |  |  | BILL/00249/2022-2023 | BP-2022-23-469 | 23/02/2023 | 23/02/2023 | FILL & SMILE | 0.8 | 0 | 0 | 0
28 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Kranti Zone-I Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000812/2023-2024 | 567/JSSD | 05/03/2024 | 04/04/2024 | KOHINOOR ISLAM | 3.22 | 0.97 | 30.09 | 70
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Kranti Zone-II Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000808/2023-2024 | 571/JSSD | 05/03/2024 | 18/03/2025 | SIDDHARTHA KAR | 8.44 | 4.06 | 48.15 | 85
31 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Construction of Boundary wall including Rising main Interconnection of Existing 2nd TW Site of Augmentation of Kranti Zone-I PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000136/2024-2025 | 1526/JD | 01/10/2024 | 31/10/2024 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.61 | 0 | 0 | 0
32 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Supplying and Installation of 45 nos. Display Board at different piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000550/2023-2024 | 497/JSSD | 02/01/2024 | 01/02/2024 | GOUTAM DAS | 7.17 | 7.13 | 99.37 | 100
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
34 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme | SM/09994 | Augmentation | Balance work of Rising Main, Internal Delivery & Iron Elimination Plant (IEP) connection for Zone-II under Augmentation of Kranti Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000009/2025-2026 | 892/JD | 08/05/2025 | 28/05/2025 | BIMAN DAS | 14.85 | 0 | 0 | 0
Total | [13 empty] | 1577.53 | 877 | 55.59