## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Boundary wall, Additional Laying distribution system adjacent to H/W site to sukhanii zone - II (H/W site T/W ) under Jalpaiguri Division PHE Dte. Part B ( Left & Right) |  |  | ORD/000179/2019-2020 | 291/JD | 13/03/2020 | 12/05/2020 | SADHAN KARMAKAR | 9.7 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Boundary wall, Additional Laying distribution system adjacent to H/W site for " SUKHANI ZONE-II WATER SUPPLY SCHEME ( H/ W SITE T/W )" under Jalpaiguri Divition , P.H.E. Dte. Part-"A" (Front Side) |  |  | ORD/000187/2019-2020 | 248/JD | 03/03/2020 | 02/05/2020 | SUBRATA GOSWAMI | 14.17 | 13.81 | 97.43 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000504/2021-2022 | 511/JD | 23/02/2022 | 16/03/2022 | B.M CONSTRUCTION | 8.09 | 0 | 0 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 4th tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000505/2021-2022 | 512/JD | 23/02/2022 | 16/03/2022 | B.M CONSTRUCTION | 8.09 | 0 | 0 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000885/2021-2022 | 842/JD | 31/03/2022 | 21/04/2022 | DEBASISH DEY | 8.09 | 7.79 | 96.26 | 1
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 4th tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000886/2021-2022 | 843/JD | 31/03/2022 | 21/04/2022 | DEBASISH DEY | 8.09 | 7.7 | 95.18 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Laying Distribution System including FHTC for Augmentation of Sukani Piped Water Supply Scheme Zone-III at Rajganj Block Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000037/2022-2023 | 1101/JD | 12/05/2022 | 09/09/2022 | BANSBERIA CONSTRUCTION CO. | 668.61 | 433.35 | 64.81 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 3rd Tube well site for Sukhani Zone I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000051/2022-2023 | 1196/JD | 20/05/2022 | 04/07/2022 | SHYAMAL KUMARSAHA | 4.64 | 4.64 | 100 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Laying Distribution System for Augmentation of Sukani Piped Water Supply Scheme Zone-I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000035/2022-2023 | 1102/JD | 12/05/2022 | 01/04/2026 | M/S A.B.G. CONSTRUCTION | 886.96 | 593.17 | 66.88 | 78
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Sukhani Zone I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000058/2022-2023 | 1200/JD | 20/05/2022 | 04/07/2022 | M/S A.P. DEVELOPERS | 4.65 | 4.65 | 100 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at head work site (ZONE-I) of SUKANI piped water supply scheme under JALPAIGURI Division PHE Dte. BLOCK ¿ RAJGANJ, DISTRICT ¿ JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2022-2023 | 1273/JD | 07/06/2022 | 22/07/2022 | M/S SURAJIT DEY AND CO. | 29.51 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000267/2022-2023 | 1010/NMD | 28/07/2022 | 18/08/2022 | ANUP BASU | 2.77 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Sukhani Zone II Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000057/2022-2023 | 1197/JD | 20/05/2022 | 04/07/2022 | UNIQUE CONSTRUCTION | 4.64 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Laying Distribution System with FHTC for Augmentation of Sukhani Piped Water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000059/2022-2023 | 1229/JD | 01/06/2022 | 27/01/2023 | MINTU CHAKRABORTY | 746.92 | 569 | 76.18 | 88
15 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. IV, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  |  | ORD/000263/2022-2023 | 1007/NMD | 28/07/2022 | 18/08/2022 | DAWA DUKPA | 2.39 | 0 | 0 | 0
16 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no IIin the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000523/2022-2023 | 1059/NMD | 24/08/2022 | 23/09/2022 | ABHISEK ENGINEERING CONCERN | 8.26 | 8.26 | 100 | 100
17 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000560/2022-2023 | 1108/NMD | 07/09/2022 | 07/10/2022 | M/S P.P. ELECTRICALS | 8.26 | 8.26 | 100 | 100
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Providing Contractor's personnel as Field Supervisor engaged in different water supply Schemes under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 10.11.2022 to 10.04.2023) |  |  | ORD/000391/2022-2023 | 2186/JD | 10/11/2022 | 10/04/2023 | SUKES BASU MAJUMDAR | 0.94 | 0.47 | 50 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Continuation order for the work of "Providing guarding arrangement at Stack Yard under Resource Division at the Head Work Site of SUKHANI PWSS (ZONE-I) under Jalpaiguri Division P.H.E. Dte. for the period from 01/08/2022 to 31/07/2023." | Assistant Engineer,HQ | Junior Engineer | ORD/000642/2022-2023 | 1504/A/JD | 28/07/2022 | 28/07/2023 | CLIFFORD FACILITY SERVICES PVT. LTD. | 16.62 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 3rd Tube well site for Sukhani Zone III Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000052/2022-2023 | 1198/JD | 20/05/2022 | 04/07/2022 | DILIP SINGHA | 4.65 | 4.65 | 100 | 1
21 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000260/2022-2023 | 1004/NMD | 28/07/2022 | 18/08/2022 | SUMON ELECTRICAL | 2.79 | 2.79 | 100 | 100
22 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000561/2022-2023 | 1107/NMD | 07/09/2022 | 01/04/2025 | M/S PARITOSH BHOWMICK AND CO. | 8.26 | 0 | 0 | 100
23 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-II) PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000562/2022-2023 | 1106/NMD | 07/09/2022 | 07/10/2022 | M/S ROYAL ENTERPRISE | 8.12 | 8.12 | 100 | 100
24 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-II) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000563/2022-2023 | 1105/NMD | 07/09/2022 | 07/10/2022 | TAPAN BISWAS | 8.09 | 8.09 | 100 | 70
25 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-I) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000565/2022-2023 | 1103/NMD | 07/09/2022 | 07/10/2022 | BONANZA ENTERPRISE | 8.26 | 8.26 | 100 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir(750 cum) at Sukhani zone-II zone under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000165/2022-2023 | 1433/JD | 18/07/2022 | 02/08/2022 | MOYTEC | 2.25 | 2.03 | 90.27 | 100
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir(750 cum) at Sukhani zone-I zone under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000173/2022-2023 | 1400/JD | 11/07/2022 | 26/07/2022 | AGAC | 2.26 | 2.24 | 99.46 | 100
28 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. I, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000264/2022-2023 | 1008/NMD | 28/07/2022 | 01/04/2025 | B.B. CONCERNED | 2.79 | 2.5 | 89.45 | 100
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- III head work site at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000582/2021-2022 | 513/JD | 23/02/2022 | 16/03/2022 | M/S R.N. TRADERS | 8.09 | 7.35 | 90.84 | 1
30 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-I) PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000564/2022-2023 | 1104/NMD | 07/09/2022 | 01/05/2025 | SANJIB SAHA | 8.26 | 6.41 | 77.63 | 100
31 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. IV, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000261/2022-2023 | 1005/NMD | 28/07/2022 | 18/08/2022 | CHOWDHURY AND BASU ENTERPRISE | 2.79 | 2.79 | 100 | 100
32 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at 3 rd tube well site ( ZONE-II) of SUKANI piped water supply scheme under JALPAIGURI Division PHE Dte. BLOCK ¿ RAJGANJ, DISTRICT - JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000070/2022-2023 | 1272/JD | 07/06/2022 | 05/09/2022 | MINTU CHAKRABORTY | 17.91 | 16.88 | 94.22 | 100
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sukhani Zone III Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000077/2022-2023 | 1373/JD | 30/06/2022 | 14/08/2022 | PARESH CHAND GHOSH ROY | 4.64 | 4.64 | 100 | 1
34 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd TubeWell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS zone -III at Rajganj Block under Jalpaiguri Division P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000701/2021-2022 | 766/JD | 23/03/2022 | 13/04/2022 | M/S KARMAKAR CONSTRACTION | 8.09 | 7.6 | 93.9 | 1
35 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. II, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000265/2022-2023 | 1009/NMD | 28/07/2022 | 18/08/2022 | SARKAR ELECTRIC | 2.79 | 2.79 | 100 | 100
36 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Support 300 mm DI pipe line near Fatapukur and construction 1 no. stand post and other ancillary works at Sukani Zone I under Rajganj block under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000219/2022-2023 | 1809/JD | 14/09/2022 | 05/10/2022 | R.K. SARKAR | 1.8 | 1.2 | 66.59 | 1
37 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000262/2022-2023 | 1006/NMD | 28/07/2022 | 18/08/2022 | M/S SAJAHAN CHOWDHURY | 2.41 | 2.39 | 99.41 | 100
38 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 2nd Tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- III at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000583/2021-2022 | 514/JD | 23/02/2022 | 16/03/2022 | M/S R.N. TRADERS | 8.09 | 7.33 | 90.61 | 1
39 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 4th Tube well site for Sukhani Zone II Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000054/2022-2023 | 1201/JD | 20/05/2022 | 04/07/2022 | KABYA ENTERPRISE | 4.64 | 4.64 | 100 | 100
40 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir (750 cum) at Sukhani Zone-III under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000166/2022-2023 | 1424/JD | 15/07/2022 | 30/07/2022 | M S PRANTIK ASSOCIATES | 2.22 | 2.12 | 95.23 | 100
41 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | LDS FHTC DAKHIN CHAK MAULANI |  |  | VCH/001271/2021-2022 | BP-2021-22-472 | 28/03/2022 | 28/03/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 21.09 | 0 | 0 | 0
42 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | New Service Connection Charge for Sukhani , Zone-III, T/W No. III near Nawapara, [APPLICATION NO. 4002960888, Reference ID : 402852055] |  |  | VCH/000843/2022-2023 | BP/22-23/57 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
43 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | New Service Connection Charge for TW-II, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002957097 , Reference ID : 402849241] |  |  | VCH/000769/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
44 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | SINKING OF 300MM X 200MM DIA 3RD T/WELL SUKHANI PWSS ZONE-II |  |  | VCH/001280/2021-2022 | BP-2021-22-479 | 29/03/2022 | 29/03/2022 | B.M CONSTRUCTION | 6.93 | 0 | 0 | 0
45 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | New Service Connection Charge for SUKHANI W/S SCHEME, T/W No. IV, under BELAKOBA CCC, [APPLICATION NO. 4002974096, Reference ID :402863303] |  |  | VCH/000894/2022-2023 | BP/22-23/60 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
46 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | New Service Connection Charge for TW-I, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002957084 , Reference ID : 402849240] |  |  | VCH/000771/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
47 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | CONST 250 M3 B/WALL BARADIGHI T.G |  |  | VCH/001369/2021-2022 | BP-2021-22-471 | 28/03/2022 | 28/03/2022 | BOSE ENTERPRISE | 49.78 | 0 | 0 | 0
48 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | EXT PIPE LINE SUKHANI ZONE - II |  |  | VCH/001399/2021-2022 | BP-2021-22-503 | 30/03/2022 | 30/03/2022 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0 | 0
49 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Infrastructure IRO NSC Application 4002960888 at Nawapara, Chaulhati under UMCCC ¿ Sukhani , Zone-III, T/W No. III, [APPLICATION NO. 100000057238, Reference ID : 860246418] |  |  | VCH/000842/2022-2023 | BP/22-23/57 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.78 | 0 | 0 | 0
50 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | New Service Connection Charge for TW-IV, ZONE-II of SUKHANI (SARIUM KALIBARI) W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002950741,Reference ID : 860244518 |  |  | VCH/000326/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
51 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | New Service Connection Charge for TW-III, ZONE-II of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951589,Reference ID : 860244513 |  |  | VCH/000324/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
52 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-III, ZONE-I of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054732,Reference ID : 402840892 |  |  | VCH/000329/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.89 | 0 | 0 | 0
53 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Infrustructure cost for New Service Connection Charge for TW-I, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000056935 , Reference ID : 860245495] |  |  | VCH/000772/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0 | 0
54 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | TUBE WELL SUKHANI ZONE-II |  |  | VCH/001438/2021-2022 | BP-2021-22-479 | 29/03/2022 | 29/03/2022 | SUKES BASU MAJUMDAR | 6.93 | 0 | 0 | 0
55 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-II, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000056936 , Reference ID : 860245496] |  |  | VCH/000770/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0 | 0
56 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | LDS PURBA DAUKIMARI PWSS |  |  | VCH/000093/2022-2023 | BP-2022-23-45 | 24/05/2022 | 24/05/2022 | SUKES BASU MAJUMDAR | 58.14 | 0 | 0 | 0
57 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Infrastructure COST at SUKHANI W/S SCHEME, T/W No. IV, under BELAKOBA CCC, [APPLICATION NO. 100000058353, Reference ID : 860248265] |  |  | VCH/000895/2022-2023 | BP/22-23/60 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
58 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | LDS BARADIGHI TG PWSS |  |  | VCH/001374/2021-2022 | BP-2021-22-475 | 31/03/2022 | 31/03/2022 | DIPAK KUMAR CHAKRABORTY | 7.66 | 0 | 0 | 0
59 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Infrustructure cost for New Service Connection Charge for TW-III, ZONE-II of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054733,Reference ID : 402840890 |  |  | VCH/000325/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0 | 0
60 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | New Service Connection Charge for TW-III, ZONE-I of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951616,Reference ID : 860244512 |  |  | VCH/000328/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
61 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-IV, ZONE-II of SUKHANI (SARIUM KALIBARI) W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054738,Reference ID : 402840893 |  |  | VCH/000327/2022-2023 | BP/2022-23/33 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
62 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-1) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000142/2023-2024 | 709/JD | 13/07/2023 | 02/04/2025 | MRINMOY KANTI DUTTA | 29.51 | 10.46 | 35.46 | 55
63 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Fitting fixing DI specials along with laying distribution for Augmentation of Sukhani Piped water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/000263/2023-2024 | 948/JD | 08/08/2023 | 07/10/2023 | MINTU CHAKRABORTY | 82.49 | 60.5 | 73.34 | 45
64 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessary connections for Augmentation of Sukhani Zone-I Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000249/2023-2024 | 1270/JD | 13/09/2023 | 01/12/2025 | SANJIT SAHA | 30.41 | 25.29 | 83.18 | 55
65 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-3) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000250/2023-2024 | 1263/JD | 13/09/2023 | 01/04/2026 | ANUP KUMAR KUNDU | 40.53 | 0 | 0 | 0
66 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-4) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000260/2023-2024 | 1262/JD | 13/09/2023 | 18/08/2025 | BILTU DAS | 40.83 | 0 | 0 | 50
67 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-2) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000280/2023-2024 | 1434/JD | 05/10/2023 | 28/04/2026 | SUBRATA GOSWAMI | 29.29 | 0 | 0 | 40
68 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). |  |  | ORD/000295/2023-2024 | 855/JD | 31/07/2023 | 31/01/2024 | SOUMEN GHOSH | 0.88 | 0.79 | 89.09 | 20
69 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | CONSTRUCTION OF RCC OVER HEAD RESERVOUR CAPACITY 700 CUM AND 20 M STAGGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKHANI (ZONE-III) PIPED WATER SUPPLY SCHEME. | Assistant Engineer,HQ | Junior Engineer | ORD/000372/2023-2024 | 1519/JD | 16/10/2023 | 08/02/2025 | M/S. SURYA I PVT. LTD COMPANY | 147.2 | 64.02 | 43.49 | 68
70 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sukhani (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000472/2022-2023 | 780/JD | 27/03/2023 | 17/04/2023 | ASIT PAUL | 19.36 | 18.41 | 95.07 | 100
71 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sukhani (Zone-III) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000485/2022-2023 | 804/JD | 29/03/2023 | 01/04/2025 | JITENDRA NATH ROY | 13.79 | 11.26 | 81.67 | 100
72 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at 3rd Tube Well site for Sukhani Piped Water Supply Scheme Zone-II at Rajganj block under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000114/2023-2024 | 449/JD. | 08/06/2023 | 23/07/2023 | JAGORAN SARKAR | 4.9 | 4.9 | 100 | 100
73 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site Sukhani PWSS (Zone-II) under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000256/2023-2024 | 1264/JD | 13/09/2023 | 28/10/2023 | A P CONSTRUCTION | 31.69 | 31.02 | 97.9 | 100
74 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site Sukhani PWSS (Zone-III) under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000319/2023-2024 | 1267/JD | 13/09/2023 | 01/08/2025 | ASHIT KUMAR SINGHA | 52.24 | 0 | 0 | 100
75 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at 4th Tubewell site Sukhani PWSS (Zone-II) under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000278/2023-2024 | 1359/JD | 26/09/2023 | 10/11/2023 | SANDIP BANIK | 17.65 | 17.58 | 99.62 | 100
76 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) for Augmentation at 3rd tubewell site Sukani (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000277/2023-2024 | 1358/JD | 26/09/2023 | 10/11/2023 | D. S. ENTERPRISE | 18.23 | 18.23 | 100 | 100
77 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1097/JD | 24/08/2023 | 24/08/2023 | Resource Division | 208.46 | 0 | 0 | 0
78 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Fitting fixing DI specials along with laying distribution and Pump House (5.40m x 3.60 m) at Head work site for Augmentation of Sukhani Piped water supply scheme Zone-III at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000564/2023-2024 | 2391/JD | 16/02/2024 | 07/03/2024 | BANSBERIA CONSTRUCTION CO. | 96.25 | 0 | 0 | 0
79 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying pipe line for H/W Site at Sukani zone III PWSS site piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ |  | ORD/000591/2023-2024 | 2329/JD | 08/02/2024 | 24/03/2024 | LOPCHAN ENTERPRISE | 18.11 | 0 | 0 | 0
80 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell site at Sukani Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000607/2023-2024 | 2308/JD | 07/02/2024 | 08/03/2024 | M/S A.P. DEVELOPERS | 7.76 | 0 | 0 | 0
81 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 3rd tubewell site at Sukani Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000730/2023-2024 | 2452/JD | 23/02/2024 | 24/03/2024 | M/S SAHA ENTERPRISE | 8.31 | 0 | 0 | 0
82 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | CONSTRUCTION OF RCC OVERHEAD RESERVOIR CAPACITY 750 CUM AND 20 M STAGGING HEIGHT AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKANI (ZONE I) PIPED WATER SUPPLY SCHEME IN CONNECTION WITH JAL JEEVAN MISSION AT BLOCK: RAJGANJ UNDER JALPAIGURI DIVISION, P.H.E DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000694/2023-2024 | 2411/JD | 19/02/2024 | 20/08/2025 | AMINUL HOQUE | 207.67 | 81.6 | 39.29 | 50
83 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell site at Sukani Zone- III piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000832/2023-2024 | 08/01/JD | 15/03/2024 | 14/04/2024 | PARESH CHAND GHOSH ROY | 8.32 | 0 | 0 | 100
84 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | CONSTRUCTION OF RCC OVER HEAD RESERVOUR CAPACITY 700 CUM AND 20 M STAGGING HEIGHT AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKHANI (ZONE-II) PIPED WATER SUPPLY SCHEME . | Assistant Engineer,HQ | Junior Engineer | ORD/000690/2023-2024 | 2392/JD | 16/02/2024 | 14/08/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 145.22 | 0 | 0 | 0
85 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Different Component like Pump House, Tube Well, IEP, Boundary wall and ancillary work at Mogradangi of Sukani PWSS (Zone-I) of Raiganj Block under Jalpaiguri Division, PHE, Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000821/2023-2024 | 2729/JD | 13/03/2024 | 31/03/2026 | D. S. ENTERPRISE | 54.2 | 0 | 0 | 20
86 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell site at Sukani Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000608/2023-2024 | 2309/JD | 07/02/2024 | 08/03/2024 | D. S. ENTERPRISE | 7.78 | 7.61 | 97.82 | 100
87 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Sukani Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000609/2023-2024 | 2310/JD | 07/02/2024 | 08/03/2024 | JAGORAN SARKAR | 8.51 | 7.82 | 91.85 | 100
88 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Sukhani (zone-III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000612/2023-2024 | 2311/JD | 07/02/2024 | 08/03/2024 | R.K. SINGHA & SONS | 8.42 | 8.1 | 96.12 | 100
89 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Shifting AC pipes ,Coumpound clearing, Cutting trees and other ancillary works at Sukani zone -II under Sukani piped water supply scheme under Jalpaiguri water supply Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000732/2023-2024 | 2453/JD | 23/02/2024 | 08/03/2024 | NEW KUNDU ENTERPRISE | 2.83 | 2.9 | 102.36 | 100
90 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Interconnection work for Iron Elimination Plant to Rising main, Construction Platform land development and other ancillary works at Sukani zone I and zone II in connection with Jal Jeevan Mission at sukani PWSS at Rajganj Block,under Jalpaiguri Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000792/2023-2024 | 2633/JD | 07/03/2024 | 22/03/2024 | D. S. ENTERPRISE | 12.81 | 12.74 | 99.51 | 100
91 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell site at Sukani Zone-III piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000007/2024-2025 | 420/JD | 12/06/2024 | 21/05/2025 | PARESH CHANDRA GHOSH ROY | 8.32 | 0 | 0 | 100
92 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Shifting AC pipes, Coumpound clearing ,Cutting trees ,Land development ,inter connection of IEP and other ancillary works at Sukani zone -II Head work site under Sukani piped water supply scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000806/2023-2024 | 2635/JD | 07/03/2024 | 22/03/2024 | A P CONSTRUCTION | 6.53 | 6.68 | 102.41 | 100
93 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | HDD Boring with MS pipe and other ancillary work at post office more of rajganj and fatapukur to belakoba road of sukani pwss under jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000056/2024-2025 | 937/JD | 07/08/2024 | 06/10/2024 | SANKAR DAS | 34.63 | 34.47 | 99.54 | 100
94 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Laying of Water Distribution System for interconnection work of left out portion and ancillary works of Augmentation of Sukani (Zone-I) PWSS at Block - Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000137/2024-2025 | 1532/JD | 01/10/2024 | 17/05/2025 | SUBRATA GOSWAMI | 13.17 | 0 | 0 | 100
95 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Construction of Boundary Wall with drain, land development including interconnection work at Augmentation of Sukani PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000125/2024-2025 | 1414/JD | 20/09/2024 | 20/10/2024 | D. S. ENTERPRISE | 10.17 | 0 | 0 | 100
96 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Supply, installation, commissioning copper wound line voltage corrector for AUGMETATION OF SUKHANI PWSS, at TW NO IV,ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000203/2024-2025 | 1379/NMD | 13/08/2024 | 01/07/2025 | NORDEN DUKPA | 3.62 | 0 | 0 | 100
97 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2024-2025 | 2221/JD | 01/12/2024 | 01/12/2024 | Resource Division | 88.05 | 0 | 0 | 0
98 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Infrastructure Cost for SUKHANI,T/W-I,ZONE-III under MAL CCC [APPLICATION NO. 100000101510, Reference ID : 860293810] |  |  | BILL/02495/2023-2024 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2 | 0 | 0 | 0
99 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Installation of Iron Elimination Plant (IEP) with Construction of Blower Room, Drain, Road including necessary connections and other ancillary work at Zone-I 4th Site of Sukani Piped Water Supply Scheme in connection with Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000186/2025-2026 | 2503/JD | 09/12/2025 | 06/08/2026 | D. S. ENTERPRISE | 25.17 | 0 | 0 | 35
100 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Interconnection work between M.S. and D.I. Pipe, construction valve chamber including filling at Sukani and other ancillary works at Ambari Falakata PWSS at Rajganj Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000566/2024-2025 | 130/JD | 16/01/2025 | 05/02/2025 | SANKAR DAS | 17.53 | 0 | 0 | 90
101 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme | SM/09995 | Augmentation | Shifting of 11 KV HTOH Line from PHE Overhead Reservoir Site I.E. at Sukhani as per Application of AE,HQ,PHE,Dte., Jalpaiguri. APPLICATION NO. 100000125722 , Reference ID : 860320252 |  |  | BILL/02007/2024-2025 | BP/24-25/250 | 21/01/2025 | 21/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.85 | 0 | 0 | 0
Total | [13 empty] | 4316.67 | 2180.32 | 50.51