## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd Tubewell by Reverse Rotary method of drilling for Augmentation of Sannyasikata PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000887/2021-2022 | 844/JD | 31/03/2022 | 21/04/2022 | DEBASISH DEY | 8.09 | 7.77 | 96.02 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd Tubewell by Reverse Rotary method of drilling for Augmentation of Sannyasikata PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000036/2022-2023 | 1020/JD | 26/04/2022 | 17/05/2022 | NARESH SEN | 8.09 | 7.92 | 97.97 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sannyasikata Zone-I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000050/2022-2023 | 1194/JD | 20/05/2022 | 04/07/2022 | MANAB BAKSHI | 4.65 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SANNYASIKATA (Z-II) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000559/2022-2023 | 1109/NMD | 07/09/2022 | 07/10/2022 | MALAY KUMAR SAHA | 8.26 | 8.26 | 100 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Providing Contractor's personnel as Field Supervisor engaged in different water supply Schemes under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 10.11.2022 to 10.04.2023) |  |  | ORD/000391/2022-2023 | 2186/JD | 10/11/2022 | 10/04/2023 | SUKES BASU MAJUMDAR | 0.94 | 0.47 | 50 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Construction of Pump House (3.60 m x 2.40 m ) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sannyasikata Zone-ii Water Supply Scheme under Jalpaiguri Division , P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000056/2022-2023 | 1195/JD | 20/05/2022 | 04/07/2022 | ETHERIA EDIFICE (OPC) PVT. LTD. | 4.65 | 4.65 | 100 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | CONSTRUCTION OF RCC OVERHEAD RESERVOIR CAPACITY 400 CUM AND 20 M STAGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPARMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SANNYASIKATA (ZONE I) PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ DISTRICT:JALPAIGURI UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2022-2023 | 876/JD | 05/04/2022 | 02/10/2022 | UMWELT ENGINEER PRIVATE LIMITED | 94.23 | 84.34 | 89.51 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Laying distribution system with FHTC for Augmentation of Sannyasikata Piped water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000060/2022-2023 | 1228/JD | 01/06/2022 | 29/09/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 788.85 | 629.96 | 79.86 | 100
9 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SANNYASIKATA W/S Scheme at T/W No. III, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000266/2022-2023 | 1011/NMD | 28/07/2022 | 18/08/2022 | M/S CHANDRANATH MUKHERJEE | 2.18 | 2.18 | 100 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir at Sannyasikata Zone-I under Sannyasikata piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000168/2022-2023 | 1414/JD | 13/07/2022 | 28/07/2022 | M.K. KAYAL & ASSOCIATES | 2.26 | 2.11 | 93.51 | 1
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Laying distribution system for Augmentation of Sannyasikata Piped water Supply Scheme Zone-I at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000034/2022-2023 | 1100/JD | 12/05/2022 | 10/08/2022 | UMWELT ENGINEER PRIVATE LIMITED | 540.04 | 506.81 | 93.85 | 100
12 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SANNYASIKATA W/S Scheme at T/W No. III, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000268/2022-2023 | 1012/NMD | 28/07/2022 | 18/08/2022 | M/S RATAN KUMAR DASGUPTA AND CO. | 2.77 | 2.77 | 100 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir at Sannyasikata Zone-II under Sannyasikata piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000169/2022-2023 | 1413/JD | 13/07/2022 | 28/07/2022 | MABCO CONSULTANT | 2.26 | 2.11 | 93.51 | 1
14 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SANNYASIKATA (Z-I) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000531/2022-2023 | 1067/NMD | 29/08/2022 | 28/09/2022 | DEY ENTERPRISE(MALDA) | 8.01 | 8.01 | 100 | 100
15 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Installation of Infrastructure COST at SANYASIKATA ZONE-II W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 100000060680, Reference ID : 860250380] |  |  | VCH/000982/2022-2023 | BP/22-23/92 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.1 | 0 | 0 | 0
16 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | New Service Connection Charge for SANYASIKATA ZONE-I W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 4002969126, Reference ID :402855384] |  |  | VCH/000983/2022-2023 | BP/22-23/92 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.66 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | New Service Connection Charge for SANYASIKATA ZONE-II W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 4002970357, Reference ID :402858305] |  |  | VCH/000981/2022-2023 | BP/22-23/92 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Installation of Infrastructure COST at SANYASIKATA ZONE-I W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 100000060668, Reference ID : 860250378] |  |  | VCH/000984/2022-2023 | BP/22-23/92 | 01/11/2022 | 01/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.55 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of different stationary for office use under Jalpaiguri division, P.H.E. Dte. as per annexure- I. |  |  | ORD/000503/2022-2023 | 358/JD | 17/02/2023 | 24/02/2023 | SUBRATA ART PRESS | 1.64 | 0 | 0 | 1
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sannyasikata (Zone-I) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2023-2024 | 840/JD | 04/04/2023 | 01/03/2025 | ARUP SARKAR | 10.16 | 7.98 | 78.6 | 50
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-I under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000279/2023-2024 | 1020/JD | 21/08/2023 | 05/10/2023 | M/S M.B. DESIGN | 33.17 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of different stationary for office use under Jalpaiguri Division, P.H.E. Dte. as per Annexure- I. |  |  | ORD/000502/2022-2023 | 357/JD | 17/02/2023 | 24/02/2023 | JAGRITI PRESS | 1.71 | 1.71 | 100 | 1
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-I under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000356/2023-2024 | 1432/JD | 05/10/2023 | 26/02/2025 | M/S M.B. DESIGN | 33.17 | 30.24 | 91.16 | 85
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-II under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000332/2023-2024 | 1353/JD | 26/09/2023 | 10/11/2023 | RAGHU DAS | 48.86 | 49.55 | 101.41 | 100
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sannyasikata (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000018/2023-2024 | 62/JD | 18/04/2023 | 01/11/2025 | RANJIT KARMAKAR | 31.21 | 24.05 | 77.06 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 1233/JD | 12/09/2023 | 12/09/2023 | Resource Division | 41 | 0 | 0 | 0
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | HIRE CHARGES BILL OF VEHICLE UNDER NBC-I, PHE Dte. For the month of june to august 2023 |  |  | BILL/00615/2023-2024 | BP-2023-24-418 | 06/10/2023 | 06/10/2023 | RUPA PRASAD | 1.03 | 0 | 0 | 0
28 | JALPAIGURI |  | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | ADDITIONAL Infrastructure Cost for SANYASHI KATA, ZONE-I,T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000091299, Reference ID : 860282879] |  |  | BILL/01168/2023-2024 | BP/23-24/143 | 06/11/2023 | 06/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0 | 0
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000566/2023-2024 | 2128/JD | 18/01/2024 | 18/07/2024 | MD AMIRUL ISLAM | 0.88 | 0.98 | 110.94 | 30
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Construction of Different Component of water supply work and other ancillary work at Kalinagar Hospital More at Sannyasikata Zone-II under Sannyasikata PWSS of Rajganj Block under Jalpaiguri Division PHE, Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000828/2023-2024 | 2756/JD | 15/03/2024 | 16/09/2025 | SHREE KRISHNA ENTERPRISE | 75.06 | 0 | 0 | 75
31 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | CONSTRUCTION OF RCC OVERHEAD RESERVOUR CAPACITY 550 CUM AND 20 M STAGING HEIGHT INCLUDING AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SANNYASIKATA (ZONE- II) PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ ,DISTRICT,JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000691/2023-2024 | 2393/JD | 16/02/2024 | 14/08/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 113.02 | 0 | 0 | 0
32 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 22.07.2024 to 21.01.2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000033/2024-2025 | 659/JD | 12/07/2024 | 12/01/2025 | MD AMIRUL ISLAM | 0.88 | 0.92 | 104.49 | 0
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying pipe line for Sannyasikata zone II H/W Site at Sannyasikata PWSS Site piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000120/2024-2025 | 1419/JD | 20/09/2024 | 14/02/2025 | PRABIR SHOME | 18.38 | 0 | 0 | 0
34 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell Site at Sannyasikata Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000613/2023-2024 | 2312/JD | 07/02/2024 | 08/03/2024 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.81 | 0 | 0 | 100
35 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for H/W Site at Sannyasikata Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000810/2023-2024 | 2630/JD | 07/03/2024 | 26/12/2024 | SADHAN KARMAKAR | 26.72 | 18.21 | 68.15 | 85
36 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Interconnection of Iron Elimination Plant to Rising Main, and other Ancillary Works at Sannyasikata Zone-II Head Work Site at Sannyasikata PWSS Rajganj Block, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000131/2024-2025 | 1285/JD | 03/09/2024 | 03/10/2024 | RAGHU DAS | 8.11 | 7.98 | 98.41 | 100
37 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2024-2025 | 2207/JD | 01/12/2024 | 01/12/2024 | Resource Division | 39.29 | 0 | 0 | 0
38 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of Fuel (Diesel) ofVehicle No. WB 71 A 5131 for the Month of August 2024. |  |  | BILL/00656/2024-2025 | BP-2024-25-370 | 13/09/2024 | 13/09/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
39 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of September 2024. |  |  | BILL/00853/2024-2025 | BP-2024-25-482 | 07/10/2024 | 07/10/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
40 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of Fuel (Diesel) of Vehicle No WB 71 A 5131 for the Month of July 2024. |  |  | BILL/00583/2024-2025 | BP-2024-25-333 | 28/08/2024 | 28/08/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
41 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of October 2024. |  |  | BILL/00940/2024-2025 | BP-2024-25-524 | 29/11/2024 | 29/11/2024 | FILL & SMILE | 0.17 | 0 | 0 | 0
42 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 01.03.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000687/2024-2025 | 71/HQ/JD | 28/02/2025 | 31/03/2025 | MD AMIRUL ISLAM | 0.15 | 0 | 0 | 0
43 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 22.01.2025 to 28.02.2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000595/2024-2025 | 15/HQ/JD | 20/01/2025 | 27/02/2025 | MD AMIRUL ISLAM | 0.19 | 0.19 | 99.8 | 0
44 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of Fuel (Diesel) & Mobil Oil of Vehicle No. WB 71 A 5131 for the Month of December 2024. |  |  | BILL/01097/2024-2025 | BP-2024-25-598 | 21/01/2025 | 21/01/2025 | FILL & SMILE | 0.25 | 0 | 0 | 0
45 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of January 2025. |  |  | BILL/01334/2024-2025 | BP-2024-25-663 | 27/03/2025 | 27/03/2025 | FILL & SMILE | 0.23 | 0 | 0 | 0
46 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of November 2024. |  |  | BILL/01045/2024-2025 | BP-2024-25-579 | 14/01/2025 | 14/01/2025 | FILL & SMILE | 0.23 | 0 | 0 | 0
47 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme | SM/09996 | Augmentation | Supply of Fuel (Diesel) & Mobil Oil of Vehicle No. WB 71 A 5131 for the Month of February 2025. |  |  | BILL/01336/2024-2025 | BP-2024-25-660 | 27/03/2025 | 27/03/2025 | FILL & SMILE | 0.25 | 0 | 0 | 0
Total | [13 empty] | 1980.6 | 1409.19 | 71.15