## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000712/2021-2022 | 2225/JD | 27/12/2021 | 25/02/2022 | ARATI CONSTRUCTION | 11.44 | 11.42 | 99.83 | 1
2 | JALPAIGURI |  | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHYA KHAGRABARI W/S SCHEME (TW-II), MAYNAGURI BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000014/2022-2023 | 473/CDD | 25/05/2022 | 24/06/2022 | PADMA ENGINEERING & CO. | 10.64 | 8.15 | 76.58 | 0
3 | JALPAIGURI |  | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | ADDITIONAL TRANSPORTATION OF DEPARTMENTAL RIG M/C & ACCESSORIES INCLUDING LOADING & UNLOADING FROM MADHYA KHAGRABARI TW-II SITE TO UTTARTAJPUR W/S SCH, UNDER CDD, PHE DTE. |  |  | ORD/000225/2022-2023 | 186/CMSD-I | 10/06/2022 | 17/06/2022 | PADMA ENGINEERING & CO. | 0.8 | 0.77 | 96.71 | 0
4 | JALPAIGURI |  | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOT CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHYA KHAGRABARI W/S SCH (TW-I), MAYNAGURI BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000171/2022-2023 | 472/CDD | 25/05/2022 | 24/06/2022 | PADMA ENGINEERING & CO. | 10.64 | 9.34 | 87.78 | 0
5 | JALPAIGURI |  | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | SINKING OF 800MM DIA SHALLOW TUBEWELL FOR REQUIREMENT OF DRILLING WATER FOR DIFFERENT CONSTRUCTION OF TUBE WELL AT MAYNAGURI BLOCK IN JALPAIGURI DISTRICT, UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000261/2021-2022 | 575/CMSD-II | 30/11/2021 | 10/12/2021 | PADMA ENGINEERING & CO. | 0.96 | 0.48 | 50 | 0
6 | JALPAIGURI |  | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | New Service Connection Charge for MADHA KHAGRABARI W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 4002941289, Reference ID : 402831971] |  |  | VCH/000896/2022-2023 | BP/22-23/62 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | New Service Connection Charge for MADHA KHAGRABARI W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 4002941293, Reference ID : 402831977] |  |  | VCH/000898/2022-2023 | BP/22-23/62 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Providing car on daily hire basis @12.00/Km for official use of the office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte |  |  | VCH/000555/2022-2023 | BP-2022-23-155 | 02/09/2022 | 02/09/2022 | RAKESH SARKAR | 0.19 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Installation of Infrastructure COST at MADHA KHAGRABARI W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 100000059497, Reference ID : 860245057] |  |  | VCH/000899/2022-2023 | BP/22-23/62 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | LDS REJ NAGRAKATA |  |  | VCH/001261/2021-2022 | BP-2021-22-517 | 30/03/2022 | 30/03/2022 | UDAYAN BOSE | 6.91 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Installation of Infrastructure COST at MADHA KHAGRABARI W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 100000059498, Reference ID : 860245058] |  |  | VCH/000897/2022-2023 | BP/22-23/62 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.04 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000711/2021-2022 | 223/JD | 24/01/2022 | 25/03/2022 | SOMNATH ROY | 11.44 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHYA KHAGRABARI PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000119/2022-2023 | 856/NMD | 18/07/2022 | 17/08/2022 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 7.87 | 7.01 | 89.14 | 80
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th T/W Site of Madhya Khagrabari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000423/2022-2023 | 680/JD | 16/03/2023 | 30/04/2023 | M/S RATAN KUMAR DAS GUPTA AND CO | 16.43 | 15.36 | 93.49 | 80
15 | JALPAIGURI |  | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 250 mtrs. Depth) by utilising Departmental machineries for Kharagpur SG Hospital W/S Scheme, under Paschim Midnapore District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000434/2022-2023 | 1350/CDD | 24/11/2022 | 24/12/2022 | PADMA ENGINEERING & CO. | 18.38 | 3.54 | 19.25 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Construction of 550 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MADHYA KHAGRABARI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000329/2021-2022 | 186/JD | 21/01/2022 | 21/05/2022 | M/S A.B.G. CONSTRUCTION | 108.63 | 69.86 | 64.31 | 1
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PH.E Dte Jalpaiguri (with valid Taxi permit). Period from 01/10/2022 to 31/01/2023 | Assistant Engineer | Junior Engineer | ORD/000249/2022-2023 | 616/RWS | 29/09/2022 | 29/01/2023 | APIKUL ALI | 0.59 | 0.49 | 82.63 | 1
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Work of DI Pipe (Raising main), Drain, Chamber, flower block & other ancillary works at 4th site of Madhya khagrabari piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000151/2023-2024 | 816/RWS | 14/07/2023 | 28/07/2023 | ARATI CONSTRUCTION | 2.65 | 2.65 | 99.86 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Construction of pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001107/2021-2022 | 2224/JD | 23/12/2021 | 21/02/2022 | SOMNATH ROY | 11.44 | 11.43 | 99.89 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 179/JD | 21/01/2022 | 21/01/2022 | Resource Division | 127.45 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 551/JD | 01/03/2022 | 01/03/2022 | Resource Division | 27.35 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | SUPPLY OF FUEL |  |  | BILL/00396/2022-2023 | BP-2022-23-545 | 25/03/2023 | 25/03/2023 | FILL & SMILE | 0.3 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | SUPPLY OF FUEL |  |  | BILL/00397/2022-2023 | BP-2022-23-544 | 25/03/2023 | 25/03/2023 | FILL & SMILE | 0.25 | 0 | 0 | 0
24 | JALPAIGURI |  | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Madhya Khagrabari W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000094/2022-2023 | 564/NMD | 14/07/2022 | 04/08/2022 | SUBODH KUMAR BANIK | 2.19 | 0 | 0 | 100
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd T/W Site of Madhya Khagrabari water supply scheme under Jalpaiguri | Assistant Engineer | Junior Engineer | ORD/000419/2022-2023 | 135/JD | 17/01/2023 | 03/03/2023 | M/S SURAJIT DEY AND CO. | 16.44 | 15.36 | 93.42 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Madhya khagrabari piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000152/2023-2024 | 817/RWS | 14/07/2023 | 28/07/2023 | SOMNATH ROY | 2.65 | 2.6 | 97.89 | 100
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | ADDITIONAL WORK FOR LAYING & DISTRIBUTION SYSTEM IN MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME BLOCK : MAYNAGURI DISTRICT : JALPAIGURI. | Assistant Engineer | Junior Engineer | ORD/000536/2023-2024 | 1895/JD | 20/12/2023 | 04/01/2024 | JAYA SARKAR | 9 | 9.1 | 101.07 | 100
28 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2024-2025 | 2214/JD | 01/12/2024 | 01/12/2024 | Resource Division | 22.14 | 0 | 0 | 0
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-C`). | Assistant Engineer | Junior Engineer | ORD/000339/2021-2022 | 213/JD | 24/01/2022 | 11/03/2025 | NARAYAN CHANDRA SAHA | 169.95 | 98.07 | 57.71 | 75
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-B). | Assistant Engineer | Junior Engineer | ORD/000335/2021-2022 | 189/JD | 21/01/2022 | 31/03/2026 | M/S A.B.G. CONSTRUCTION | 181.29 | 94.98 | 52.39 | 100
31 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-A). | Assistant Engineer | Junior Engineer | ORD/000336/2021-2022 | 194/JD | 21/01/2022 | 01/04/2025 | M/S A.B.G. CONSTRUCTION | 173.57 | 51.19 | 29.49 | 100
32 | JALPAIGURI |  | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHYA KHAGRABARI PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000118/2022-2023 | 855/NMD | 18/07/2022 | 01/12/2024 | GOENKA ENTERPRISE | 7.87 | 6.32 | 80.25 | 100
33 | JALPAIGURI |  | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. | SM/10028 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Madhya Khagrabari W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2022-2023 | 563/NMD | 14/07/2022 | 01/12/2024 | MUSTAFI CONCERN | 2.16 | 0 | 0 | 100
Total | [13 empty] | 981.74 | 418.11 | 42.59