## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Installation of Iron Elimination Plant (IEP) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. in addition ancillary pipe line works (i.e. CIDF pipe line, construction of valve chamber etc.) at Head Work Site Augmentation of Maynaguri (Zone-II) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000474/2021-2022 | 397/JD | 10/02/2022 | 27/03/2022 | SUKES BASU MAJUMDAR | 39.13 | 12.95 | 33.1 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Sinking of 2 No. 300 mm x 200 mm x 128 m deep Rig Bored tubewell by Reverse Rotary method of drilling for Augmentation of Maynaguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000127/2022-2023 | 1393/JD | 05/07/2022 | 26/07/2022 | B.M CONSTRUCTION | 19.95 | 19.62 | 98.34 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Construction of Rig approach with partial land development for 1st site & 2nd site under Maynaguri piped Water Supply Scheme within Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000183/2022-2023 | 562/RWS | 01/09/2022 | 16/09/2022 | B.M CONSTRUCTION | 3.56 | 3.54 | 99.47 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Laying of new pipe line beside diversion of PWD road (damaged by PWD for connection of sasan road culvert under Maynaguri Water Supply Scheme (Zone-I). | Assistant Engineer | Junior Engineer 2 | ORD/000184/2022-2023 | 563/RWS | 01/09/2022 | 01/10/2022 | B.M CONSTRUCTION | 1.16 | 1.03 | 88.71 | 1
5 | JALPAIGURI |  | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under MAYNAGURI (AUG) W/S Scheme, at ZONE-I, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000066/2022-2023 | 441/NMD | 14/06/2022 | 05/07/2022 | M/S P.P. ELECTRICALS | 2.99 | 2.99 | 100 | 0
6 | JALPAIGURI |  | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under MAYNAGURI (AUG) W/S Scheme, at ZONE-I, TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000065/2022-2023 | 440/NMD | 14/06/2022 | 05/07/2022 | UTTAM PAUL | 2.99 | 2.99 | 100 | 0
7 | JALPAIGURI |  | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of MAYNAGURI (ZONE-I) PWSS, at TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000079/2022-2023 | 537/NMD | 08/07/2022 | 07/08/2022 | ALPHA ENTERPRISE | 8.6 | 8.6 | 100 | 0
8 | JALPAIGURI |  | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of MAYNAGURI (ZONE-I) PWSS, at TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000080/2022-2023 | 538/NMD | 08/07/2022 | 07/08/2022 | B.B. CONCERNED | 8.6 | 8.6 | 100 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of different Chemicals (Lime) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001056/2021-2022 | 07/RWS | 04/01/2022 | 04/04/2022 | SUKES BASU MAJUMDAR | 0.73 | 0.73 | 100 | 1
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of different Chemicals (Bleaching Powder) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 | Assistant Engineer | Junior Engineer 2 | ORD/000290/2022-2023 | 13/RWS | 03/11/2022 | 03/02/2023 | BHOWMIK ENTERPRISES | 0.4 | 0.4 | 100 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of different Chemicals (Bleaching powder) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001057/2021-2022 | 11/RWS | 04/01/2022 | 04/04/2022 | SADHAN KARMAKAR | 0.4 | 0.4 | 100 | 1
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of different Chemicals (Alam) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001058/2021-2022 | 10/RWS | 04/01/2022 | 04/04/2022 | A.P CONSTRUCTION | 0.24 | 0.24 | 100 | 1
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of different Chemicals (Lime) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001059/2021-2022 | 09/RWS | 04/01/2022 | 04/04/2022 | PROFULLA GHOSH | 0.26 | 0.26 | 100 | 1
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 2nd Tube well site of Augmentation Maynaguri (Zone-I) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000708/2021-2022 | 2208/JD | 27/12/2021 | 25/02/2022 | PRIYABRATA KARMAKAR | 11.45 | 7.78 | 67.95 | 1
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | CONST RCC KHALAIGRAM |  |  | VCH/001397/2021-2022 | BP-2021-22-555 | 31/03/2022 | 31/03/2022 | DULAL CHOUDHURY | 4.48 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | SOIL TEST MAYNAGURI PWSS |  |  | VCH/001441/2021-2022 | BP-2021-22-484 | 29/03/2022 | 29/03/2022 | PRIYA ASSOCITED | 1.69 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | LAYING OF NEW PIPE LINE CHAMURCHI BAZAR W/S/S |  |  | VCH/001405/2021-2022 | BP-2021-22-556 | 31/03/2022 | 31/03/2022 | NARAYAN CHANDRA SAHA | 13.02 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | supply of fuel |  |  | VCH/000595/2022-2023 | BP-2022-23-375 | 18/11/2022 | 18/11/2022 | FILL & SMILE | 0.29 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | New Service Connection Charge for T/W No.I of MAYNAGURI SUPER MARKET under MAYNAGURI CCC, APPLICATION NO. 4002930314, Reference ID : 402824634 |  |  | VCH/000255/2022-2023 | BP/2022-23/22 | 28/06/2022 | 28/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
20 | JALPAIGURI |  | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | New Service Connection Charge for T/W No. II of MAYNAGURI NEAR DHARMASHALA under MAYNAGURI CCC, APPLICATION NO. 4002932365, Reference ID : 402825215 |  |  | VCH/000254/2022-2023 | BP/2022-23/22 | 28/06/2022 | 28/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
21 | JALPAIGURI |  | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-II, of MAYNAGURI NEAR DHARMASAKA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000057038 , Reference ID : 860246648] |  |  | VCH/000773/2022-2023 | BP/2022-23/29 | 16/08/2022 | 16/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
22 | JALPAIGURI |  | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Infrastructure cost for New Service Connection Charge for T/W No. I of MAYNAGURI SUPER MARKET under MAYNAGURI CCC, APPLICATION NO. 100000052512, Reference ID : 860241672 |  |  | VCH/000250/2022-2023 | BP/2022-23/20 | 23/06/2022 | 23/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.65 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | KAYING OF PIPELINE FOR MADHABDANGA PWSS |  |  | VCH/001258/2021-2022 | BP-2021-22-404 | 23/03/2022 | 23/03/2022 | M/S SIBU DEY AND CO. | 2.65 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | LDS FHTC RAMSAI PART - II |  |  | VCH/001315/2021-2022 | BP-2021-22-427 | 25/03/2022 | 25/03/2022 | ASHIT KUMAR SINGHA | 64.85 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Laying Distribution System with higher dia HDPE pipe to promot Augmentation of Maynaguri (Zone-I) Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer 2 | ORD/000276/2022-2023 | 641/RWS | 21/10/2022 | 20/11/2022 | M/S SURAJIT DEY AND CO. | 3.27 | 2.18 | 66.67 | 0
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Laying Distribution System with higher dia HDPE pipe to promot Augmentation of Maynaguri (Zone-I) Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer 2 | ORD/000275/2022-2023 | 640/RWS | 21/10/2022 | 20/11/2022 | M/S SURAJIT DEY AND CO. | 4 | 4 | 100 | 0
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MAYNAGURI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer 2 | ORD/000333/2021-2022 | 205/JD | 24/01/2022 | 24/05/2022 | SUKES BASU MAJUMDAR | 97.41 | 94.45 | 96.96 | 1
28 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Construction of Boundary wall, Pump House and Installation of Iron Elimination Plant (IEP) including construction of Blower Room (3.60M x 3.00M) Size, concrete platform & drain etc. in addition ancillary pipe line works (i.e. CIDF pipe line, construction of valve chamber etc.) at Head Work Site Augmentation of Maynaguri (Zone-I) Water Supply Scheme under Jalpaiguri division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000126/2022-2023 | 1392/JD | 05/07/2022 | 04/08/2022 | SUKES BASU MAJUMDAR | 77.4 | 63.44 | 81.96 | 1
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of different Chemicals (Alam) for I.E.P at Head Work site under Maynaguri W/S/S for 3 months under Jalpaiguri Division P.H.E. Dte. Period from - 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001055/2021-2022 | 08/RWS | 04/01/2022 | 04/04/2022 | SUKES BASU MAJUMDAR | 0.67 | 0.67 | 100 | 1
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Extension of pipe lines at different locations and provision of a new by pass line near NBSTC Bus Depot to facilitate FHTC L.c.w. JJM under Augmentation of Maynaguri Water Supply Scheme, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000007/2023-2024 | 331/RWS | 10/04/2023 | 24/04/2023 | ARUP SARKAR | 2.96 | 2.96 | 100 | 100
31 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 178/JD | 21/01/2022 | 21/01/2022 | Resource Division | 69.48 | 0 | 0 | 0
32 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | SUPPLY OF ALL TYPES OF PETROLEUM PRODUCTS |  |  | BILL/00354/2022-2023 | BP-2023-24-112 | 17/05/2023 | 17/05/2023 | M/S MILLENNIUM FUEL CENTRE | 1.03 | 0 | 0 | 0
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | SUPPLY OF DIFFERENT STATINARY ITEMS FOR OFFICE USE UNDER JALPAIGURI DIVISION P.H.E DTE. |  |  | BILL/00963/2023-2024 | BP-2023-24-548 | 20/12/2023 | 20/12/2023 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 3.53 | 0 | 0 | 0
34 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Rising Main Connection for Augmentation of Maynaguri (Zone-I) piped Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri | Assistant Engineer | Junior Engineer 2 | ORD/000378/2022-2023 | 243/JD | 04/02/2023 | 06/03/2023 | ARATI CONSTRUCTION | 3.57 | 3.56 | 99.68 | 100
35 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Replacement of old damaged pipe by new HDPE Pipe line at Sahidgarh area, Ward no. 15 under Augmentation of Maynaguri Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000008/2023-2024 | 333/RWS | 10/04/2023 | 01/05/2023 | SUKES BASU MAJUMDAR | 4.95 | 5.06 | 102.3 | 100
36 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2024-2025 | 2210/JD | 01/12/2024 | 01/12/2024 | Resource Division | 44.3 | 0 | 0 | 0
37 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | SUPPLY OF DIFFERENT STATIONARY ITEMS FOR OFFICE USE UNDER JALPAIGURI R.W.S SUB DIVISION, P.H.E. Dte. |  |  | BILL/01006/2023-2024 | BP-2023-24-573 | 09/01/2024 | 09/01/2024 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.21 | 0 | 0 | 0
38 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). |  |  | BILL/01017/2023-2024 | BP-2023-24-575 | 09/01/2024 | 09/01/2024 | SOUMEN GHOSH | 0.68 | 0 | 0 | 0
39 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of Fuel Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte. |  |  | BILL/00391/2024-2025 | BP-2024-25-242 | 26/07/2024 | 26/07/2024 | FILL & SMILE | 0.29 | 0 | 0 | 0
40 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | SUPPLY OF FUEL (DIESEL) FOR VEHICLES FOR P.H.E JALPAIGURI |  |  | BILL/00985/2023-2024 | BP-2023-24-563 | 05/01/2024 | 05/01/2024 | FILL & SMILE | 2.6 | 0 | 0 | 0
41 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of Fuel & lubricant for EXECUTIVE ENGINEER , P.H.E Dte. JALPAIGURI |  |  | BILL/01018/2023-2024 | BP-2023-24-578 | 10/01/2024 | 10/01/2024 | FILL & SMILE | 0.83 | 0 | 0 | 0
42 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | FUEL BILL FOR GOVT. VEHICLE FOR THE MONTH OF NOVEMBER-2023 |  |  | BILL/01007/2023-2024 | BP-2023-24-571 | 09/01/2024 | 09/01/2024 | FILL & SMILE | 0.17 | 0 | 0 | 0
43 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) |  |  | BILL/01016/2023-2024 | BP-2023-24-574 | 09/01/2024 | 09/01/2024 | APIKUL ALI | 0.37 | 0 | 0 | 0
44 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00392/2024-2025 | BP-2024-25-241 | 26/07/2024 | 26/07/2024 | FILL & SMILE | 0.02 | 0 | 0 | 0
45 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Laying Distribution System and Functional House Hold Tap Connection for Augmentation of Maynaguri (Zone-II) Piped Water Supply Scheme. Block- Maynaguri. District - Jalpaiguri. | Assistant Engineer | Junior Engineer 2 | ORD/000350/2021-2022 | 226/JD | 25/01/2022 | 02/06/2025 | M/S SURAJIT DEY AND CO. | 197.94 | 66.23 | 33.46 | 100
46 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Laying Distribution System and Functional House Hold Connection for Augmentation of Maynaguri (Zone-I) Piped Water Supply Scheme Block- Maynaguri, Dist. Jalpaiguri. | Assistant Engineer | Junior Engineer 2 | ORD/000349/2021-2022 | 225/JD | 25/01/2022 | 02/06/2025 | M/S SURAJIT DEY AND CO. | 197.12 | 107.65 | 54.61 | 100
47 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Laying Distribution line crossing through Bridge and main distribution connections at Augmentation of Maynaguri Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000095/2024-2025 | 814/RWS | 22/08/2024 | 21/09/2024 | M/S SURAJIT DEY AND CO. | 8.68 | 0 | 0 | 100
48 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. | SM/10042 | Augmentation | Continuation work order for "Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01/02/2025 to 31/07/2025)" | Assistant Engineer | Junior Engineer | ORD/000673/2024-2025 | 76/RWS | 30/01/2025 | 30/07/2025 | ASHIM SARKAR | 0.88 | 0.44 | 50 | 32
Total | [13 empty] | 916.2 | 420.78 | 45.93