## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Emergency reparing and laying of distribution system near Gadi khana parallel to the Hatinala and indian oil pipeline in connection with for augmentation of Banarhat Bazar PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000439/2022-2023 | 681/JD | 16/03/2023 | 06/04/2023 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 5.54 | 5.53 | 99.82 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Emergent minor repairing of Pump House and Chlorine room with Construction of Toilet and Sanitary plumbing system located near Banarhat Thana and repairing works of Pump House near Banarhat Panchayat Office with other ancillary works for Augmentation of Banarhat Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000097/2022-2023 | 1305/JD | 14/06/2022 | 05/07/2022 | SANKAR DAS | 3.54 | 3.5 | 98.79 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1096/JD | 24/08/2023 | 24/08/2023 | Resource Division | 106.7 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | New Service Connection Charge for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 4003103092, Reference ID : 402976412] |  |  | BILL/00785/2022-2023 |  | 20/03/2023 | 20/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | New Service Connection Charge for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 4003103092, Reference ID : 402976412] |  |  | BILL/00464/2023-2024 | BP/23-24/31 | 09/06/2023 | 09/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Infrastructure Cost for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 100000073457, Reference ID : 860265207] |  |  | BILL/00465/2023-2024 | BP/23-24/46 | 04/07/2023 | 04/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.12 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Infrastructure Cost for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 100000073457, Reference ID : 860265207] |  |  | BILL/00786/2022-2023 |  | 20/03/2023 | 20/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.12 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Infrastructure Cost for BANERHAT BAZAR NEAR BDO OFFICE, T/W IV, ZONE - I, under BANARHAT CCC [APPLICATION NO. 100000083816 ; Reference ID : 860275316] |  |  | BILL/01000/2023-2024 | BP/23-24/114 | 06/10/2023 | 06/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.11 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | New Service Connection Charge for BANERHAT BAZAR NEAR BDO OFFICE, T/W IV, ZONE - I, under BANARHAT CCC [APPLICATION NO. 4003103095 ; Reference ID : 402976411] |  |  | BILL/00999/2023-2024 | BP/23-24/114 | 06/10/2023 | 06/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Laying distribution system with Rising Main Connection, of Banarhat Bazar ( Zone-I) Piped water Supply Scheme , at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000338/2022-2023 | 2518/JD | 30/12/2022 | 02/01/2026 | PRADIP SAHA | 68.1 | 33.17 | 48.71 | 70
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Laying distribution system with Rising Main Connection of Banarhat Bazar (Zone-II) Piped water supply Scheme, at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000293/2022-2023 | 2051/JD | 02/11/2022 | 21/02/2025 | GLOBAL POWER & CONSTRUCTION CO. | 108.22 | 71.76 | 66.3 | 41
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Construction of 350 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing and Boundary Wall with land development at Head Works site for Augmentation of Banarhat Bazar (zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000331/2022-2023 | 2486/JD | 28/12/2022 | 27/05/2023 | PRADIP SAHA | 107.22 | 102.52 | 95.62 | 95
13 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Banerhat Bazar PWSS at TW-IV (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Driller-in-Charge | Junior Engineer | ORD/000812/2022-2023 | 313/DSD | 06/03/2023 | 16/03/2023 | M/S MATRI CONSTRUCTION | 0.49 | 0.49 | 100 | 100
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Laying of Rising Main Connection between Head works Pump House site and Tube Well site including Internal Pump Connection along with Construction of Pump House for Zone-I of Augmentation of Banarhat PWSS i.c.w. Jal Jeevan Mission at under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000393/2022-2023 | 569/JD | 03/03/2023 | 24/03/2023 | PARAMJYOTI ENTERPRISE | 9.04 | 8.42 | 93.11 | 100
15 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BANERHAT BAZAR PWSS, AT TW no IV (ZONE-I) AND AT TW NO I (ZONE-II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000889/2022-2023 | 372/NMD | 29/03/2023 | 28/04/2023 | ANIMA ENTERPRISE | 20.46 | 20.46 | 100 | 100
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Construction of Pump House (5.40m x 3.60m) internal size with sanitary & plumbing arrangement at Head work site and Providing Functional Household Tap Connection (FHTC) for Augmentation of Banarhat Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000531/2023-2024 | 1851/JD | 15/12/2023 | 02/09/2024 | SOUVIK SAHA | 10.02 | 9.65 | 96.22 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Providing Functional Household Tap Connection in Connection with Jal Jeevan Mission for Augmentation of Banerhat Bazar Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000667/2023-2024 | 2459/JD | 23/02/2024 | 02/09/2024 | PRADIP SAHA | 19.04 | 0 | 0 | 100
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Augmentation of Banerhat Bazar Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ |  | ORD/000586/2023-2024 | 2335/JD | 08/02/2024 | 23/02/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 16.67 | 100.2 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Interconnection work to connect Pump House, reservoir and distribution network and other allied work of Banarhat Bazar zone- II piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000824/2023-2024 | 2752/JD | 14/03/2024 | 29/03/2024 | PRADIP SAHA | 18.08 | 16.27 | 90 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Construction of Approach Culvert at Head Work Site of Banarhat Bazar Zone-II PWSS in Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000123/2024-2025 | 1273 | 03/09/2024 | 03/10/2024 | PRADIP SAHA | 8.67 | 6.41 | 73.95 | 100
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Minor Repairing of Overhead Reservoir, Boundary Wall and Pathway and Allied Works under Augmentation of Banarhat Bazar Zone - I in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000121/2024-2025 | 1266/JD | 02/09/2024 | 02/10/2024 | PRADIP SAHA | 8.05 | 7.69 | 95.49 | 100
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2024-2025 | 2211/JD | 01/12/2024 | 01/12/2024 | Resource Division | 24.1 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Shifting and Extension of pipeline for widening and strengthening of B.R.O Road From Chamurchi More to Moraghat More along with other L.D.S. Repairing and other anciellary works related to L.D.S. within the command area of Augmentation of Banerhat Piped Water Supply Scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000242/2022-2023 | 1949/JD | 13/10/2022 | 02/04/2025 | SANKAR DAS | 8.96 | 5.79 | 64.57 | 100
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Providing Functional Household Tap Connection in Connection with Jal Jeevan Mission for Augmentation Banerhat Bazar Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000008/2024-2025 | 421/JD | 12/06/2024 | 12/07/2024 | PRADIP SAHA | 19.04 | 0 | 0 | 60
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Sinking of five nos Tube Well by Odex- 165 method of drilling at different Tube Well site in connection with jal jeevan mission under Augmentation/Rejuvenation of Kathalguri TG PWSS (Two Nos), Devpara TG PWSS (One No), Banarhat Bazar PWSS (One No), Sajna Para PWSS (One No) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2023-2024 | 1520/JD | 16/10/2023 | 30/04/2025 | ROY ENGINEERS | 41.28 | 6.52 | 15.79 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Construction of Pump Houses, Boundary wall (2nd Site), Drain, & Pathway etc. at Banarhat Bazar PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000554/2024-2025 | 2281/JD | 05/12/2024 | 02/02/2025 | PRADIP SAHA | 27.89 | 0 | 0 | 100
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | Laying of Pipeline for Crossing Culvert, including supply of CIDF specials and other allied works at Grassmore Tea Garden Piped Water Supply Scheme, in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000368/2024-2025 | 2013/JD | 18/11/2024 | 29/03/2025 | PRADIP SAHA | 2.93 | 0 | 0 | 100
28 | JALPAIGURI |  | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme | SM/10044 | Augmentation | New Service Connection Charge for BANARHAT BAZAR ZONE -II, T/W-II under BANARHAT CCC. APPLICATION NO. 4003541407 Reference ID : 403314044 |  |  | BILL/01499/2024-2025 | BP/24-25/247 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.91 | 0 | 0 | 0
Total | [13 empty] | 644.32 | 314.83 | 48.86