## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd tube well site for Rejuvenation of Jurantee Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000596/2022-2023 | 05/JSSD | 16/05/2022 | 30/06/2022 | RAJAT GHOSH | 4.65 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Sinking of Two Nos. 183 mm x 125mm dia 120 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Jurantee Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000590/2021-2022 | 737/JD | 17/03/2022 | 16/04/2022 | ASHIS DUTTA | 13.5 | 0 | 0 | 100
3 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Laying Distribution System of Rejuvenation of Jurantee Tea Garden Area piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2022-2023 | 2456/JD | 22/12/2022 | 21/01/2023 | SANDIP BANIK | 71.54 | 0 | 0 | 100
4 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Infrastructure Cost for NEORA LINE ZURRANTEE TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 100000084451, Reference ID : 860276312] |  |  | BILL/00615/2023-2024 | BP/23-24/82 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Infrastructure Cost for NEORA LINE ZURRANTEE TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 100000085207, Reference ID : 860276427] |  |  | BILL/00613/2023-2024 | BP/23-24/82 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.19 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | New Service Connection Charge for NEORA LINE ZURRANTEE TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 4003197409, Reference ID : 403049081] |  |  | BILL/00614/2023-2024 | BP/23-24/82 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | New Service Connection Charge for NEORA LINE ZURRANTEE TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 4003197405, Reference ID : 403049083] |  |  | BILL/00611/2023-2024 | BP/23-24/82 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Construction of boundary wall with gate,drain and pathway for 3rd tube-well site of Rejuvenation of Jurantee tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2022-2023 | 62/JSSD | 19/07/2022 | 08/08/2022 | ARINDAM CHATTERJEE | 3.88 | 0 | 0 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 4th tube well site for Juranteeee TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 252/JD | 10/05/2023 | 24/06/2023 | SARKAR CONSTRUCTION | 4.64 | 0 | 0 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Jurantee Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2023-2024 | 2628/JD | 07/03/2024 | 21/04/2024 | ASIT PAUL | 5.61 | 0 | 0 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) at Juranti TG PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000095/2025-2026 | 115/JSSD | 03/06/2025 | 03/07/2025 | ASIT PAUL | 9.61 | 0 | 0 | 100
13 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing including Rising Main in connection with Jal Jeevan Mission for Rejuvenation of Juranti Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 348/JD | 24/05/2023 | 01/04/2025 | ASIT PAUL | 73.94 | 0 | 0 | 38
14 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JURANTI PWSS, TW no III, IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000434/2023-2024 | 1373/NMD | 09/08/2023 | 30/01/2025 | S.S. ENTERPRISES | 27.5 | 0 | 0 | 100
15 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme | SM/10069 | Augmentation | Restoration work of damaged road due to laying of pipeline and other allied works under Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000352/2023-2024 | 298/JSSD | 27/09/2023 | 30/08/2024 | SANDIP BANIK | 9.64 | 0 | 0 | 100
Total | [13 empty] | 274.15 | 0 | 0