## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Hila Tea Garden Area Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000142/2022-2023 | 562/NMD | 14/07/2022 | 04/08/2022 | ALPHA ENTERPRISE | 2.99 | 2.99 | 100 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | FHTC HILLA T.G PWSS |  |  | VCH/001356/2021-2022 | BP-2021-22-473 | 28/03/2022 | 28/03/2022 | SCEC BOENTER KDAS JOINT VENTURE | 19.05 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 100000058152 ; Reference ID :860247832] [PART-I] |  |  | VCH/000967/2022-2023 | BP/22-23/59 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.98 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | SUPPLY INSTALATION COMMISSIONING AND TRIAL OPERATION OF HILA T.G PWSS |  |  | VCH/001443/2021-2022 | BP-2021-22-483 | 29/03/2022 | 29/03/2022 | S P ENTERPRISE | 8.09 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000058152, Reference ID :860247832] |  |  | VCH/000889/2022-2023 |  | 16/09/2022 | 16/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | EARTH FILLING WORK H/W DAKSHIN SALBARI WSS |  |  | VCH/001381/2021-2022 | BP-2021-22-534 | 31/03/2022 | 31/03/2022 | R.S CONSTRUCTION | 4.66 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | RECONNECTION OF PIPE LINE RETROFITTING HILLA T.G WSS |  |  | VCH/001357/2021-2022 | BP-2021-22-474 | 28/03/2022 | 28/03/2022 | SCEC BOENTER KDAS JOINT VENTURE | 17.01 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. V, under NAGRAKATA CCC, [APPLICATION NO. 100000058117, Reference ID : 860247827] |  |  | VCH/000851/2022-2023 | BP/22-23/46 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000058152, Reference ID :860247832] |  |  | VCH/000852/2022-2023 |  | 26/08/2022 | 26/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 100000058152 ; Reference ID :860247832] [PART-II] |  |  | VCH/000966/2022-2023 | BP/22-23/58 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.71 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | New Service Connection Charge for HILA T.G (REJU) W/S SCHEME, T/W No. V, under NAGRAKATA CCC, [APPLICATION NO. 4002969966, Reference ID :402856020] |  |  | VCH/000850/2022-2023 | BP/22-23/46 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | New Service Connection Charge for HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 4002969959 ; Reference ID :402856023] |  |  | VCH/000965/2022-2023 | BP/22-23/46 | 08/09/2022 | 08/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HILA TG AREA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000769/2022-2023 | 75/NMD | 27/01/2023 | 26/02/2023 | GURUKRIPA ENTERPRISE | 11.38 | 10.84 | 95.24 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Construction of Boundary wall at 3rd Tube well site for Hila T.G. PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000417/2020-2021 | 552/JSSD | 29/01/2021 | 28/02/2021 | SAHA CONSTRUCTION | 4.55 | 3.66 | 80.37 | 1
15 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Hila Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000611/2021-2022 | 561/JD | 01/03/2022 | 31/03/2022 | ASHIS DUTTA | 13.22 | 13.51 | 102.16 | 1
16 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Construction of Pump House (3.60 m X 2.40m size with sanitary & plumbing arrangement at 4th tube well site for Rejuvenation of Water Supply Scheme for HILA Tea Garden under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000835/2021-2022 | 1105/W/JSSD | 27/01/2022 | 13/03/2022 | TECHNOCRACY ELECTRICAL CONTRACTOR & GENERAL ORDER SUPPLIER | 4.64 | 4.64 | 100 | 1
17 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 4th tube-well site of Rejuvenation of Piped Water Supply Scheme for HILA under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000086/2022-2023 | 1364/JSSD | 19/04/2022 | 09/05/2022 | GOPAL DEY | 3.89 | 3.91 | 100.29 | 100
18 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 5th tube well site for Hila TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000271/2022-2023 | 215/JSSD | 16/09/2022 | 15/11/2022 | U TURN CONSTRUCTION | 4.65 | 4.65 | 100 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Retrofitting works for Laying Distribution System of Rejuvenation of water supply scheme for Hilla Tea Garden Mouza under Jalpaiguri Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 733/JD | 22/03/2023 | 21/04/2023 | PROFULLA GHOSH | 32.91 | 24.85 | 75.5 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Construction of peripherial drain with Land development and RBT at 4th tubewell site of Hila Tea Garden in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 254/JD | 10/05/2023 | 24/05/2023 | GOPAL DEY | 1.19 | 1.19 | 99.77 | 100
21 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Retrofitting works of 3rd Pump House site at Hila Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  |  | ORD/000553/2023-2024 | 503/JSSD | 02/01/2024 | 01/02/2024 | SCEC BOENTER AND KDAS JOINT VENTURE | 6.04 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 6th tube well site of Rejuvenation of Hila Tea Garden Piped Water Supply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2024-2025 | 1389/JD | 18/09/2024 | 03/10/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0 | 0
23 | JALPAIGURI |  | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HILA TG AREA PWSS, TW no V in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000770/2022-2023 | 76/NMD | 27/01/2023 | 26/02/2023 | HARA PROSAD DAS | 12.38 | 12.37 | 99.95 | 70
24 | JALPAIGURI |  | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme | SM/10070 | Augmentation | Providing Functional Household Tap Connection 261Nos. in Connection with Jal Jeevan Mission Hila Tea Garden Piped Water Supply Scheme Under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000799/2023-2024 | 564/JSSD | 05/03/2024 | 04/04/2024 | SAHA CONSTRUCTION | 9.52 | 9.46 | 99.38 | 100
Total | [13 empty] | 193.32 | 92.08 | 47.63