## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Replacing Old Damaged Pipeline With Laying New UPVC Pipeline Due To Construction of Rural Road at Angravasa Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001032/2021-2022 | 56 /JSSD | 12/05/2021 | 11/06/2021 | ROY & SARKAR CONSTRUCTION | 3.76 | 1.17 | 31.09 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Continuation Work order for the work of Annual Maintenance of pipe line and other misc. work related to pipe line including maintenance of I.E.Plant (if any)for Angravasa T.G. PWSS under Jalpaiguri Division, P.H.E Dte. period from 15/07/2021 to 31/12/2021. |  | Junior Engineer | ORD/001037/2021-2022 | 162 /JSSD | 15/07/2021 | 01/01/2022 | ROY & SARKAR CONSTRUCTION | 2.23 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Soil investigation work for 200 Cum over head Reservoir (OHR)for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division PHE.Dte. |  | Junior Engineer | ORD/000834/2021-2022 | 1183/W/JSSD | 08/03/2022 | 28/03/2022 | G MITRA & ASSOCIATES | 2 | 1.99 | 99.83 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 555/JD | 01/03/2022 | 01/03/2022 | Resource Division | 52.27 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | New Service Connection Charge for PUMP HOUSE IN ANGRABHASA w/s scheme under BANARHAT CCC, [APPLICATION NO. 4002813842, Reference ID : 422058156] |  |  | BILL/00463/2023-2024 | BP/23-24/32 | 09/06/2023 | 09/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.46 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Construction of Pump House (3.60 m x2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/001000/2021-2022 | 1242/JSSD | 25/03/2022 | 09/05/2022 | SURAJIT KUNDU | 4.65 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001006/2021-2022 | 1262/JSSD | 25/03/2022 | 14/04/2022 | SURAJIT KUNDU | 4.8 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Angrabhasa Piped Water Supply Scheme Block- Dhupguri, District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000137/2022-2023 | 1554/JD | 05/08/2022 | 02/04/2026 | SWAPAN SAHA | 54.69 | 31.22 | 57.08 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Laying Rising Main for Augmenmtation of Angrabhasa piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000479/2022-2023 | 798/JD.. | 29/03/2023 | 12/04/2023 | M/S ROY & SARKAR CONSTRUCTION | 6.39 | 2.72 | 42.52 | 70
10 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Sinking of 1 No. 250 mm x 200 mm x 147 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for the Augmentation of Angrabhasa piped water supply scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000785/2021-2022 | 840/JD | 31/03/2022 | 21/04/2022 | MALAY BHOWMIK | 8.83 | 5.52 | 62.47 | 100
11 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | New Service Connection Charge for ANGRABHASA, T/W No.III, under BANARHAT CCC, [APPLICATION NO. 4003323154, Reference ID : 403149195] |  |  | BILL/01937/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.34 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Laying of dedicated pipeline along with commissioning of Augmentation of Angrabhasa Piped W/S Scheme in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000079/2025-2026 | 99/JSSD | 30/05/2025 | 29/06/2025 | RAGHU DAS | 12.42 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Laying Distribution System providing With Functional Household Tap Connection (FHTC) in connection with Jalswapna/JJM for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000007/2022-2023 | 878/JD | 05/04/2022 | 02/01/2026 | M/S R.N. TRADERS | 282.14 | 193.85 | 68.71 | 1
14 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Construction of boundary wall with gate, drain and pathway for 3rd tubewell Site for Augmentation of Angrabhasa PWSS, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000192/2022-2023 | .99/JSSD | 22/07/2022 | 02/12/2024 | CHANDAN GHOSH | 4.78 | 0 | 0 | 100
15 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. | SM/10071 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ANGRABHASA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000880/2022-2023 | 363/NMD | 29/03/2023 | 16/02/2025 | M/S ROYAL ENTERPRISE | 10.1 | 10.04 | 99.39 | 100
Total | [13 empty] | 453.86 | 246.51 | 54.31