## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | LDS FHTC GHASMARI |  |  | VCH/001355/2021-2022 | BP-2021-22-499 | 29/03/2022 | 29/03/2022 | M/S R.N. TRADERS | 56.2 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 4th Tubewell site for Augmentation of Dakshin Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000352/2022-2023 | 164/JD | 19/01/2023 | 05/03/2023 | KAUSHIK SEN | 10.78 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Rising Main Connections (at 4th TW site) including other necessary arrangement for Augmentation of Dakshin Berubari Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000436/2022-2023 | 167/RWS | 28/02/2023 | 14/03/2023 | SAPTASWA SARKAR | 1.58 | 0 | 0 | 1
4 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAKSHIN BERUBARI PWSS,TW No IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000882/2022-2023 | 365/NMD | 29/03/2023 | 28/04/2023 | SARKAR ELECTRIC | 11.14 | 8.61 | 77.34 | 70
5 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Sinking of Shallow Tubewell for the Contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Augmentation Dakshin Berubari PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000128/2023-2024 | 42/DSD | 14/07/2023 | 24/07/2023 | SARKAR ELECTRIC | 0.08 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tube well (BDTW) by the Reverse Rotary Circulation method of drilling at Augmentation Dakshin Berubari PWSS TW-IV, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000129/2023-2024 | 43/DSD | 14/07/2023 | 24/07/2023 | SARKAR ELECTRIC | 0.79 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.07.2023) |  |  | ORD/000253/2023-2024 | 672/JD | 10/07/2023 | 10/01/2024 | APIKUL ALI | 0.88 | 0.82 | 92.43 | 30
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-D). |  | Junior Engineer | ORD/000462/2021-2022 | 343/JD | 03/02/2022 | 04/05/2022 | SUKES BASU MAJUMDAR | 177.1 | 94.69 | 53.47 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 560/JD | 01/03/2022 | 01/03/2022 | Resource Division | 53.75 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | FUEL AND LUBRICANTS FOR THE VEHICLES UNDER JALPAIGURI |  |  | BILL/00610/2023-2024 | BP-2023-24-416 | 06/10/2023 | 06/10/2023 | FILL & SMILE | 2.41 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | New Service Connection Charge for DAKSHIN BERUBARI, T/W IV, under HALDIBARI CCC, [APPLICATION NO. 4003215403, Reference ID : 403062802] |  |  | BILL/01116/2023-2024 | BP/23-24/123 | 10/10/2023 | 10/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | supply of 1(one) Maxi cab with engine capacity less than or equal to 2000c.c on hire basis including driver for the Executive Engineer ,planing & Design Division-III, P.H.E. Dte., silliguri |  |  | BILL/00664/2023-2024 | BP-2023-24-467 | 17/10/2023 | 17/10/2023 | SHREYANSH AUTO MOBILE | 1.14 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | SUPPLY OF FUEL & LUBRICANT FOR THE VEHICLE RUNNING UNDER JALPAIGURI RWS FOR THE MONTH OF OCTOBER-2023 |  |  | BILL/00894/2023-2024 | BP-2023-24-508 | 29/11/2023 | 29/11/2023 | FILL & SMILE | 0.22 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | FUEL BILL |  |  | BILL/00685/2023-2024 | BP-2023-24-491 | 08/11/2023 | 08/11/2023 | FILL & SMILE | 0.32 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | SUPPLY OF FUEL FOR THEB HIRED VEHICLES UNDER JALPAIGURI DIVISION AND SUB DIVISION |  |  | BILL/00480/2023-2024 | BP-2023-24-375 | 19/09/2023 | 19/09/2023 | FILL & SMILE | 0.7 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-B). |  | Junior Engineer | ORD/000368/2021-2022 | 340/JD | 03/02/2022 | 01/04/2026 | M/S RATAN KUMAR DAS GUPTA AND CO | 162.92 | 83.77 | 51.42 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.07.2023) |  |  | ORD/000252/2023-2024 | 683/JD | 11/07/2023 | 11/01/2024 | RAKESH SARKAR | 0.88 | 1.04 | 118.12 | 50
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Providing FHTC and Retrofitting works in connection with FHTC works at Jakhai bari, Kathal Tali, Kalirhat & adjacent area of Dwarikamari W/S/S under Jalpaiguri Division , P.H.E .Dte. (Part-F). Block-Maynaguri. District- Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000426/2022-2023 | 625/JD | 13/03/2023 | 27/04/2023 | ARATI CONSTRUCTION | 45 | 0 | 0 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Sinking of 250 mm X 150 mm dia tube well by Reverse Rotary method of drilling at 4th Site of A Dakshin Berubari PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000204/2024-2025 | 1591/JD | 23/10/2024 | 22/11/2024 | NARESH SEN | 9.11 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Construction of 700 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME, Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000455/2021-2022 | 337/JD | 02/02/2022 | 02/06/2022 | M/S RATAN KUMAR DAS GUPTA AND CO | 143.72 | 110.73 | 77.04 | 100
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2024-2025 | 2213/JD | 01/12/2024 | 01/12/2024 | Resource Division | 30.21 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-C). | Assistant Engineer | Junior Engineer | ORD/000461/2021-2022 | 341/JD | 03/02/2022 | 10/02/2026 | M/S A.B.G. CONSTRUCTION | 174.6 | 92.67 | 53.07 | 100
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-A). |  | Junior Engineer | ORD/000367/2021-2022 | 347/JD | 03/02/2022 | 01/04/2026 | M/S RATAN KUMAR DAS GUPTA AND CO | 175.44 | 136.33 | 77.71 | 100
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-F). | Assistant Engineer | Junior Engineer | ORD/000464/2021-2022 | 346/JD | 03/02/2022 | 01/04/2026 | M/S SURAJIT DEY AND CO. | 197.49 | 67.35 | 34.11 | 100
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Soil Investigation Work, Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling, 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall (H/W and 2nd Site) along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Satkhaya Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000284/2023-2024 | 1255/JD | 13/09/2023 | 31/05/2025 | B RAI CONSTRUCTION COMPANY | 183 | 0 | 0 | 14
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | Additional work of OHR including IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Dakshin Berubari Pipe Water Supply Scheme under Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000548/2024-2025 | 128/JD | 16/01/2025 | 01/04/2026 | M/S RATAN KUMAR DAS GUPTA AND CO | 78.71 | 0 | 0 | 85
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. | SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-E). | Assistant Engineer | Junior Engineer | ORD/000463/2021-2022 | 344/JD | 03/02/2022 | 22/02/2024 | R.S CONSTRUCTION | 177.82 | 124.31 | 69.91 | 100
Total | [13 empty] | 1701.53 | 720.32 | 42.33