## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-A). |  | Junior Engineer | ORD/000446/2021-2022 | 342/JD | 03/02/2022 | 04/05/2022 | M/S R.N. TRADERS | 158.04 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Continuation order for Maintenance of pipe line & others Mise. Work related to pipe line Mtc. Of I.E plant for MondalghatP/ W/S/S under Jalpaiguri Division PHE Dte. Period from 01.07.2021 to 31.12.2021 |  | Junior Engineer | ORD/000723/2021-2022 | 400/RWS | 30/06/2021 | 31/12/2021 | UNITED CONSTRUCTION | 2.01 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | providing drainage system for mondalghat pwss |  |  | VCH/000021/2022-2023 | BP-2021-23-7 | 21/04/2022 | 21/04/2022 | M/S RATAN KUMAR DAS GUPTA AND CO | 1.72 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | PROVIDING DRAINAGE SYSTEM FOR MONDALGHAT PWSS |  |  | VCH/000057/2022-2023 | BP-2021-22-7 | 21/04/2022 | 21/04/2022 | M/S RATAN KUMAR DAS GUPTA AND CO | 1.72 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | SOIL TEST FOR MANDALGHAT |  |  | VCH/001437/2021-2022 | BP-2021-22 | 22/03/2022 | 22/03/2022 | R.B TESTING | 2.02 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | FHTC GRASS MORE |  |  | VCH/000061/2022-2023 | BP-2021-22-25 | 26/04/2022 | 26/04/2022 | M/S R.N. TRADERS | 7.08 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | CONSTRUCTION 550 M3 AUG MANDALGHAT PWSS |  |  | VCH/001306/2021-2022 | BP-2021-22-391 | 17/03/2022 | 17/03/2022 | R.N.TRADER'S | 51.64 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Construction of 550 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MANDALGHAT PWSS, Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000447/2021-2022 | 336/JD | 02/02/2022 | 02/06/2022 | M/S R.N. TRADERS | 110.23 | 0 | 0 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Construction of boundary wall with drain for 3rd site of Mondal ghat piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000283/2022-2023 | 648/RWS | 21/10/2022 | 20/11/2022 | ALICK DUTTA | 4.84 | 0 | 0 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Repair work of Pump house , bath room of H/W site & ancilliary works at Mondalghat PWSS under Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/000487/2022-2023 | 285/RWS | 29/03/2023 | 12/04/2023 | M/S UNITED CONSTRUCTION | 1.53 | 0 | 0 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Construction of valve chember & Blower room(3.60MX3.00M ) Size for Iron Elimination Plant at Head Work Site of Mondalghat piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000043/2023-2024 | 390/RWS | 25/04/2023 | 09/05/2023 | SWAPAN SAHA | 4.8 | 0 | 0 | 100
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 550/JD | 01/03/2022 | 01/03/2022 | Resource Division | 60.75 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Reparing of pump houses & construction of Boundary wall at 2nd site for Mandalghat W/S/S under Jalpaiguri Division , P.H.E Dte | Assistant Engineer | Junior Engineer | ORD/000278/2021-2022 | 820/RWS | 30/11/2021 | 30/12/2021 | ALICK DUTTA | 4.83 | 0 | 0 | 99
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Construction of Boundary wall and land development at Head Work Site for Mandalghat Water Supply Scheme under Jalpaiguri Division P.H.E. Dte |  |  | ORD/000136/2021-2022 | 1442/JD | 09/09/2021 | 09/10/2021 | M/S UNITED CONSTRUCTION | 10.53 | 0 | 0 | 100
15 | JALPAIGURI |  | Northern Mechanical | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANDALGHAT PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000235/2023-2024 | 1250/NMD | 31/07/2023 | 30/08/2023 | M/S ANJALI ENTERPRISE | 11.6 | 0 | 0 | 100
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Mandolghat PWSS under JJM work at Jalpaiguri sadar Block under PHE Dte., Jalpaiguri Division | Assistant Engineer | Junior Engineer | ORD/000334/2023-2024 | 1082/RWS | 19/09/2023 | 19/10/2023 | TIRTHANKAR CHOWDHURY | 9.24 | 0 | 0 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2024-2025 | 2212/JD | 01/12/2024 | 01/12/2024 | Resource Division | 23.36 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 2095/JD | 25/11/2024 | 25/11/2024 | Resource Division | 70.02 | 0 | 0 | 0
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-D). | Assistant Engineer | Junior Engineer | ORD/000460/2021-2022 | 339/JD | 03/02/2022 | 01/04/2026 | BISWANATH GHOSH | 150.63 | 0 | 0 | 60
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-B). | Assistant Engineer | Junior Engineer | ORD/000465/2021-2022 | 345/JD | 03/02/2022 | 01/04/2026 | M/S SURAJIT DEY AND CO. | 195.6 | 0 | 0 | 85
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. | SM/10087 | Augmentation | Installation of Iron Elimination Plant (IEP) including construction of concrete platform & drain at Head work site for Augmentation Mondalghat piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000615/2021-2022 | 402/JD | 11/02/2022 | 03/02/2023 | M/S R.N. TRADERS | 27.54 | 0 | 0 | 100
Total | [13 empty] | 909.73 | 0 | 0