## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of Boundary wall including repairing of Pump House at 2nd Site for Kharija Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001044/2021-2022 | 1438/JD | 09/09/2021 | 09/10/2021 | PROFULLA GHOSH | 9.74 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Distribution System and Functional Household Tap Connection for Augmentation of Kharija Berubari Zone-II Piped Water Supply Scheme Block - Jalpaiguri District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000038/2022-2023 | 1099/JD | 12/05/2022 | 09/09/2022 | BANSBERIA CONSTRUCTION CO. | 554.56 | 503.06 | 90.71 | 90
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Distribution system and functional household tap connection for Augmentation of Kharija Berubari Zone-I piped Water Supply Scheme Block- Jalapiguri, District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000019/2022-2023 | 1066/JD | 28/04/2022 | 01/11/2025 | M/S R.N. TRADERS | 605.44 | 385.99 | 63.75 | 85
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF KHARIJA BERUBARI PIPED WATER SUPPLY SCHEME (ZONE-II), Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000454/2021-2022 | 335/JD | 02/02/2022 | 02/06/2022 | NARAYAN CHANDRA SAHA | 97.85 | 71.39 | 72.95 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of 400 m3 OHR as per Departmental Design & Drawing & Pump House (3.60m x 2.40m) internal size with sanitary & Plumbing arrangement at Head Work site for AUGMENTATION OF KHARIJA BERUBARI (Zone-I) Piped Water Supply Scheme Block- Jalpaiguri, District : Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000250/2022-2023 | 1845//JD | 15/09/2022 | 14/03/2023 | SUKES BASU MAJUMDAR | 87.97 | 89.05 | 101.23 | 100
6 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply delivery of the different UPVC materials for Reverse Rotary Circulation method of drilling for construction of BDTW for the Augmentation of KharijaBerubari PWSS (Zone-I), Block - Jalpaiguri, Dist.- Jalpaiguri, at deptt. Stack-Yard at Fulbari under NMSD (D), PHE, Dte. | Driller-in-Charge | Junior Engineer | ORD/000668/2022-2023 | 1411/NMD | 13/12/2022 | 12/01/2023 | ALPHA ENTERPRISE | 11.43 | 11.43 | 100 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 559/JD | 01/03/2022 | 01/03/2022 | Resource Division | 96.47 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SOIL INVESTIGATION WORK AUGMENTATION KHARIJA BERUBARI (ZONE -I) PWSS |  |  | VCH/001276/2021-2022 | BP-2021-22-353 | 08/03/2022 | 08/03/2022 | GEOCON INDIA | 2.03 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SOIL INVESTIGATION |  |  | VCH/001199/2021-2022 | BP-2021-22-316 | 28/02/2022 | 28/02/2022 | MOYTEC | 2.03 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Sinking of 250mm x 150mm dia tube wells by Reverse Rotary method of drilling for Augmentation of Kharija Berubari Zone-I PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division (H/W and 2nd Site) | Assistant Engineer | Junior Engineer | ORD/000003/2023-2024 | 848/JD | 06/04/2023 | 06/05/2023 | SHYAMAL KUMARSAHA | 17.39 | 17.17 | 98.73 | 100
11 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KHARIJA BERUBARI PWSS, ZONE-I, TW No I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 1272/NMD | 02/08/2023 | 01/05/2025 | SANJIB SAHA | 23.13 | 12.37 | 53.51 | 100
12 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | New Service Connection Charge for KHARIJA BERUBARI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003207489, Reference ID : 403056596] |  |  | BILL/00624/2023-2024 | BP/23-24/86 | 21/08/2023 | 21/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply of Fuel & lubricant for Vehicle No:- WMA-2539, WB-71A-5774 FOR THE MONTH OF APRIL, MAY ,& OCTOBER |  |  | BILL/00948/2023-2024 | BP-2023-24-545 | 18/12/2023 | 18/12/2023 | FILL & SMILE | 0.54 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | New Service Connection Charge for NANDANPUR,KHARIJA BERUBARI, T/W I, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003212076, Reference ID : 403060257] |  |  | BILL/01070/2023-2024 | BP/23-24/103 | 30/09/2023 | 30/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.98 | 0 | 0 | 0
15 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Infrastructure Cost for KHARIJA BERUBARI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000086246, Reference ID : 860277656] |  |  | BILL/00625/2023-2024 | BP/23-24/86 | 21/08/2023 | 21/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SUPPLY OF DIFFERENT STATIONARY FOR OFFICE USE |  |  | BILL/00462/2023-2024 | BP-2023-24-363 | 13/09/2023 | 13/09/2023 | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 4.59 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Kharija Berubari - II Pipe Water Supply Scheme under Jalpaiguri Sadar Block Within Jalpaiguri PHE Division, Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000086/2024-2025 | 1176/JD | 23/08/2024 | 01/04/2026 | NARAYAN CHANDRA SAHA | 72.2 | 0 | 0 | 80
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement and Boundary Wall, Foot Path, Drain of 2nd Site at Kharija - I Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000124/2024-2025 | 1369/JD | 13/09/2024 | 02/04/2026 | ALICK DUTTA | 12.67 | 6.41 | 50.59 | 65
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.01.2024 to 29.02.2024) | Assistant Engineer,HQ | Junior Engineer | ORD/000563/2023-2024 | 2121/JD | 17/01/2024 | 17/03/2024 | GURUKUL INFOTECH | 3.16 | 3.16 | 100 | 50
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply of different forms for office use under jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ |  | ORD/000822/2023-2024 | 2721/JD | 12/03/2024 | 19/03/2024 | SUBRATA ART PRESS | 0.7 | 0.7 | 100 | 100
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.03.2024 to 30.04.2024)" | Assistant Engineer,HQ | Junior Engineer | ORD/000865/2023-2024 | 2488/JD | 27/02/2024 | 27/04/2024 | GURUKUL INFOTECH | 3.16 | 3.16 | 100 | 100
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Additional work of OHR including Boundary wall, Foot Path, Drain, IEP, Pipeline for washout at Kharija Berubari Zone-I HWS PWSS in connection with Jal jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2024-2025 | 938/JD | 07/08/2024 | 05/12/2024 | B.M CONSTRUCTION | 83.38 | 22.06 | 26.45 | 100
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2024-2025 | 2215/JD | 01/12/2024 | 01/12/2024 | Resource Division | 35.61 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SUPPLY OF FUEL for vehicle FOR OFFICE OF THE ASSISTANT ENGINEER , JALPAIGURI SADAR SUB DIVISION, P.H.E Dte. |  |  | BILL/01047/2023-2024 | BP-2023-24-591 | 16/01/2024 | 16/01/2024 | FILL & SMILE | 1.02 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SUPPLY OF ONE MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 C.C. ON HIRE BESIS INCLUDING DRIVER UNDER OFFICE OF THE ASSISTANT ENGINEER ,JALPAIGURI SADAR SUB DIVISION , P.H.E Dte. |  |  | BILL/01046/2023-2024 | BP-2023-24-592 | 16/01/2024 | 16/01/2024 | MRITYUNJAY SIKDAR | 0.54 | 0 | 0 | 0
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Sinking of Additional 1 No Tube Well by Reverse Rotary Method including construction Pump House, Boundary Wall and installation of Iron Elimination Plant (IEP) and Inter Connection work at Gosaimore under Nagar Berubari GP of Augmentation of Kharija Berubari Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block- Jalpaiguri under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2025-2026 | 678/JD | 04/04/2025 | 02/08/2025 | KANAI LAL SEN | 38.97 | 0 | 0 | 0
Total | [13 empty] | 1772.27 | 1125.95 | 63.53