## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SOIL INVESTIGATION |  |  | VCH/001199/2021-2022 | BP-2021-22-316 | 28/02/2022 |  | MOYTEC | 2.03 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SOIL INVESTIGATION WORK AUGMENTATION KHARIJA BERUBARI (ZONE -I) PWSS |  |  | VCH/001276/2021-2022 | BP-2021-22-353 | 08/03/2022 |  | GEOCON INDIA | 2.03 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of Boundary wall including repairing of Pump House at 2nd Site for Kharija Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001044/2021-2022 | 1438/JD | 09/09/2021 | 09/10/2021 | PROFULLA GHOSH | 9.74 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply delivery of the different UPVC materials for Reverse Rotary Circulation method of drilling for construction of BDTW for the Augmentation of KharijaBerubari PWSS (Zone-I), Block - Jalpaiguri, Dist.- Jalpaiguri, at deptt. Stack-Yard at Fulbari under NMSD (D), PHE, Dte. | Driller-in-Charge | Junior Engineer | ORD/000668/2022-2023 | 1411/NMD | 13/12/2022 | 12/01/2023 | ALPHA ENTERPRISE | 11.43 | 11.43 | 100 | 0
5 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | New Service Connection Charge for KHARIJA BERUBARI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003207489, Reference ID : 403056596] |  |  | BILL/00624/2023-2024 | BP/23-24/86 | 21/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Infrastructure Cost for KHARIJA BERUBARI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000086246, Reference ID : 860277656] |  |  | BILL/00625/2023-2024 | BP/23-24/86 | 21/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Distribution system and functional household tap connection for Augmentation of Kharija Berubari Zone-I piped Water Supply Scheme Block- Jalapiguri, District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000019/2022-2023 | 1066/JD | 28/04/2022 | 26/08/2022 | M/S R.N. TRADERS | 605.44 | 385.99 | 63.75 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SUPPLY OF DIFFERENT STATIONARY FOR OFFICE USE |  |  | BILL/00462/2023-2024 | BP-2023-24-363 | 13/09/2023 |  | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 4.59 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | New Service Connection Charge for NANDANPUR,KHARIJA BERUBARI, T/W I, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003212076, Reference ID : 403060257] |  |  | BILL/01070/2023-2024 | BP/23-24/103 | 30/09/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.98 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 559/JD | 01/03/2022 |  | Resource Division | 96.47 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply of Fuel & lubricant for Vehicle No:- WMA-2539, WB-71A-5774 FOR THE MONTH OF APRIL, MAY ,& OCTOBER |  |  | BILL/00948/2023-2024 | BP-2023-24-545 | 18/12/2023 |  | FILL & SMILE | 0.54 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply of Fuel & lubricant for Vehicle No:- WMA-2539, WB-71A-5774 FOR THE MONTH OF APRIL, MAY ,& OCTOBER |  |  | BILL/00948/2023-2024 | BP-2023-24-545 | 18/12/2023 |  | FILL & SMILE | 0.54 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SUPPLY OF FUEL for vehicle FOR OFFICE OF THE ASSISTANT ENGINEER , JALPAIGURI SADAR SUB DIVISION, P.H.E Dte. |  |  | BILL/01047/2023-2024 | BP-2023-24-591 | 16/01/2024 |  | FILL & SMILE | 1.02 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SUPPLY OF FUEL for vehicle FOR OFFICE OF THE ASSISTANT ENGINEER , JALPAIGURI SADAR SUB DIVISION, P.H.E Dte. |  |  | BILL/01047/2023-2024 | BP-2023-24-591 | 16/01/2024 |  | FILL & SMILE | 1.02 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | SUPPLY OF ONE MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 C.C. ON HIRE BESIS INCLUDING DRIVER UNDER OFFICE OF THE ASSISTANT ENGINEER ,JALPAIGURI SADAR SUB DIVISION , P.H.E Dte. |  |  | BILL/01046/2023-2024 | BP-2023-24-592 | 16/01/2024 |  | MRITYUNJAY SIKDAR | 0.54 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF KHARIJA BERUBARI PIPED WATER SUPPLY SCHEME (ZONE-II), Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000454/2021-2022 | 335/JD | 02/02/2022 | 02/06/2022 | NARAYAN CHANDRA SAHA | 97.85 | 60.72 | 62.05 | 100
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.01.2024 to 29.02.2024) | Assistant Engineer,HQ | Junior Engineer | ORD/000563/2023-2024 | 2121/JD | 17/01/2024 | 17/03/2024 | GURUKUL INFOTECH | 3.16 | 1.58 | 50 | 50
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply of different forms for office use under jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ |  | ORD/000822/2023-2024 | 2721/JD | 12/03/2024 | 19/03/2024 | SUBRATA ART PRESS | 0.7 | 0.35 | 50 | 100
19 | JALPAIGURI |  | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KHARIJA BERUBARI PWSS, ZONE-I, TW No I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 1272/NMD | 02/08/2023 | 01/09/2023 | SANJIB SAHA | 23.13 | 6.19 | 26.75 | 40
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.03.2024 to 30.04.2024)" | Assistant Engineer,HQ | Junior Engineer | ORD/000865/2023-2024 | 2488/JD | 27/02/2024 | 27/04/2024 | GURUKUL INFOTECH | 3.16 | 1.58 | 50 | 100
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of 400 m3 OHR as per Departmental Design & Drawing & Pump House (3.60m x 2.40m) internal size with sanitary & Plumbing arrangement at Head Work site for AUGMENTATION OF KHARIJA BERUBARI (Zone-I) Piped Water Supply Scheme Block- Jalpaiguri, District : Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000250/2022-2023 | 1845//JD | 15/09/2022 | 14/03/2023 | SUKES BASU MAJUMDAR | 87.97 | 58.4 | 66.38 | 100
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Additional work of OHR including Boundary wall, Foot Path, Drain, IEP, Pipeline for washout at Kharija Berubari Zone-I HWS PWSS in connection with Jal jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2024-2025 | 938/JD | 07/08/2024 | 05/12/2024 | B.M CONSTRUCTION | 83.38 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Distribution System and Functional Household Tap Connection for Augmentation of Kharija Berubari Zone-II Piped Water Supply Scheme Block - Jalpaiguri District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000038/2022-2023 | 1099/JD | 12/05/2022 | 09/09/2022 | BANSBERIA CONSTRUCTION CO. | 554.56 | 371.87 | 67.06 | 90
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Sinking of 250mm x 150mm dia tube wells by Reverse Rotary method of drilling for Augmentation of Kharija Berubari Zone-I PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division (H/W and 2nd Site) | Assistant Engineer | Junior Engineer | ORD/000003/2023-2024 | 848/JD | 06/04/2023 | 06/05/2023 | SHYAMAL KUMARSAHA | 17.39 | 8.59 | 49.36 | 100
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. | SM/10088 | Augmentation | Construction of IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Kharija Berubari - II Pipe Water Supply Scheme under Jalpaiguri Sadar Block Within Jalpaiguri PHE Division, Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000086/2024-2025 | 1176/JD | 23/08/2024 | 21/12/2024 | NARAYAN CHANDRA SAHA | 72.2 | 0 | 0 | 0
Total | [13 empty] | 1686.58 | 906.68 | 53.76