## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | TUBE WELL BILL |  |  | VCH/001151/2021-2022 | BP-2021-22-266 | 16/02/2022 |  | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 45.75 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LDS MOGALKATA T.G PWSS |  |  | VCH/001262/2021-2022 | BP-2021-22-554 | 31/03/2022 |  | DULAL CHOUDHURY | 10.11 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | CONSTRUCTION OF PUMP HOUSE, BOUNDARY WALL, 4TH TUBE WELL SITE BAIKUR |  |  | VCH/001272/2021-2022 | BP-2021-22-486 | 29/03/2022 |  | ABHIJIT SARKAR | 4.65 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LDS FHTC AUG BAIKUR (PART -VI) PWSS |  |  | VCH/001321/2021-2022 | BP-2021-22-429 | 25/03/2022 |  | M/S S.G. CONSTRUCTION | 74.99 | 0 | 0 | 0
5 | JALPAIGURI |  | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-I) PWSS UNDER CDD, PHE DTE. |  |  | ORD/000177/2021-2022 | 753/ CDD | 07/10/2021 | 06/11/2021 | PADMA ENGINEERING & CO. | 10.61 | 8.69 | 81.95 | 0
6 | JALPAIGURI |  | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-II) PWSS UNDER CDD, PHE DTE. |  |  | ORD/000181/2021-2022 | 754/ CDD | 07/10/2021 | 06/11/2021 | PADMA ENGINEERING & CO. | 10.61 | 8.33 | 78.56 | 0
7 | JALPAIGURI |  | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-III) PWSS UNDER CENTRAL DRILLING DIVISION, PHE DTE. |  |  | ORD/000179/2021-2022 | 755/ CDD | 07/10/2021 | 06/11/2021 | PADMA ENGINEERING & CO. | 10.61 | 8.32 | 78.43 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LDS AUG OF BAIKUR PWSS |  |  | VCH/001390/2021-2022 | BP-2021-22-509 | 30/03/2022 |  | UNIBRO INFRASERV PRIVATE LIMITED | 26.36 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | AUG LATAGURI ZONE III |  |  | VCH/001396/2021-2022 | BP-2021-22-552 | 31/03/2022 |  | RAGHU DAS | 22.91 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LDS BAIKUR PWSS |  |  | VCH/001407/2021-2022 | BP-2021-22-513 | 30/03/2022 |  | CALCON CONSTRUCTIONS | 27.67 | 0 | 0 | 0
11 | JALPAIGURI |  | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000188/2021-2022 | 463/CMSD-II (D) | 25/10/2021 | 01/11/2021 | PADMA ENGINEERING & CO. | 0.85 | 0.85 | 100 | 0
12 | JALPAIGURI |  | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 10M3 GRAVELS (1 M3 = 1.68MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000187/2021-2022 | 464/CMSD-II (D) | 25/10/2021 | 01/11/2021 | PADMA ENGINEERING & CO. | 0.42 | 0.03 | 6.79 | 0
13 | JALPAIGURI |  | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200KM FOR 20 M3 GRAVELS (1 M3 = 1.68MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-III) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000186/2021-2022 | 472/CMSD-II (D) | 26/10/2021 | 02/11/2021 | PADMA ENGINEERING & CO. | 0.85 | 0.77 | 91.16 | 0
14 | JALPAIGURI |  | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS ( 1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-II) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000184/2021-2022 | 471/CMSD-II (D) | 26/10/2021 | 02/11/2021 | PADMA ENGINEERING & CO. | 0.85 | 0.77 | 90.9 | 0
15 | JALPAIGURI |  | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF BENTONITE AFTER 200 KM FOR (4X3)=12 MT BENTONITE AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000185/2021-2022 | 473/CMSD-II (D) | 26/10/2021 | 02/11/2021 | PADMA ENGINEERING & CO. | 0.3 | 0.28 | 91.67 | 0
16 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | New Service Connection Charge for T/W No. IV of BAIKUR JORPAKRI BAZER W/S Scheme under BHOPATTY CCC [APPLICATION NO. 4002923158 ; Reference ID : 402820488] |  |  | VCH/000173/2022-2023 | BP/2022-23/16 | 16/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Installation of Infrastructure IRO NSC application T/W No. III of BAIKUR GOURGRAM HELAPAKRI BAZER W/S Scheme under BHOPATTY CCC [APPLICATION NO. 100000052275 ; Reference ID : 860241545] |  |  | VCH/000174/2022-2023 | BP/2022-23/16 | 16/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.73 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | New Service Connection Charge for T/W No. IV of JORPAKRI BAZAR W/S Scheme under BHOPATTY CCC [APPLICATION NO. 4002923158 ; Reference ID : 402820488] |  |  | VCH/000171/2022-2023 | BP/2022-23/16 | 16/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Installation of Infrastructure IRO NSC application T/W No. IV of JORPAKRI BAZAR W/S Scheme under BHOPATTY CCC [APPLICATION NO. 100000052276 ; Reference ID : 860241546] |  |  | VCH/000172/2022-2023 | BP/2022-23/16 | 16/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.18 | 0 | 0 | 0
20 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for augmentation of BAIKUR W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000004/2022-2023 | 207/NMD | 04/04/2022 | 25/04/2022 | MALAY KUMAR SAHA | 2.77 | 2.77 | 100 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Baikur Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000616/2021-2022 | 2238/JD | 29/12/2021 | 27/02/2022 | ABHIJIT SARKAR | 11.44 | 0 | 0 | 1
22 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for augmentation of BAIKUR W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2022-2023 | 206/NMD | 04/04/2022 | 25/04/2022 | R.K.ENTERPRISES | 2.77 | 2.77 | 100 | 0
23 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of BAIKUR PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000011/2022-2023 | 279/NMD | 26/04/2022 | 26/05/2022 | INDTECH ASSOCIATES | 8.74 | 8.74 | 100 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LDS OF AUG OF BAIKUR |  |  | VCH/000274/2022-2023 | BP-2022-23-145 | 29/08/2022 |  | MINTU CHAKRABORTY | 5.32 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LDS BAIKUR |  |  | VCH/000252/2022-2023 | BP-2022-23-74 | 21/07/2022 |  | UNIBRO INFRASERV PRIVATE LIMITED | 77.99 | 0 | 0 | 0
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | CONST OF PUMP HOUSE BAIKUR PWSS |  |  | VCH/000322/2022-2023 | BP-2022-23-125 | 22/08/2022 |  | ABHIJIT SARKAR | 5.2 | 0 | 0 | 0
27 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BAIKUR PWSS, at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000068/2022-2023 | 443/NMD | 14/06/2022 | 05/07/2022 | BONANZA ENTERPRISE | 2.76 | 2.76 | 100 | 0
28 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BAIKUR PWSS, at TW No. IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000082/2022-2023 | 540/NMD | 08/07/2022 | 07/08/2022 | SARKAR ELECTRIC | 8.31 | 8.31 | 100 | 0
29 | JALPAIGURI |  | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of BAIKUR PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000012/2022-2023 | 280/NMD | 26/04/2022 | 26/05/2022 | M/S P.P. ELECTRICALS | 8.74 | 8.74 | 100 | 0
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Additional pipeline works for Augmentation of Baikur (Part-I) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/000239/2022-2023 | 1861/JD | 20/09/2022 | 20/10/2022 | PRADIP KR SEN | 18 | 18.53 | 102.95 | 1
31 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-VI) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000365/2021-2022 | 327/JD | 02/02/2022 | 03/05/2022 | M/S S.G. CONSTRUCTION | 213.61 | 67.02 | 31.38 | 1
32 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-V) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000364/2021-2022 | 326/JD | 02/02/2022 | 03/05/2022 | MINTU CHAKRABORTY | 220.34 | 63.39 | 28.77 | 1
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Baikur Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000710/2021-2022 | 2223/JD | 27/12/2021 | 25/02/2022 | DREAM CONSTRUCTION | 11.43 | 10.39 | 90.88 | 1
34 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Baikur Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000340/2022-2023 | 275/JD | 22/11/2022 | 07/12/2022 | DREAM CONSTRUCTION | 6.32 | 5.15 | 81.43 | 0
35 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Minor Repairing work for Pump House & construction of CC path for Baikur Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000365/2022-2023 | 191/JD | 20/01/2023 | 04/02/2023 | DREAM CONSTRUCTION | 2.55 | 1.79 | 70.47 | 0
36 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Installation of Iron Elimination Plant (40m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Baikur water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000286/2022-2023 | 2014/JD | 01/11/2022 | 16/12/2022 | M/S R.N. TRADERS | 17.88 | 17.37 | 97.15 | 100
37 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Installation of Iron Elimination Plant (40m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Baikur water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000344/2022-2023 | 137/JD | 17/01/2023 | 03/03/2023 | SADHAN KARMAKAR | 17.86 | 17.27 | 96.66 | 100
38 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-IV) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000363/2021-2022 | 325/JD | 02/02/2022 | 03/05/2022 | NARAYAN CHANDRA SAHA | 221.81 | 146.12 | 65.88 | 1
39 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | PROVIDING INSPECTION VEHICLE FOR OFFICIAL USE OF THE OFFICE OF THE EXECUTIVE ENGINEER,JALPAIGURI DIVISION, P.H.E. Dte. |  |  | BILL/00621/2023-2024 | BP-2023-24-426 | 10/10/2023 |  | SADHAN KARMAKAR | 0.16 | 0 | 0 | 0
40 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2023 to 31/10/2023 |  |  | ORD/000117/2023-2024 | 44/JSSD | 27/04/2023 | 24/10/2023 | MRITYUNJAY SIKDAR | 0.88 | 0.88 | 99.21 | 34
41 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 557/JD | 01/03/2022 |  | Resource Division | 1.82 | 0 | 0 | 0
42 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | supply of 1(one) Maxi cab on hire basis including driver for the office of the Executive Engineer , planning & Design Division -III,P.H.E. Dte. Silliguri |  |  | BILL/00904/2023-2024 | BP-2023-24-515 | 06/12/2023 |  | SHREYANSH AUTO MOBILE | 1.15 | 0 | 0 | 0
43 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-III) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000362/2021-2022 | 324/JD | 02/02/2022 | 03/05/2022 | CALCON CONSTRUCTIONS | 218.39 | 140.05 | 64.13 | 50
44 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-II) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000360/2021-2022 | 323/JD | 02/02/2022 | 03/05/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 224.83 | 185.19 | 82.37 | 1
45 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Laying of Additional 75 mm dia pipeline for providing FHTC for Augmentation of Baikur PWSS for Part-VI area. | Assistant Engineer | Junior Engineer | ORD/000530/2023-2024 | 1876/JD | 20/12/2023 | 10/01/2024 | PRADIP KR SEN | 13.08 | 6.24 | 47.67 | 100
46 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Jamuribari, Sovabhita, Pakuritala, Chandanidanga, Nayabari, Kohorapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000202/2022-2023 | 1741/JD | 08/09/2022 | 23/10/2022 | PROVA CONSTRUCTION | 75.59 | 47.84 | 63.29 | 100
47 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. | SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-I) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. | Assistant Engineer | Junior Engineer | ORD/000361/2021-2022 | 322/JD | 02/02/2022 | 03/05/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 224.8 | 90.26 | 40.15 | 100
Total | [13 empty] | 1880.31 | 879.61 | 46.78