## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | OHR BARNESH |  |  | VCH/001234/2021-2022 | BP-2021-22-362 | 14/03/2022 |  | ASHIT KUMAR SINGHA | 52 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Continuation order for Maintenance of pipe line & others Mise. Work related to pipe line Mtc. Of I.E plant for Barnish P/ W/S/S under Jalpaiguri Division PHE Dte. Period from 01.07.2021 to 31.12.2021 |  | Junior Engineer | ORD/000717/2021-2022 | 408/RWS | 30/06/2021 | 27/12/2021 | JITENDRA NATH ROY | 0.86 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | PREPARATION OF DPR ODLABARI PWSS |  |  | VCH/001283/2021-2022 | BP-2021-22-492 | 09/04/2022 |  | SUBHANKAR GHOSH | 1.94 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | SOIL INVESTIGATION AUG BARNES PWSS |  |  | VCH/001338/2021-2022 | BP-2021-22-398 | 22/03/2022 |  | M S PRANTIK ASSOCIATES | 2.02 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | CONST 700 M3RCC RESERVOIR AUG BARNES |  |  | VCH/001352/2021-2022 | BP-2021-22-362 | 14/03/2022 |  | ASHIT KUMAR SINGHA | 52 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | BARNESH PWSS |  |  | VCH/001442/2021-2022 | BP-2021-22- | 24/03/2022 |  | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 16.99 | 0 | 0 | 0
7 | JALPAIGURI |  | Central Drilling | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BARNES (TW-I) PWSS UNDER CDD, PHE DTE. |  |  | ORD/000190/2021-2022 | 756/ CDD | 07/10/2021 | 06/11/2021 | PADMA ENGINEERING & CO. | 10.61 | 8.39 | 79.1 | 0
8 | JALPAIGURI |  | Central Drilling | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BARNES (TW-II) PWSS UNDER CDD, PHE DTE. |  |  | ORD/000191/2021-2022 | 757/ CDD | 07/10/2021 | 06/11/2021 | PADMA ENGINEERING & CO. | 10.61 | 8.77 | 82.69 | 0
9 | JALPAIGURI |  | Central Drilling | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BARNES (TW-II) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000197/2021-2022 | 596/CMSD-II (D) | 07/12/2021 | 17/12/2021 | PADMA ENGINEERING & CO. | 0.92 | 0.92 | 100 | 0
10 | JALPAIGURI |  | Central Drilling | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | ADDITIONAL TRANSPORTATION AFTER 200 KM FOR BENTONITE AND OTHERS FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000198/2021-2022 | 607/CMSD-II (D) | 10/12/2021 | 20/12/2021 | PADMA ENGINEERING & CO. | 0.68 | 0.57 | 84.35 | 0
11 | JALPAIGURI |  | Central Drilling | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BARNES (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000199/2021-2022 | 597/CMSD-II (D) | 07/12/2021 | 17/12/2021 | PADMA ENGINEERING & CO. | 0.92 | 0.87 | 94.61 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Barnes Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000714/2021-2022 | 2227/JD | 27/12/2021 | 25/02/2022 | SADHAN KARMAKAR | 11.45 | 11.38 | 99.44 | 1
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Barnes Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000713/2021-2022 | 2226/JD | 27/12/2021 | 25/02/2022 | JITENDRA NATH ROY | 11.44 | 11.45 | 100.07 | 1
14 | JALPAIGURI |  | Central Drilling | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 24/11/2021 | PADMA ENGINEERING & CO. | 4.52 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | CONSTRUCTION OF 700M3 CAPACITY 20MTR.. AUG OF BURNIS PWSS |  |  | VCH/000265/2022-2023 | BP-2022-23-147 | 29/08/2022 |  | ASHIT KUMAR SINGHA | 35.56 | 0 | 0 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | CONST OHR BARNESH PWSS |  |  | VCH/000247/2022-2023 | BP-2022-23-58 | 08/06/2022 |  | ASHIT KUMAR SINGHA | 6.69 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | IEP BARNESH |  |  | VCH/000260/2022-2023 | BP-2022-23-69 | 06/07/2022 |  | ASHIT KUMAR SINGHA | 20.69 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | New Service Connection Charge for BARNISH W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 4002941264, Reference ID : 402831973] |  |  | VCH/000900/2022-2023 | BP/22-23/61 | 23/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Installation of Infrastructure COST at BARNISH W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 100000059561, Reference ID : 860249301] |  |  | VCH/000901/2022-2023 | BP/22-23/61 | 23/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.97 | 0 | 0 | 0
20 | JALPAIGURI |  | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | New Service Connection Charge for BARNISH W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 4002941261, Reference ID : 402831975] |  |  | VCH/000902/2022-2023 | BP/22-23/61 | 23/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
21 | JALPAIGURI |  | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Installation of Infrastructure COST at BARNISH W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 100000059398, Reference ID : 860248698] |  |  | VCH/000903/2022-2023 | BP/22-23/61 | 23/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
22 | JALPAIGURI |  | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under BARNES PWSS, at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000069/2022-2023 | 444/NMD | 14/06/2022 | 05/07/2022 | TALUKDER ENTERPRISE | 2.16 | 2.16 | 100 | 0
23 | JALPAIGURI |  | Central Drilling | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | SINKING OF 800MM DIA SHALLOW TUBEWELL FOR REQUIREMENT OF DRILLING WATER FOR DIFFERENT CONSTRUCTION OF TUBE WELL AT MAYNAGURI BLOCK IN JALPAIGURI DISTRICT, UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000261/2021-2022 | 575/CMSD-II | 30/11/2021 | 10/12/2021 | PADMA ENGINEERING & CO. | 0.96 | 0.12 | 12.5 | 0
24 | JALPAIGURI |  | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Barnes W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000099/2022-2023 | 567/NMD | 14/07/2022 | 04/08/2022 | S.D. CONCERN WORKSHOP | 2.16 | 2.16 | 100 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  |  | BILL/00355/2022-2023 | BP-2023-24-109 | 17/05/2023 |  | M/S MILLENNIUM FUEL CENTRE | 0.55 | 0 | 0 | 0
26 | JALPAIGURI |  | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BARNES PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000117/2022-2023 | 854/NMD | 18/07/2022 | 17/08/2022 | SAIKAT SINHA | 7.87 | 7.87 | 100 | 100
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Construction of 700 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/001015/2021-2022 | 185/JD | 21/01/2022 | 21/05/2022 | ASHIT KUMAR SINGHA | 141.66 | 29.8 | 21.03 | 1
28 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-D). |  | Junior Engineer | ORD/000445/2021-2022 | 331/JD | 02/02/2022 | 03/05/2022 | SUKES BASU MAJUMDAR | 155.8 | 58.03 | 37.24 | 1
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Retrofitting works related to FHTC at different places of Barnes PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000454/2022-2023 | 731/JD | 22/03/2023 | 21/04/2023 | ASHIT KUMAR SINGHA | 17.49 | 17.49 | 100 | 100
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Extention of pipe line at different places of Barnes PWSS under Jalpiaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000484/2022-2023 | 803/JD | 29/03/2023 | 19/04/2023 | R.S CONSTRUCTION | 10.28 | 10.28 | 100 | 100
31 | JALPAIGURI |  | Central Drilling | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 28/01/2023 | DEY ENTERPRISE | 13.83 | 0 | 0 | 0
32 | JALPAIGURI |  | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BARNES PWSS, at TW No. III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000083/2022-2023 | 541/NMD | 08/07/2022 | 07/08/2022 | SUMON ELECTRICAL | 7.86 | 7.86 | 100 | 100
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | supply of one maxi cab on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar sub Division,P.H.E Dte. |  |  | BILL/00623/2023-2024 | BP-2023-24-428 | 11/10/2023 |  | DHIRAJ BISWAS | 1.2 | 0 | 0 | 0
34 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 558/JD | 01/03/2022 |  | Resource Division | 124.02 | 0 | 0 | 0
35 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain...etc. at 3rd T/W Site of Barnesh piped water supply scheme under JALPAIGURI Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000339/2022-2023 | 2519/JD | 30/12/2022 | 13/02/2023 | GIYASUDDIN SEKH | 16.44 | 13.2 | 80.33 | 100
36 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Work of DI Pipe (Raising main), Pathway, Drain,Chember,flower block,Partial land Development , approach & other ancillary works at 4th site of Barnish Water supply scheme within Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000035/2023-2024 | 388/RWS | 25/04/2023 | 09/05/2023 | JITENDRA NATH ROY | 5.18 | 2.4 | 46.37 | 100
37 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Barnish piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000010/2023-2024 | 335/RWS | 10/04/2023 | 24/04/2023 | SADHAN KARMAKAR | 3.21 | 1.61 | 50 | 100
38 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain...etc. at 4th T/W Site of Barnesh piped water supply scheme under JALPAIGURI Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 1266/JD | 13/09/2023 | 28/10/2023 | ASHIT KUMAR SINGHA | 16.44 | 10.78 | 65.55 | 100
39 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Installation of Iron Elimination Plant (IEP) including construction of concrete platform & drain at Head work site of Augmentation Barnish piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000603/2021-2022 | 409/JD | 15/02/2022 | 01/04/2022 | ASHIT KUMAR SINGHA | 26.37 | 5.17 | 19.62 | 20
40 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-A). | Assistant Engineer | Junior Engineer | ORD/000452/2021-2022 | 328/JD | 02/02/2022 | 03/05/2022 | ASHIT KUMAR SINGHA | 163.38 | 119.24 | 72.98 | 1
41 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | Construction of boundary wall with gate,drain, Pipe line,rising line, Approach road & other ancillary works for OHR site of Barnish piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 60/JD | 18/04/2023 | 18/05/2023 | ASHIT KUMAR SINGHA | 25.62 | 12.8 | 49.96 | 100
42 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-C). | Assistant Engineer | Junior Engineer | ORD/000371/2021-2022 | 330/JD | 02/02/2022 | 03/05/2022 | R.S CONSTRUCTION | 170.45 | 136.23 | 79.93 | 1
43 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. | SM/10090 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-B). | Assistant Engineer | Junior Engineer | ORD/000359/2021-2022 | 329/JD | 02/02/2022 | 03/05/2022 | ASHIT KUMAR SINGHA | 146.7 | 95.61 | 65.18 | 80
Total | [13 empty] | 1310.81 | 575.17 | 43.88