## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Mal,Matiali,Nagrakata | Jalpaiguri Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT | SM/10775 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 9 (nine) villages under different blocks having less than 100 households under Jalpaiguri district in connection with Jal Swapna | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000063/2022-2023 | 1226/JD | 01/06/2022 | 01/07/2022 | M/S NANDY ENTERPRISE | 355.27 | 40.51 | 11.4 | 0
2 | JALPAIGURI | Mal,Matiali,Nagrakata | Jalpaiguri Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT | SM/10775 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 4 (Four) no. village under different blocks having less than 100 household under Jalpaiguri district in connection with Jal Swapna. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000064/2022-2023 | 1227/JD | 01/06/2022 | 01/04/2026 | M/S SIBU DEY AND CO. | 142.11 | 34.23 | 24.09 | 60
Total | [13 empty] | 497.37 | 74.74 | 15.03