## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Sinking of One No. 183 mm x 125mm dia 109 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Meteli Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000556/2021-2022 | 457/JD | 18/02/2022 | 11/03/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 6.38 | 0 | 0 | 100
2 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Retrofitting works related with Jal swapna / JJM for Mateli Bazar area P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001031/2021-2022 | 1053 /JSSD | 24/01/2022 | 08/02/2022 | GOURAB GUHA ROY | 3.1 | 3.03 | 97.57 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Laying distribution system For Rejuvenation Of Meteli Bazar (Zone-I) Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000295/2022-2023 | 2061/JD | 03/11/2022 | 01/04/2026 | SAHA CONSTRUCTION | 115.22 | 16.97 | 14.73 | 45
4 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Providing Functional Household Tap Connection in Connection with Jaldhara/Jal Swapna near Jyoti Colony for Matiali Bazar Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000189/2022-2023 | 89/JSSD | 22/07/2022 | 01/08/2022 | GOURAB GUHA ROY | 4.53 | 4.51 | 99.57 | 100
5 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Sinking of Two Nos. 183 mm x 125mm dia 109 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Meteli Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000557/2021-2022 | 456/JD | 18/02/2022 | 20/03/2022 | UNIBRO INFRASERV PRIVATE LIMITED | 12.75 | 13.11 | 102.81 | 100
6 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Urgent Retrofitting works at Prem Nagar & Thakur line under Meteli Bazar Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000255/2022-2023 | 175/JSSD | 25/08/2022 | 24/09/2022 | SUJAN LAMA | 3.14 | 3.03 | 96.68 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Laying distribution system For Rejuvenation Of Meteli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000021/2022-2023 | 1030/JD | 26/04/2022 | 27/06/2025 | NARAYAN CHAKRABORTY | 97.34 | 86.6 | 88.96 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Construction of Boundary wall reservoir at Head works site for Mateli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000346/2022-2023 | 139//JD | 17/01/2023 | 16/02/2023 | M/S KARMAKAR CONSTRACTION | 14.88 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Construction of Boundary wall reservoir at Head works site for Mateli Bazar (Zone-I) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000345/2022-2023 | 138/JD | 17/01/2023 | 16/02/2023 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.88 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF METELI BAZAR PWSS, ZONE-I, TW No II AND ZONE-II,TW NO- I and II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000887/2022-2023 | 370/NMD | 29/03/2023 | 30/10/2025 | ASHUTOSH DAS AND CO. | 38.04 | 0 | 0 | 30
11 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Mateli Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000398/2023-2024 | 1586/JD | 06/11/2023 | 21/12/2023 | M/S SUNSHINE | 5.61 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Providing Household Tap Connection 846 Nos. in connection with Jal Jeevan Mission at Mateli Bazar Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000402/2023-2024 | 1669/JD | 24/11/2023 | 24/12/2023 | DIPAK KUMAR CHAKRABORTY | 30.54 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing including Rising Main in connection with Jal Jeevan Mission for Meteli Bazar Zone-II area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000396/2023-2024 | 1582/JD | 03/11/2023 | 01/05/2024 | UNIVERSAL ENTERPRISES | 73.78 | 0 | 0 | 0
14 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Mateli Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000002/2023-2024 | 849/JD | 06/04/2023 | 21/05/2023 | M/S YADAV CONSTRUCTION | 5.44 | 5.44 | 100 | 100
15 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Emergent repairing of HW site & 1st site Pump House with Sanitary and plumbing arrangement for Augmentation of Mateli Bazar(Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000360/2023-2024 | 283/JSSD | 26/09/2023 | 26/09/2024 | M/S YADAV CONSTRUCTION | 6.32 | 0 | 0 | 100
16 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | New Service Connection Charge for METELLI TEA GARDEN LASAN LINE, TW No. III, MATELLI CCC, [APPLICATION NO.4003117038, Reference ID : 403006108] |  |  | BILL/00069/2023-2024 | BP/23-24/19 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Infrastructure Cost for METELLI TEA GARDEN GAHADI LINE, TW No. II, MATELLI CCC, [APPLICATION NO. 100000075619, Reference ID : 860267309] |  |  | BILL/00066/2023-2024 | BP/23-24/19 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.93 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | New Service Connection Charge for METELLI BANGLA SCHOOL, TW No. I, MATELLI CCC, [APPLICATION NO.4003117033, Reference ID : 403006110] |  |  | BILL/00067/2023-2024 | BP/23-24/19 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Infrastructure Cost for METELLI TEA GARDEN LASAN LINE, TW No. III, MATELLI CCC, [APPLICATION NO. 100000076010, Reference ID : 860267310] |  |  | BILL/00070/2023-2024 | BP/23-24/19 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0 | 0
20 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Infrastructure Cost for METELLI BANGLA SCHOOL, TW No. I, MATELLI CCC, [APPLICATION NO. 100000075618, Reference ID : 860267308] |  |  | BILL/00068/2023-2024 | BP/23-24/19 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.28 | 0 | 0 | 0
21 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | New Service Connection Charge for METELLI TEA GARDEN GAHADI LINE, TW No. II, MATELLI CCC, [APPLICATION NO.4003117034, Reference ID : 403006109] |  |  | BILL/00065/2023-2024 | BP/23-24/19 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
22 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Restoration work of damaged road due to lying of pipeline, GI works and other allied works under Rejuvenatioin of Mateli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000545/2023-2024 | 496/JSSD | 02/01/2024 | 01/02/2024 | NARAYAN CHAKRABORTY | 8.47 | 8.35 | 98.64 | 100
23 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Sinking of 3 Nos. Big Dia Tube well by Modified DTH - ODEX Method at 6th, 7th & 8th tube well site of Rejuvenation of Mateli Bazar (Zone- I & II) Piped Water Supply Scheme of Matiali Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2024-2025 | 931/JD | 07/08/2024 | 21/09/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 52.84 | 50.1 | 94.81 | 100
24 | JALPAIGURI |  | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000095/2025-2026 | 1085/HQ/NMD | 15/05/2025 | 22/05/2025 | D.K. & SONS | 0.63 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS | SM/11813 | Augmentation | Providing Functional Water Tap Connection including laying pipeline in the command area of Metelibazar PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2025-2026 | 104/JSSD | 30/05/2025 | 29/06/2025 | SUJAN LAMA | 4.83 | 0 | 0 | 100
Total | [13 empty] | 513.7 | 191.14 | 37.21