## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/001043/2021-2022 | 548/JD (Wrong Entry) | 28/02/2022 | 14/04/2022 | GAP ENGINEERS ENTERPRISES | 79.03 | 0 | 0 | 0
2 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT LAKSAN BAZER W/S SCHEME, T/W No. I, under NAGRAKATA CCC, [APPLICATION NO. 100000058118, Reference ID : 860247828] |  |  | VCH/000891/2022-2023 | BP/22-23/63 | 23/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.79 | 0 | 0 | 0
3 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | New Service Connection Charge for LAKSAN BAZER W/S SCHEME, T/W No. II, under NAGRAKATA CCC, [APPLICATION NO. 4002966831, Reference ID :402856022] |  |  | VCH/000892/2022-2023 | BP/22-23/63 | 23/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT LAKSAN BAZER W/S SCHEME, T/W No. II, under NAGRAKATA CCC, [APPLICATION NO. 100000056975, Reference ID : 860246285] |  |  | VCH/000893/2022-2023 | BP/22-23/63 | 23/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | New Service Connection Charge for LAKSAN BAZER W/S SCHEME, T/W No. I, under NAGRAKATA CCC, [APPLICATION NO. 4002969971, Reference ID :402856021] |  |  | VCH/000890/2022-2023 | BP/22-23/63 | 23/09/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2022-2023 | 1232/JD | 02/06/2022 | 23/06/2022 | J.M. CONSTRUCTION | 7.16 | 4.67 | 65.13 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 2nd tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2022-2023 | 1218/JD | 26/05/2022 | 16/06/2022 | J.M. CONSTRUCTION | 7.16 | 5.53 | 77.22 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- I) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000705/2021-2022 | 818/JD | 30/03/2022 | 20/04/2022 | PINAKI MITRA | 7.15 | 7.01 | 98.07 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000704/2021-2022 | 817/JD | 30/03/2022 | 20/04/2022 | PINAKI MITRA | 7.15 | 6.25 | 87.35 | 1
10 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with Sanitary & Plumbing arrangement at Head works site for Augmentation of Luksan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000039/2022-2023 | 1080/JD | 29/04/2022 | 28/06/2022 | MONOTOSH ROY | 5.61 | 5.61 | 100 | 1
11 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Infrastructure Cost for LUKSAN BAZER,T/W I,ZONE-I, under NAGRAKATA CCC, [APPLICATION NO. 100000072620, Reference ID : 860263640] |  |  | BILL/00760/2022-2023 | BP/22-23/159 | 23/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.27 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | New Service Connection Charge for LUKSAN BAZER,T/W I,ZONE-III, under NAGRAKATA CCC, [APPLICATION NO. 4003097549, Reference ID : 402966979] |  |  | BILL/00761/2022-2023 | BP/22-23/159 | 23/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Infrastructure Cost for LUKSAN BAZER,T/W I,ZONE-III, under NAGRAKATA CCC, [APPLICATION NO. 100000072602, Reference ID : 860263632] |  |  | BILL/00762/2022-2023 | BP/22-23/159 | 23/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.49 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | New Service Connection Charge for LUKSAN BAZER,T/W I,ZONE-I, under NAGRAKATA CCC, [APPLICATION NO. 4003095902, Reference ID : 402966241] |  |  | BILL/00759/2022-2023 | BP/22-23/159 | 23/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-11) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000833/2021-2022 | 1182/W/JSSD | 08/03/2022 | 28/03/2022 | M K KAYAL & ASSOCIATES | 2.02 | 2 | 98.97 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-1) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000827/2021-2022 | 1184/W/JSSD | 08/03/2022 | 28/03/2022 | MABCO CONSULTANT | 2.02 | 0.85 | 41.88 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  |  | BILL/00357/2022-2023 | BP-2023-24-110 | 17/05/2023 |  | M/S MILLENNIUM FUEL CENTRE | 4.99 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 1st tube-well site for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  |  | ORD/001007/2021-2022 | 1263/JSSD | 25/03/2022 | 14/04/2022 | JAYA SARKAR | 4.79 | 4.24 | 88.53 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | 250 Cum OHR as per Departmental Design & Drawing for Augmentation of Lukshan Bazar Piped Water Supply Scheme at Zone-I Block- Nagrakata, District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000558/2023-2024 | 1975/JD | 03/01/2024 | 01/07/2024 | SUBIR GHOSH | 57.18 | 0 | 0 | 0
20 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Balance work for construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement at 2nd T/W site for Augmentation of Lukshan Bazar (Zone - II) Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. |  |  | ORD/000554/2023-2024 | 505/JSSD | 02/01/2024 | 16/02/2024 | ARUP SARKAR | 2.75 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at Lukshan Bazar (Zone-III) for Augmentation of Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/001003/2021-2022 | 1244/JSSD | 25/03/2022 | 09/05/2022 | SURAJIT KUNDU | 4.65 | 4.01 | 86.28 | 100
22 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Lukshan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001005/2021-2022 | 1261/JSSD | 25/03/2022 | 14/04/2022 | SURAJIT KUNDU | 4.79 | 3.37 | 70.39 | 100
23 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000570/2021-2022 | 548/JD | 28/02/2022 | 31/07/2023 | GAP ENGINEERS ENTERPRISES | 79.03 | 18.53 | 23.45 | 48
24 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar Water Supply Scheme (Zone-II). | Assistant Engineer | Junior Engineer | ORD/000073/2022-2023 | 1315/JD | 16/06/2022 | 31/07/2022 | ANUP SARKAR | 90.22 | 14.95 | 16.58 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Laying Rising Main for Augmenmtation of Luksan Bazar (Zone -I ,zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000478/2022-2023 | 797/JD.. | 29/03/2023 | 12/04/2023 | MONTOSH GHOSH | 7.71 | 0 | 0 | 0
26 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Pump House (3.60 m x 2.40 m ) size with sanitary & plumbing arrangement at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme for under Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/001002/2021-2022 | 1243/JSSD | 25/03/2022 | 09/05/2022 | KABYA ENTERPRISE | 4.64 | 2.32 | 50 | 100
27 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Pump House (3.60m x 2.40m) size including sanitary & plumbing works at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-II) Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/001004/2021-2022 | 1245/JSSD | 25/03/2022 | 09/05/2022 | DEBABRATA SARKAR | 4.65 | 0 | 0 | 100
28 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000581/2021-2022 | 547/JD | 28/02/2022 | 30/03/2022 | ALICK DUTTA | 21.58 | 1.83 | 8.48 | 15
29 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Emergent repair of damage pipe line and FHTC at Lukshan Bazar (Zone-III) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000547/2023-2024 | 498/JSSD | 02/01/2024 | 01/02/2024 | ALICK DUTTA | 4.81 | 1.67 | 34.79 | 100
30 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LUKSAN BAZAR PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000800/2022-2023 | 163/NMD | 17/02/2023 | 19/03/2023 | CHOWDHURY AND BASU ENTERPRISE | 41.3 | 28.71 | 69.53 | 80
31 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Redevelopment of Boundary Wall with gate, drain and pathway for Existing tubewell (2nd site as per new drawing) site for Augmentation of Luksan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2024-2025 | 959/JD | 09/08/2024 | 08/09/2024 | ALICK DUTTA | 22.33 | 0 | 0 | 0
32 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Boundary Wall at Head Work (OHR) site of Augmentation of Luksan Bazar (Zone-II) i.c.w. Jal Jeevan Mission at block Nagrakata in Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000059/2024-2025 | 960/JD | 09/08/2024 | 08/09/2024 | ALICK DUTTA | 12.36 | 0 | 0 | 0
33 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Lukshan Bazar Piped Water Supply Scheme at Zone-II Block- Nagrakata, District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000587/2021-2022 | 735/JD | 17/03/2022 | 13/09/2022 | SCEC BOENTER KDAS JOINT VENTURE | 55.08 | 11.11 | 20.16 | 100
Total | [13 empty] | 566.79 | 122.68 | 21.65