## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2022-2023 | 1232/JD | 02/06/2022 | 23/06/2022 | J.M. CONSTRUCTION | 7.16 | 4.67 | 65.13 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 2nd tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2022-2023 | 1218/JD | 26/05/2022 | 16/06/2022 | J.M. CONSTRUCTION | 7.16 | 5.53 | 77.22 | 1
3 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | New Service Connection Charge for LAKSAN BAZER W/S SCHEME, T/W No. II, under NAGRAKATA CCC, [APPLICATION NO. 4002966831, Reference ID :402856022] |  |  | VCH/000892/2022-2023 | BP/22-23/63 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | New Service Connection Charge for LAKSAN BAZER W/S SCHEME, T/W No. I, under NAGRAKATA CCC, [APPLICATION NO. 4002969971, Reference ID :402856021] |  |  | VCH/000890/2022-2023 | BP/22-23/63 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT LAKSAN BAZER W/S SCHEME, T/W No. II, under NAGRAKATA CCC, [APPLICATION NO. 100000056975, Reference ID : 860246285] |  |  | VCH/000893/2022-2023 | BP/22-23/63 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT LAKSAN BAZER W/S SCHEME, T/W No. I, under NAGRAKATA CCC, [APPLICATION NO. 100000058118, Reference ID : 860247828] |  |  | VCH/000891/2022-2023 | BP/22-23/63 | 23/09/2022 | 23/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.79 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with Sanitary & Plumbing arrangement at Head works site for Augmentation of Luksan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000039/2022-2023 | 1080/JD | 29/04/2022 | 28/06/2022 | MONOTOSH ROY | 5.61 | 5.61 | 100 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- I) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000705/2021-2022 | 818/JD | 30/03/2022 | 20/04/2022 | PINAKI MITRA | 7.15 | 7.01 | 98.07 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000704/2021-2022 | 817/JD | 30/03/2022 | 20/04/2022 | PINAKI MITRA | 7.15 | 6.25 | 87.35 | 1
10 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-11) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000833/2021-2022 | 1182/W/JSSD | 08/03/2022 | 28/03/2022 | M K KAYAL & ASSOCIATES | 2.02 | 2 | 98.97 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-1) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000827/2021-2022 | 1184/W/JSSD | 08/03/2022 | 28/03/2022 | MABCO CONSULTANT | 2.02 | 0.85 | 41.88 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 1st tube-well site for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  |  | ORD/001007/2021-2022 | 1263/JSSD | 25/03/2022 | 14/04/2022 | JAYA SARKAR | 4.79 | 4.24 | 88.53 | 100
13 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Infrastructure Cost for LUKSAN BAZER,T/W I,ZONE-I, under NAGRAKATA CCC, [APPLICATION NO. 100000072620, Reference ID : 860263640] |  |  | BILL/00760/2022-2023 | BP/22-23/159 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.27 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Infrastructure Cost for LUKSAN BAZER,T/W I,ZONE-III, under NAGRAKATA CCC, [APPLICATION NO. 100000072602, Reference ID : 860263632] |  |  | BILL/00762/2022-2023 | BP/22-23/159 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.49 | 0 | 0 | 0
15 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | New Service Connection Charge for LUKSAN BAZER,T/W I,ZONE-I, under NAGRAKATA CCC, [APPLICATION NO. 4003095902, Reference ID : 402966241] |  |  | BILL/00759/2022-2023 | BP/22-23/159 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
16 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | New Service Connection Charge for LUKSAN BAZER,T/W I,ZONE-III, under NAGRAKATA CCC, [APPLICATION NO. 4003097549, Reference ID : 402966979] |  |  | BILL/00761/2022-2023 | BP/22-23/159 | 23/03/2023 | 23/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  |  | BILL/00357/2022-2023 | BP-2023-24-110 | 17/05/2023 | 17/05/2023 | M/S MILLENNIUM FUEL CENTRE | 4.99 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Lukshan Bazar Piped Water Supply Scheme at Zone-II Block- Nagrakata, District - Jalpaiguri. | Assistant Engineer | Junior Engineer | ORD/000587/2021-2022 | 735/JD | 17/03/2022 | 13/09/2022 | SCEC BOENTER KDAS JOINT VENTURE | 55.08 | 22.21 | 40.33 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Sinking of Big Dia 2nd Tube well by Modified DTH - ODEX Method at 1st tube well site of Augmentation of Luksan Bazar Piped Water Supply Scheme of (zone-I) of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2024-2025 | 2319/JD | 11/12/2024 | 26/12/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | -Interconnection work including FHTC with allied works at Augmentation of Looksan Bazar Piped W/S Scheme ( zone-I & III) in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000148/2024-2025 | 267/JSSD | 25/09/2024 | 10/10/2024 | GOURAV CONSTRUCTION CO. | 2.25 | 0 | 0 | 0
21 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Balance work in connection with Laying Rising Main for Augmentation of Luksan Bazar (Zone -I ,Zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000150/2024-2025 | 263/JSSD | 25/09/2024 | 02/01/2025 | MONTOSH GHOSH | 2.78 | 1.5 | 54.04 | 100
22 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Pump House (3.60 m x 2.40 m ) size with sanitary & plumbing arrangement at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme for under Jalpaiguri Division. | Assistant Engineer | Junior Engineer | ORD/001002/2021-2022 | 1243/JSSD | 25/03/2022 | 09/05/2022 | KABYA ENTERPRISE | 4.64 | 4.64 | 100 | 100
23 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at Lukshan Bazar (Zone-III) for Augmentation of Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/001003/2021-2022 | 1244/JSSD | 25/03/2022 | 09/05/2022 | SURAJIT KUNDU | 4.65 | 4.65 | 100 | 100
24 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Lukshan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001005/2021-2022 | 1261/JSSD | 25/03/2022 | 14/04/2022 | SURAJIT KUNDU | 4.79 | 3.37 | 70.39 | 100
25 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Laying Rising Main for Augmenmtation of Luksan Bazar (Zone -I ,zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000478/2022-2023 | 797/JD.. | 29/03/2023 | 17/11/2024 | MONTOSH GHOSH | 7.71 | 7.5 | 97.38 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000581/2021-2022 | 547/JD | 28/02/2022 | 30/03/2022 | ALICK DUTTA | 21.58 | 4.67 | 21.64 | 15
27 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Pump House (3.60m x 2.40m) size including sanitary & plumbing works at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-II) Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/001004/2021-2022 | 1245/JSSD | 25/03/2022 | 09/05/2022 | DEBABRATA SARKAR | 4.65 | 0 | 0 | 100
28 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Emergent repair of damage pipe line and FHTC at Lukshan Bazar (Zone-III) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000547/2023-2024 | 498/JSSD | 02/01/2024 | 01/02/2024 | ALICK DUTTA | 4.81 | 2.61 | 54.36 | 100
29 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Balance work for construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement at 2nd T/W site for Augmentation of Lukshan Bazar (Zone - II) Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000554/2023-2024 | 505/JSSD | 02/01/2024 | 02/12/2024 | ARUP SARKAR | 2.75 | 2.75 | 100 | 100
30 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000570/2021-2022 | 548/JD | 28/02/2022 | 02/10/2025 | GAP ENGINEERS ENTERPRISES | 79.03 | 18.53 | 23.45 | 75
31 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LUKSAN BAZAR PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Driller-in-Charge | Junior Engineer | ORD/000800/2022-2023 | 163/NMD | 17/02/2023 | 19/03/2023 | CHOWDHURY AND BASU ENTERPRISE | 41.3 | 37.91 | 91.81 | 80
32 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Redevelopment of Boundary Wall with gate, drain and pathway for Existing tubewell (2nd site as per new drawing) site for Augmentation of Luksan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2024-2025 | 959/JD | 09/08/2024 | 03/04/2026 | ALICK DUTTA | 22.33 | 3.46 | 15.5 | 75
33 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Construction of Boundary Wall at Head Work (OHR) site of Augmentation of Luksan Bazar (Zone-II) i.c.w. Jal Jeevan Mission at block Nagrakata in Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000059/2024-2025 | 960/JD | 09/08/2024 | 02/04/2026 | ALICK DUTTA | 12.36 | 0 | 0 | 0
34 | JALPAIGURI |  | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Land development works at the Zone-II H/W Site along with pump connection and other allied works at Augmentation of Luksan Bazar Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000142/2024-2025 | 257/JSSD | 25/09/2024 | 02/01/2026 | ARUP SARKAR | 2.61 | 0 | 0 | 0
35 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS | SM/11814 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 25/03/2025 | D.K. & SONS | 1.23 | 0 | 0 | 0
Total | [13 empty] | 366.84 | 150 | 40.89