## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Minor repairing of Two nos. Pump House with Construction of Toilet and Sanitary Plumbing System located at head work site including Land Development work at 2nd Pummp house site and adjacent area along with ancillary work of Augmentation of Bhatiapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000098/2022-2023 | 1306/JD | 14/06/2022 | 05/07/2022 | RABINDRANATH DUTTA | 3.93 | 0 | 0 | 100
2 | JALPAIGURI |  | Central Drilling | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 135 mtrs. Depth) by utilising Departmental machineries for Bhatipara PWSS, Dhupguri block under Jalpaiguri District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000460/2022-2023 | 1776/CDD | 20/01/2023 | 19/02/2023 | PADMA ENGINEERING & CO. | 12.61 | 0 | 0 | 100
3 | JALPAIGURI |  | Central Drilling | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Additional work for drilling bolder/sand stone Zone at Bhatiapara (Zone-I) PWSS (TW-II), Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | Driller In Charge | Junior Engineer | ORD/000046/2023-2024 | 132/CMSD-II(D) | 23/05/2023 | 02/06/2023 | PADMA ENGINEERING & CO. | 0.72 | 0 | 0 | 100
4 | JALPAIGURI |  | Central Drilling | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Additional work for drilling bolder/sand stone Zone at Bhatiapara (Zone-I) PWSS (TW-I) HW, Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | Driller In Charge | Junior Engineer | ORD/000047/2023-2024 | 131/CMSD-II(D) | 23/05/2023 | 02/06/2023 | PADMA ENGINEERING & CO. | 0.79 | 0 | 0 | 100
5 | JALPAIGURI |  | Central Drilling | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Providing drilling crews for construction of Tube Well (250 mm x 150 mm x 88 mtrs depth) by SUPER RR Rig machine for Bhatiyapara PWSS Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000496/2022-2023 | 219/CMSD-I | 15/03/2023 | 30/03/2023 | PADMA ENGINEERING & CO. | 4.64 | 0 | 0 | 100
6 | JALPAIGURI |  | Central Drilling | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Providing Tube Well materials conforming to IS : 12818 : 2010 with other works at site for construction of Tube well for Bhatiyapara Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000497/2022-2023 | 221/CMSD-I | 15/03/2023 | 30/03/2023 | PADMA ENGINEERING & CO. | 2.64 | 0 | 0 | 100
7 | JALPAIGURI |  | Central Drilling | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Providing additional Tubewell materials conforming to IS: 12818:2010 with other works at site for construction of Tubewell for Bhatiapara (Zone-I) PWSS (TW-II), Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | Driller In Charge | Junior Engineer | ORD/000045/2023-2024 | 133/CMSD-II | 23/05/2023 | 02/06/2023 | PADMA ENGINEERING & CO. | 0.87 | 0 | 0 | 100
8 | JALPAIGURI |  | Central Drilling | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 130 mtrs. Depth) by utilising Departmental machineries for Bhatiapara W/S Scheme (Z-II,TW-III), Nagrakata block under Jalpaiguri District, CDD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000053/2023-2024 | 875/CDD | 11/07/2023 | 10/08/2023 | PADMA ENGINEERING & CO. | 13.53 | 0 | 0 | 100
9 | JALPAIGURI |  | Central Drilling | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Providing strainer conforming to IS : 12818 : 2010 with other materials & works at site for construction of Tube well at Bhatipara Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000498/2022-2023 | 220/CMSD-I | 15/03/2023 | 30/03/2023 | PADMA ENGINEERING & CO. | 2.13 | 0 | 0 | 100
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 1065/JD | 24/08/2023 | 24/08/2023 | Resource Division | 7.18 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Laying Distribution System for Augmentation of Bhatiapara (Zone-II) Piped Water Supply Scheme (Part A & D) at Nagrakata Block Under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000260/2022-2023 | 1948/JD | 13/10/2022 | 10/02/2023 | JAYANTA GHOSH | 241.53 | 0 | 0 | 60
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara ( Zone-I )Piped water Supply Scheme (Part-B) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000296/2022-2023 | 2060/JD | 03/11/2022 | 24/11/2022 | SAPTASWA SARKAR | 74.86 | 0 | 0 | 100
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara ( Zone-II )Piped water Supply Scheme (Part-E) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000240/2022-2023 | 1959/JD | 17/10/2022 | 07/11/2022 | M/S SIBU DEY AND CO. | 81.95 | 0 | 0 | 95
14 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara ( Zone-I )Piped water Supply Scheme (Part-C) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000272/2022-2023 | 2013/JD | 01/11/2022 | 22/11/2022 | NEW KUNDU ENTERPRISE | 58.51 | 0 | 0 | 96
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Construction of One No Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Augmentation of Bhatiapara PWSS Zone-I under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000272/2023-2024 | 1260/JD | 13/09/2023 | 01/09/2025 | NARAYAN CHAKRABORTY | 56.64 | 0 | 0 | 6
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Bhatia Para (Zone-II) Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000525/2023-2024 | 1970/JD | 03/01/2024 | 24/01/2024 | RABINDRANATH DUTTA | 18.51 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara ( Zone-II ) Piped water Supply Scheme (Part-C) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000319/2022-2023 | 2004/JD | 28/10/2022 | 18/11/2022 | GOURAB GUHA ROY | 33.43 | 0 | 0 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2024-2025 | 2209/JD | 01/12/2024 | 01/12/2024 | Resource Division | 31.51 | 0 | 0 | 0
20 | JALPAIGURI |  | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | New Service Connection Charge for BHATIAPARA T/W-II, under GAIRKATA CCC, [APPLICATION NO. 4003356887, Reference ID : 403176984] |  |  | BILL/02172/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
21 | JALPAIGURI |  | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | New Service Connection Charge for AUGMENTATION OF BHATIAPARA, T/W-III, under BANARHAT CCC APPLICATION NO. 4003373992 Reference ID : 403189742 |  |  | BILL/00133/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.53 | 0 | 0 | 0
22 | JALPAIGURI |  | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | New Service Connection Charge for BHATIAPARA T/W-II, under GAIRKATA CCC, [APPLICATION NO. 100000101603, Reference ID : 860292663] |  |  | BILL/02173/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.21 | 0 | 0 | 0
23 | JALPAIGURI |  | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | New Service Connection Charge for AUGMENTATION OF BHATIAPARA, T/W-I, under BANARHAT CCC APPLICATION NO. 4003373981 Reference ID : 403189738 |  |  | BILL/00132/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.13 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Construction of 450 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at Head Works site for Augmentation of Bhatiapara (Zone-II) Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2023-2024 | 240/JD | 08/05/2023 | 28/04/2025 | JAYANTA GHOSH | 140.51 | 0 | 0 | 60
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Construction of One No Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Augmentation of Bhatiapara PWSS Zone-II under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000273/2023-2024 | 1261/JD | 13/09/2023 | 31/08/2025 | RANA DEY | 90.44 | 0 | 0 | 50
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Construction of 2nd Tube well site Boundary wall, Drain, Pathway and Laying of Rising main at Zone-I of Bhatiapara PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000596/2024-2025 | 268/JD | 07/02/2025 | 01/01/2026 | RANA DEY | 9.33 | 0 | 0 | 0
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Laying distribution system for Augmentation of BHATIAPARA (ZONE-I) Piped Water Supply Scheme (PART-A) at Banarhut Block under Jalpaiguri Division, P.H.E Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000536/2024-2025 | 569/JD | 25/03/2025 | 01/04/2026 | ANUP SARKAR | 146.75 | 0 | 0 | 0
28 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Construction of 3rd site Tube well Boundary wall, Drain, Pathway and Laying of Rising main at Zone-II of Bhatiapara PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000597/2024-2025 | 269/JD | 07/02/2025 | 04/07/2025 | RANA DEY | 9.24 | 0 | 0 | 0
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara (Zone-II ) Piped water Supply Scheme(Part-B) at Nagrakata Block under Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000146/2022-2023 | 1889/JD | 22/09/2022 | 30/08/2025 | RANA DEY | 65.49 | 0 | 0 | 97
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at Head Works site for Augmentation of Bhatiapara (Zone-I) Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000330/2023-2024 | 1346/JD | 26/09/2023 | 31/12/2024 | D. S. ENTERPRISE | 109.4 | 0 | 0 | 100
31 | JALPAIGURI |  | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme | SM/13277 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BHATIAPARA PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte.. | Driller-in-Charge | Junior Engineer | ORD/000973/2023-2024 | 1895/NMD | 30/11/2023 | 16/02/2025 | M/S P.P. ELECTRICALS | 32.53 | 0 | 0 | 85
Total | [13 empty] | 1296.9 | 0 | 0