## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Providing Functional Household Tap Connection in connection with Jalswapna with retrofitting work for Mahalaxmi Colony, Lataguri for Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001064/2021-2022 | 995/JSSD | 05/01/2022 | 20/01/2022 | ALICK DATTA | 4.6 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Soil Investigation work for 350 CuM Over Head Reservoir for Augmentation of Lataguri (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000702/2021-2022 | 1069/JSSD | 25/01/2022 | 14/02/2022 | GLORY ENGINEERS SYNDICATE | 1.83 | 1.62 | 88.85 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Providing Functional House hold Tap connection in connection with Jalswapna with retroffiting work for Mahalaxmi Colony, Lataguri for Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001065/2021-2022 | 995/JSSD | 05/01/2022 | 20/01/2022 | ALICK DATTA | 4.6 | 4.7 | 102.13 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Minor repairing and renovation of 3rd T/W site and H/W site Pump Houses at Lataguri Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000553/2021-2022 | 987/JSSD | 03/01/2022 | 23/01/2022 | D. S. ENTERPRISE | 2.63 | 2.64 | 100.16 | 0
5 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. III, Zone III under KRANTI CCC, [APPLICATION NO. 4002975529, Reference ID : 402862647] |  |  | VCH/000987/2022-2023 | BP/22-23/95 | 18/11/2022 | 18/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
6 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. II, Zone-II under KRANTI CCC , [APPLICATION NO. 100000059309, Reference ID : 860248969] |  |  | VCH/001005/2022-2023 |  | 03/11/2022 | 03/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.9 | 0 | 0 | 0
7 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. I, Zone III under KRANTI CCC, [APPLICATION NO. 4002975529, Reference ID : 402862647] |  |  | VCH/001006/2022-2023 |  | 03/11/2022 | 03/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
8 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. III, Zone I under KRANTI CCC, [APPLICATION NO. 4100000054083, Reference ID : 860243703] |  |  | VCH/001009/2022-2023 | BP/22-23/95 | 18/11/2022 | 18/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.49 | 0 | 0 | 0
9 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. II, Zone I under KRANTI CCC , [APPLICATION NO. 100000059310, Reference ID : 860248970] |  |  | VCH/000986/2022-2023 | BP/22-23/95 | 18/11/2022 | 18/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.9 | 0 | 0 | 0
10 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. II, Zone II under KRANTI CCC, [APPLICATION NO. 4002975542, Reference ID : 402862648] |  |  | VCH/001004/2022-2023 |  | 03/11/2022 | 03/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
11 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. I, Zone-III under KRANTI CCC , [APPLICATION NO. 100000059308, Reference ID : 860248968] |  |  | VCH/001007/2022-2023 |  | 03/11/2022 | 03/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0 | 0
12 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. II,Zone I under KRANTI CCC, [APPLICATION NO. 4002975542, Reference ID : 402862648] |  |  | VCH/000985/2022-2023 | BP/22-23/95 | 18/11/2022 | 18/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
13 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. III, Zone III under KRANTI CCC , [APPLICATION NO. 100000059310, Reference ID : 860248970] |  |  | VCH/000988/2022-2023 | BP/22-23/95 | 18/11/2022 | 18/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0 | 0
14 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. III, Zone I under KRANTI CCC, [APPLICATION NO. 4002941867, Reference ID : 402838302] |  |  | VCH/001008/2022-2023 | BP/22-23/95 | 18/11/2022 | 18/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.4 | 0 | 0 | 0
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of approach for Head Works Site for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000384/2022-2023 | 360/JD | 20/02/2023 | 27/02/2023 | RAGHU DAS | 0.56 | 0.56 | 99.38 | 0
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Laying of Rising Main from 1st, 2nd & 3rd Tube Well site to OHR for Augmentation of Lataguri (Zone-I) PWSS in connection with Jal Jeevan Mission at Block -Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000359/2023-2024 | 277/JSSD | 21/09/2023 | 21/10/2023 | ARUP SARKAR | 6.5 | 0 | 0 | 0
17 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of Pump House (3.60 M x 2.40 M) size including sanitary and Plumbing Works at 3rd tube well site for Augmentation of Lataguri (zone-II) PWSS under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000600/2021-2022 | 1066/JSSD | 24/02/2022 | 10/04/2022 | ROY CONSTRUCTION | 4.76 | 4.7 | 98.82 | 1
18 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Emergent Laying of diverted line damaged by excavator due to construction of Market Complex at Lataguri Bazar and replacing the damaged GI line at Lal Setu at Lataguri Water Supply Scheme under Jalpaiguri Division PHE Dte. |  |  | ORD/000552/2021-2022 | 990/JSSD | 03/01/2022 | 13/01/2022 | LOKNATH CONSTRUCTION | 1.47 | 1.12 | 76.65 | 100
19 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of Pump House (3.60 M x 2.40 M) size including sanitary plumbing works at 2nd tube well site for Augmentation of Lataguri (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000596/2021-2022 | 1054/JSSD | 24/01/2022 | 10/03/2022 | KABYA ENTERPRISE | 4.76 | 4.76 | 100 | 100
20 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Soil Investigation work for 300 CuM Over Head Reservoir Augmentation of Lataguri (Zone-III) PWSS, under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000692/2021-2022 | 1067/JSSD | 24/01/2022 | 13/02/2022 | MABCO CONSULTANT | 1.83 | 1.73 | 94.9 | 1
21 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of 350 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Lataguri (Zone-II) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2022-2023 | 1031/JD | 26/04/2022 | 23/10/2022 | RAGHU DAS | 96.77 | 98.75 | 102.05 | 1
22 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of Rig approach for Installation of tubewell of Head Works, 2nd Tubewell and 3rd Tube Well site for Augmentation of Lataguri Piped Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2022-2023 | 86/JSSD | 22/07/2022 | 29/07/2022 | ALICK DUTTA | 1.46 | 1.45 | 99.63 | 1
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Emergent Laying of pipeline at Purba Lataguri Station Para and repairing old stand post (broken)due to widening and strengthening of PWD lataguri-Kranti Road at Lataguri Water Supply Scheme under Jalpaiguri Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2022-2023 | 87/JSSD | 22/07/2022 | 01/08/2022 | KAMALESH SEN | 1.11 | 1.11 | 100 | 1
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Repairing of 2nd Pump House, office-cum-godown, IEP platform and construction of drain with earth filling in H/W site and ancillary works with over hauling of 3-unit IEP plant for Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000230/2022-2023 | 1946/JD | 13/10/2022 | 03/11/2022 | D. S. ENTERPRISE | 18.91 | 18.8 | 99.39 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PHE Dte Jalpaiguri (with valid Taxi permit). Period from 01/06/2023 to 31/07/2023. |  |  | ORD/000134/2023-2024 | 558/RWS | 31/05/2023 | 31/07/2023 | APIKUL ALI | 0.29 | 0.29 | 100 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 1066/JD | 24/08/2023 | 24/08/2023 | Resource Division | 342.41 | 0 | 0 | 0
27 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Infrastructure Cost for LATAGURI W/S Scheme, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 100000070391, Reference ID : 860261321] |  |  | BILL/00580/2022-2023 | BP/22-23/136 | 28/02/2023 | 28/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.57 | 0 | 0 | 0
28 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | New Service Connection Charge for LATAGURI, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 4003078500, Reference ID : 402950395] |  |  | BILL/00578/2022-2023 | BP/22-23/136 | 28/02/2023 | 28/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
29 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Infrastructure Cost for LATAGURI W/S Scheme, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 100000070390, Reference ID : 860261320] |  |  | BILL/00581/2022-2023 | BP/22-23/136 | 28/02/2023 | 28/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.94 | 0 | 0 | 0
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  |  | BILL/00356/2022-2023 | BP-2023-24-111 | 17/05/2023 | 17/05/2023 | M/S MILLENNIUM FUEL CENTRE | 2.85 | 0 | 0 | 0
31 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | New Service Connection Charge for LATAGURI, ZONE-II,T/W No - III W/S Scheme, under KRANTI CCC, [APPLICATION NO. 4003071675, Reference ID : 402950393] |  |  | BILL/00579/2022-2023 | BP/22-23/136 | 28/02/2023 | 28/02/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
32 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | SUPPLY OF 1(ONE) MAXI CAB WITH ENGINE CAPACITY MORE THAN 2000C.C ON HIRE BASIS INCLUDING DRIVER FOR ASSISTANT ENGINEER (SADAR), JALPAIGURI SADAR SUB DIVISION, P.H.E. DTE. DIST-JALPAIGURI (WITH VALID PERMIT) |  |  | BILL/00322/2023-2024 | BP-2023-24-292 | 10/08/2023 | 10/08/2023 | MANIK RAY | 0.25 | 0 | 0 | 0
33 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000289/2022-2023 | 1899/JD | 26/09/2022 | 25/12/2022 | CALCON CONSTRUCTIONS | 267.26 | 211.29 | 79.06 | 80
34 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000291/2022-2023 | 2059/JD | 03/11/2022 | 23/07/2025 | M/S SURAJIT DEY AND CO. | 383.43 | 260.59 | 67.96 | 95
35 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 1/11/2023-30/04/2024 | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 378/JSSD | 30/10/2023 | 27/04/2024 | MRITYUNJAY SIKDAR | 0.88 | 0.42 | 47.17 | 0
36 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
37 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/08/2024 to 31/10/2024 | Assistant Engineer | Junior Engineer | ORD/000113/2024-2025 | .142/2/JSSD | 29/07/2024 | 29/10/2024 | MRITYUNJAY SIKDAR | 0.44 | 0.16 | 37.29 | 0
38 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2024 to 30/07/2024 | Assistant Engineer | Junior Engineer | ORD/000001/2024-2025 | 022/JSSD | 30/04/2024 | 29/07/2024 | MRITYUNJAY SIKDAR | 0.44 | 0.22 | 50.93 | 70
39 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Lataguri (Zone-III) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000069/2022-2023 | 1922/JD | 28/09/2022 | 27/03/2023 | J.M. CONSTRUCTION | 84.24 | 83.45 | 99.06 | 100
40 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of Boundary Wall at 2nd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Lataguri (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000099/2022-2023 | 78/JSSD | 22/07/2022 | 11/08/2022 | SURAJIT KUNDU | 4.57 | 4.52 | 98.74 | 100
41 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no II, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000756/2022-2023 | 56/NMD | 24/01/2023 | 23/02/2023 | SUDIP DUTTA | 10.71 | 10.71 | 99.96 | 60
42 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no III, Z-I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000767/2022-2023 | 73/NMD | 27/01/2023 | 01/11/2023 | MUSTAFI CONCERN | 10.7 | 10.7 | 100 | 100
43 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no I, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000755/2022-2023 | 55/NMD | 24/01/2023 | 23/02/2023 | SUMON ELECTRICAL | 10.74 | 10.74 | 100 | 90
44 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no III, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000757/2022-2023 | 57/NMD | 24/01/2023 | 23/02/2023 | INDRANI ENTERPRISE | 10.74 | 10.74 | 100 | 100
45 | JALPAIGURI |  | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no I, Z-III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000754/2022-2023 | 54/NMD | 24/01/2023 | 23/02/2023 | S.P. ENTERPRISE | 10.73 | 10.73 | 100 | 80
46 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Laying Rising Main from 1st & 2nd Tubewell site to OHR for Augmentation of Lataguri (Zone-III) in connection with PWSS in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000365/2023-2024 | 281/JSSD | 26/09/2023 | 26/10/2023 | GOPRO CONSTRUCTION | 3.62 | 3.55 | 97.85 | 100
47 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Rising Line Connection with wash line and balance work in Head Works site at Augmentation of Lataguri(zone-II) PWSS under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2023-2024 | 506/JSSD | 02/01/2024 | 01/02/2024 | RAGHU DAS | 9.22 | 9.2 | 99.82 | 100
48 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Rejuvenation of different components of PWSS of Over Head Reservoir site at Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000010/2024-2025 | 423/JD | 12/06/2024 | 27/07/2024 | APEX ENGINEERING | 22.45 | 3.28 | 14.63 | 100
49 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Lataguri (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000103/2022-2023 | 79/JSSD | 22/07/2022 | 11/08/2022 | SURAJIT KUNDU | 4.57 | 4.47 | 97.7 | 100
50 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Balance work for Laying Distribution System with Providing FHTC for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.¿. Dte. | Assistant Engineer | Junior Engineer | ORD/000198/2024-2025 | 298/JSSD | 03/10/2024 | 18/10/2024 | CALCON CONSTRUCTIONS | 8.06 | 0 | 0 | 100
51 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2024-2025 | 2216/JD | 01/12/2024 | 01/12/2024 | Resource Division | 30.66 | 0 | 0 | 0
52 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | SUPPLY OF FUEL(DISEL) FOR THE VEHICLE NO. WB-78-3405 FOR THE MONTH OF FEBRUARY2024 FOR THE OFFICE USE OF THE ASSISTANT ENGINEER ,SADAR SUB DIVISION, UNDER EXECUTIVE ENGINEER ,JALPAIGURI DIVISION. |  |  | BILL/01356/2023-2024 | BP-2024-25-15 | 12/04/2024 | 12/04/2024 | FILL & SMILE | 0.25 | 0 | 0 | 0
53 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Aug'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00855/2024-2025 | BP-2024-25-499 | 07/10/2024 | 07/10/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
54 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2022-2023 | 877/JD | 05/04/2022 | 01/01/2026 | SCEC BOENTER KDAS JOINT VENTURE | 237.94 | 126.1 | 53 | 88
55 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 3rd & 4th TW including Rising main for Augmentation of Lataguri PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000111/2024-2025 | 1417/JD | 20/09/2024 | 14/05/2025 | M/S SIBU DEY AND CO. | 40.12 | 0 | 0 | 40
56 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Balance work in HW site at Zone-III of Augmentation of Lataguri PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000590/2024-2025 | 455/JD | 10/03/2025 | 09/04/2025 | J.M. CONSTRUCTION | 16.72 | 0 | 0 | 0
57 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Construction of Pump House (3.6x2.4) m with Land Development, Boundary Wall, approach, Retrofitting work of Lataguri Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte | Assistant Engineer | Junior Engineer | ORD/000092/2021-2022 | 1331/JD | 23/08/2021 | 03/09/2025 | R.K. SINGHA & SONS | 15.94 | 11.1 | 69.63 | 100
58 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme | SM/13278 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Lataguri (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/000346/2023-2024 | 1433/JD | 05/10/2023 | 12/10/2024 | ARUP SARKAR | 15.64 | 0 | 0 | 100
Total | [13 empty] | 1774.16 | 914.21 | 51.53