## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Construction of different components of Madhya Boragari Zone-I PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000285/2023-2024 | 1521/JD | 16/10/2023 | 02/04/2026 | R.S CONSTRUCTION | 430.92 | 155.57 | 36.1 | 65
2 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA BORAGARI PWSS, ZONE-I, TW no I, II, III, IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000433/2023-2024 | 1372/NMD | 09/08/2023 | 08/09/2023 | EASTERN INDIA SALES & SERVICE | 43.5 | 19.52 | 44.86 | 45
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1109/JD | 24/08/2023 | 24/08/2023 | Resource Division | 25.74 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 2004/JD | 08/01/2024 | 08/01/2024 | Resource Division | 13.46 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003378751 Reference ID : 403193482 |  |  | BILL/00157/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.36 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003376713 Reference ID : 403191839 |  |  | BILL/00159/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.13 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-III, under DHUPGURI CCC APPLICATION NO. 4003390202 Reference ID : 403202832 |  |  | BILL/00306/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.73 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Madhya Boragari Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000541/2024-2025 | 110/JD | 16/01/2025 | 02/03/2025 | BISWANATH GHOSH | 47.44 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 05/02/2025 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME | SM/13681 | New | Material Requisition To Resource Division |  |  | RTOR000108/2024-2025 | 517/JD | 13/03/2025 | 13/03/2025 | Resource Division | 22.85 | 0 | 0 | 0
Total | [13 empty] | 705.22 | 175.08 | 24.83