## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/13682 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1110/JD | 24/08/2023 | 24/08/2023 | Resource Division | 14.91 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/13682 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 1843/JD | 15/12/2023 | 15/12/2023 | Resource Division | 8.21 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/13682 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA BORAGARI PWSS, ZONE-II, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000241/2023-2024 | 1255/NMD | 31/07/2023 | 30/08/2023 | RMD TRADING | 21.74 | 0 | 0 | 60
4 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/13682 | New | New Service Connection Charge for MADHYA BORAGARI PWSS, ZONE-II, TW NO II, under DHUPGURI CCC APPLICATION NO. 4003460802 Reference ID : 403255266 |  |  | BILL/00971/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.3 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/13682 | New | New Service Connection Charge for MADHYA BORAGARI PWSS, ZONE-II, TW NO I, under DHUPGURI CCC APPLICATION NO. 4003460793 Reference ID : 403255267 |  |  | BILL/00972/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.21 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/13682 | New | Construction of different components of MADHYA BORAGARI ZONE-II PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division, P.H.E DTE. | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000239/2025-2026 | 2345/JD | 04/11/2025 | 02/06/2026 | BISWANATH GHOSH | 327.82 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME | SM/13682 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Madhya Barogari Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000166/2025-2026 | 1958/JD | 18/09/2025 | 02/11/2025 | DEBASISH DEY | 29.65 | 0 | 0 | 0
Total | [13 empty] | 412.84 | 0 | 0