## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 161/JD | 28/04/2023 | 28/04/2023 | Resource Division | 131.96 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 2058/JD | 09/01/2024 | 09/01/2024 | Resource Division | 8.7 | 0 | 0 | 0
3 | JALPAIGURI | Maynaguri | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | New Service Connection Charge for Dakshin Putimari, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003388138 Reference ID : 403201474 |  |  | BILL/00207/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.63 | 0 | 0 | 0
4 | JALPAIGURI | Maynaguri | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | New Service Connection Charge for Dakshin Putimari, T/W-I under BHOTPATTY CCC APPLICATION NO. 4003378682 Reference ID : 403193481 |  |  | BILL/00206/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.99 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Additional work for Laying pipe line at Dakshin Putimari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000081/2024-2025 | 1171/JD | 23/08/2024 | 01/04/2026 | PAMPA CONSTRUCTION | 20.26 | 0 | 0 | 65
7 | JALPAIGURI | Maynaguri | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 23/02/2025 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001006/2024-2025 | 26/NMD | 06/01/2025 | 05/02/2025 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
10 | JALPAIGURI | Maynaguri | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
11 | JALPAIGURI | Maynaguri | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN PUTIMARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000845/2022-2023 | 333/NMD | 29/03/2023 | 01/08/2025 | RIPON DAS | 21.5 | 18.66 | 86.81 | 100
12 | JALPAIGURI | Maynaguri | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 22/08/2024 | GURUKUL INFOTECH | 4.43 | 0 | 0 | 100
13 | JALPAIGURI | Maynaguri | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Construction of different components of Dakshin Putimari PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN , FHTC etc. in connection with JJM at Block - Maynaguri under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000467/2022-2023 | 778/JD | 27/03/2023 | 02/04/2026 | ASHIT KUMAR SINGHA | 363.4 | 145.33 | 39.99 | 45
14 | JALPAIGURI | Maynaguri | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME | SM/13700 | New | Construction of boundary wall with gate, drain, Land development, pathway at H/W site and 2nd site including laying pipe line and FHTC work at Dakshin Putimari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte i.c.w. JJM . | Assistant Engineer | Junior Engineer | ORD/000561/2024-2025 | 115/JD | 16/01/2025 | 01/04/2026 | ASHIT KUMAR SINGHA | 35.9 | 0 | 0 | 65
Total | [13 empty] | 1108.72 | 164 | 14.79