## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 159/JD | 28/04/2023 | 28/04/2023 | Resource Division | 62.06 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Construction of Boundary Wall at 2nd site of GAUGRAM PWSS in connection with Jal Jeevan Mission at Block - MAYNAGURI under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000686/2023-2024 | 152/RWS | 15/02/2024 | 16/03/2024 | JAGORAN SARKAR | 5.23 | 5.22 | 99.73 | 100
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 22/08/2024 | PRITAM DUTTA | 4.83 | 0 | 0 | 100
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 2040/JD | 09/01/2024 | 09/01/2024 | Resource Division | 14.78 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | New Service Connection Charge for GOURGRAM, T/W No. I under BHOTPATTY CCC [APPLICATION NO. 4003305799 ; Reference ID : 403134434] |  |  | BILL/01856/2023-2024 | BP/23-24/294 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.37 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | New Service Connection Charge for Gourgram, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003375840 Reference ID : 403191702 |  |  | BILL/00289/2024-2025 | BP/24-25/36 | 14/05/2024 | 14/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.64 | 0 | 0 | 0
7 | JALPAIGURI | Maynaguri | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Construction of different components of Gaurgram PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal JeevanMission at Block- Maynaguri under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000476/2022-2023 | 787/JD | 27/03/2023 | 21/02/2026 | M/S S.G. CONSTRUCTION | 346.83 | 168.71 | 48.64 | 100
9 | JALPAIGURI | Maynaguri | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAURGRAM PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000415/2023-2024 | 1329/NMD | 08/08/2023 | 16/06/2025 | DIPALI CONSTRUCTION | 22.21 | 17.48 | 78.69 | 100
10 | JALPAIGURI | Maynaguri | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Gaurgram PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000453/2024-2025 | 633/JD | 28/03/2025 | 12/05/2025 | RABINDRA NATH DUTTA | 34.39 | 0 | 0 | 0
11 | JALPAIGURI | Maynaguri | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 23/02/2025 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
12 | JALPAIGURI | Maynaguri | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001006/2024-2025 | 26/NMD | 06/01/2025 | 05/02/2025 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0 | 0
13 | JALPAIGURI | Maynaguri | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
14 | JALPAIGURI | Maynaguri | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME | SM/13701 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
Total | [13 empty] | 1018.3 | 191.41 | 18.8