## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 168/JD | 28/04/2023 | 28/04/2023 | Resource Division | 23.28 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-I) of MAHANBHITA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  | Junior Engineer | ORD/001706/2023-2024 | 439/SMSD | 28/03/2024 | 04/04/2024 | CHOWDHURY AND BASU ENTERPRISE | 0.73 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-II) of MAHANBHITA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  | Junior Engineer | ORD/001707/2023-2024 | 440/SMSD | 28/03/2024 | 04/04/2024 | S.P. ENTERPRISE | 0.73 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Jalpaiguri Division | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 2051/JD | 09/01/2024 | 09/01/2024 | Resource Division | 13.02 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | New Service Connection Charge for MOHANVITA,ZONE-I, T/W-I, under FULBARIHAT CCC APPLICATION NO. 4003359104 Reference ID : 403178079 |  |  | BILL/00332/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0 | 0
6 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | New Service Connection Charge for MAHANVITA,ZONE-II,T/W-II, under FULBARIHAT CCC APPLICATION NO. 4003365271 Reference ID : 403182689 |  |  | BILL/00162/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0 | 0
7 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Additional New Service Connection Charge for MOHANBHITA, T/W-III, ZONE-I,under FULBARI CCC APPLICATION NO. 4003338759 Reference ID : 860296643 |  |  | BILL/00125/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.23 | 0 | 0 | 0
8 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Infrastructure Cost for MOHONVITA, ZONE-II T/W-I, under FULBARI CCC [APPLICATION NO. 4003338806 , Reference ID : 403162021] |  |  | BILL/02046/2023-2024 | BP/23-24/313 | 28/02/2024 | 28/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.89 | 0 | 0 | 0
9 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | New Service Connection Charge for MOHANVITA,ZONE-I, T/W-II, under FULBARIHAT CCC APPLICATION NO. 4003359089 Reference ID : 403178078 |  |  | BILL/00333/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.78 | 0 | 0 | 0
10 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Additional New Service Connection Charge for MOHANBHITA, T/W-I, ZONE-II,under FULBARI CCC APPLICATION NO. 4003338806 Reference ID : 860296639 |  |  | BILL/00126/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.23 | 0 | 0 | 0
11 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Infrastructure Cost for MOHONVITA, ZONE-I T/W-III, under FULBARI CCC [APPLICATION NO. 4003338759 , Reference ID : 403161865] |  |  | BILL/02045/2023-2024 | BP/23-24/313 | 28/02/2024 | 28/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0 | 0
12 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MAHANBHITA PWSS, ZONE-I AND II, TW NO I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000025/2023-2024 | 467/NMD | 25/04/2023 | 01/01/2026 | M/S P.P. ELECTRICALS | 73.36 | 60.7 | 82.74 | 95
13 | JALPAIGURI | Rajganj | Jalpaiguri Division | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Construction of different components of Mahanbhita (Zone-I and II) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc under Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000066/2023-2024 | 367/JD | 26/05/2023 | 15/01/2026 | MINTU CHAKRABORTY | 512 | 206.47 | 40.33 | 40
14 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
15 | JALPAIGURI | Rajganj | Jalpaiguri Division | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Construction of boundary wall with gate, drain, Land development and pathway including laying pipe line at Mahanbhita Zone-I (HW site & 2nd site) and Mahanbhita Zone-II (HW site, 2nd site and 3rd site) of Mahanbhita piped water supply scheme i.c.w. JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000585/2024-2025 | 270/JD | 07/02/2025 | 23/04/2025 | SANKAR DAS | 80.69 | 0 | 0 | 30
16 | JALPAIGURI | Rajganj | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME | SM/13702 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 1323.39 | 267.17 | 20.19