## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Matiali | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME | SM/13703 | New | Commissioning of Baradighi Tea Garden Area Piped water supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000253/2022-2023 | 173/JSSD | 25/08/2022 | 24/10/2022 | PRIYABRATA KARMAKAR | 4.59 | 4.57 | 99.58 | 0
2 | JALPAIGURI | Matiali | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME | SM/13703 | New | Construction of different components of BaraDighi PWSS i.e. TW, Pump Houses, Water distribution Network,OHR,RISING MAIN,FHTC etc. i.c.w Jal Jeevan Mission at Block-Matiali under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000471/2022-2023 | 775/JD | 27/03/2023 | 30/03/2026 | RAGHU DAS | 107.46 | 73.31 | 68.22 | 90
3 | JALPAIGURI | Matiali | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME | SM/13703 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 171/JD | 28/04/2023 | 28/04/2023 | Resource Division | 3.55 | 0 | 0 | 0
4 | JALPAIGURI | Matiali | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME | SM/13703 | New | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 2044/JD | 09/01/2024 | 09/01/2024 | Resource Division | 1.29 | 0 | 0 | 0
5 | JALPAIGURI | Matiali | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME | SM/13703 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month June'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00454/2024-2025 | BP-2024-25-279 | 01/08/2024 | 01/08/2024 | FILL & SMILE | 0.23 | 0 | 0 | 0
6 | JALPAIGURI | Matiali | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME | SM/13703 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
Total | [13 empty] | 151.46 | 77.88 | 51.42