## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1107/JD | 24/08/2023 | 24/08/2023 | Resource Division | 25.88 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | New Service Connection Charge for SAKATI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4400307494, Reference ID : 403056595] |  |  | BILL/00626/2023-2024 | BP/23-24/87 | 21/08/2023 | 21/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | New Service Connection Charge for SAKATI, T/W I, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003212055, Reference ID : 403060258] |  |  | BILL/01069/2023-2024 | BP/23-24/105 | 30/09/2023 | 30/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0 | 0
4 | JALPAIGURI | Jalpaiguri | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Infrastructure Cost for SAKATI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000086241, Reference ID : 860277651] |  |  | BILL/00627/2023-2024 | BP/23-24/87 | 21/08/2023 | 21/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0 | 0
5 | JALPAIGURI | Jalpaiguri | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SHAKATI PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000021/2023-2024 | 463/NMD | 25/04/2023 | 25/05/2023 | SUMON ELECTRICAL | 22.07 | 17.9 | 81.11 | 100
6 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 2002/JD | 08/01/2024 | 08/01/2024 | Resource Division | 7.26 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Construction of different components of Shakati PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000465/2022-2023 | 753/JD | 24/03/2023 | 11/09/2025 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 346.92 | 250.01 | 72.07 | 95
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Installation of two tank chlorination system at SHAKATI and other adjacent water supply scheme UNDER JJM under JALPAIGURI SADAR Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/000887/2024-2025 | 79/SMSD | 07/02/2025 | 22/02/2025 | SUMON ELECTRICAL | 1.57 | 0 | 0 | 0
10 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Construction of Boundary Wall ,Foot Path,Drain, at 2nd site of Shakati PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000111/2025-2026 | 489/RWS | 29/05/2025 | 28/06/2025 | MS DEBABRATA SARKAR | 6.24 | 0 | 0 | 0
11 | JALPAIGURI | Jalpaiguri | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
12 | JALPAIGURI | Jalpaiguri | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
13 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 22/08/2024 | GURUKUL INFOTECH | 4.43 | 0 | 0 | 100
14 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Balance Work of Distribution System for Shakati Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000057/2024-2025 | 958/JD | 09/08/2024 | 07/12/2024 | DIPANKAR DUTTA | 29.74 | 0 | 0 | 100
15 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME | SM/13704 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Shakati PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000676/2024-2025 | 468/JD | 11/03/2025 | 20/04/2025 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 17.67 | 0 | 0 | 100
Total | [13 empty] | 1118.97 | 267.91 | 23.94