## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1112/JD | 24/08/2023 | 24/08/2023 | Resource Division | 122.36 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 1506/JD | 13/10/2023 | 13/10/2023 | Resource Division | 15.68 | 0 | 0 | 0
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Construction of Boundary Wall at 3rd Pump House site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division PHE, DTE. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 1299/JD | 05/09/2024 | 04/11/2024 | M/S KARMAKAR CONSTRUCTION | 10.93 | 0 | 0 | 0
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Brahmapur PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000458/2024-2025 | 2335./JD | 12/12/2024 | 10/02/2025 | SANDIP BANIK | 61.25 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Construction of Boundary Wall at 2nd Pump House site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000083/2024-2025 | 802/RWS | 20/08/2024 | 19/09/2024 | TECHNO CRACY | 7.49 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 22/08/2024 | PRITAM DUTTA | 4.83 | 4.83 | 100 | 100
7 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 2053/JD | 09/01/2024 | 09/01/2024 | Resource Division | 15.68 | 0 | 0 | 0
8 | JALPAIGURI | Maynaguri | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | New Service Connection Charge for Brahmapur, T/W-III under BHOTPATTY CCC APPLICATION NO. 4003377837 Reference ID : 403192843 |  |  | BILL/00288/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.64 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | New Service Connection Charge for Brahmapur, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003375994 Reference ID : 403191703 |  |  | BILL/00208/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.64 | 0 | 0 | 0
10 | JALPAIGURI | Maynaguri | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BRAHAMPURI PWSS, TW no I, II and III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000825/2022-2023 | 267/NMD | 21/03/2023 | 01/09/2025 | DAS ENTERPRISE | 32.59 | 0 | 0 | 65
11 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Construction of different components of Brahmapur PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000436/2023-2024 | 1670/JD | 24/11/2023 | 02/04/2025 | NARAYAN CHANDRA SAHA | 597.49 | 147.47 | 24.68 | 50
12 | JALPAIGURI | Maynaguri | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 23/02/2025 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
13 | JALPAIGURI | Maynaguri | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001006/2024-2025 | 26/NMD | 06/01/2025 | 05/02/2025 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0 | 0
14 | JALPAIGURI | Maynaguri | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
15 | JALPAIGURI | Maynaguri | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME | SM/13705 | New | Construction of Boundary Wall at H/W site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000073/2024-2025 | 1173/JD | 23/08/2024 | 22/10/2024 | PARAMJYOTI ENTERPRISE | 23.37 | 0 | 0 | 100
Total | [13 empty] | 1014.34 | 152.3 | 15.01