## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 151/JD | 28/04/2023 | 28/04/2023 | Resource Division | 105.47 | 0 | 0 | 0
2 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AMGURI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000843/2022-2023 | 271/NMD | 21/03/2023 | 20/04/2023 | TALUKDER ENTERPRISE | 22.92 | 21.83 | 95.24 | 100
3 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Construction of Boundary Wall at 2nd Pump House site Including raising main and interconnection of Amguri PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000674/2023-2024 | 165/RWS | 15/02/2024 | 16/03/2024 | DEEP CONSTRUCTION | 6.17 | 6.16 | 99.89 | 100
4 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 2056/JD | 09/01/2024 | 09/01/2024 | Resource Division | 14.62 | 0 | 0 | 0
5 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | New Service Connection Charge for AMGURI, T/W No. I, under MAYNAGURI CCC, [APPLICATION NO. 4003266414, Reference ID : 403108583] |  |  | BILL/01283/2023-2024 | 23-24/155&163 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.24 | 0 | 0 | 0
6 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | New Service Connection Charge for AMGURI, T/W No. II, under MAYNAGURI CCC [APPLICATION NO. 4003297950 , Reference ID : 403128266] |  |  | BILL/01780/2023-2024 | BP/23-24/217 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.49 | 0 | 0 | 0
7 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Balance Laying Distribution System and Providing Functional Household Tap Connection in connection with Jal Jeevan Mission at Amguri PWSS in Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000512/2024-2025 | 45/JD | 09/01/2025 | 01/03/2026 | B. M CONSTRUCTION | 70.87 | 0 | 0 | 60
8 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 23/02/2025 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
9 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001007/2024-2025 | 27/NMD | 06/01/2025 | 05/02/2025 | M/S BHOWMICK & CO. | 18.4 | 0 | 0 | 0
10 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
11 | JALPAIGURI | Maynaguri | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
12 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-C of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 985/JD | 14/08/2024 | 29/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 4.63 | 0 | 0 | 100
13 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of Amguri PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000814/2023-2024 | 2631/JD | 07/03/2024 | 21/04/2024 | B.M CONSTRUCTION | 16.14 | 6.46 | 40.05 | 100
14 | JALPAIGURI | Maynaguri | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME | SM/13706 | New | Construction of approach for Head Works Site for Amguri Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000099/2025-2026 | 478/RWS | 29/05/2025 | 28/06/2025 | SUKES BASU MAJUMDAR | 4.32 | 0 | 0 | 100
Total | [13 empty] | 726.45 | 34.45 | 4.74