## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Laying Distribution System with Providing Functional Household Tap Connection with Jalswapna for Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 881/JD | 05/04/2022 | 01/08/2025 | CALCON CONSTRUCTIONS | 234.41 | 104.98 | 44.79 | 75
2 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Laying Distribution System with Providing Functional Household Tap Connection with Jalswapna for Augmentation of Oodlabari (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2022-2023 | 880/JD | 05/04/2022 | 01/01/2026 | M/S SURAJIT DEY AND CO. | 275.87 | 134.75 | 48.84 | 70
3 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Repairing Over Head Reservoir (OHR) with 2 Nos Pump House Head Works Boundary Wall and other ancillary works related to H/W site at Oodlabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001070/2021-2022 | 165/JD | 20/01/2022 | 06/03/2022 | U TURN CONSTRUCTION | 18.63 | 18.64 | 100.04 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari More towards Damdim Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-II) | Assistant Engineer | Junior Engineer | ORD/000263/2022-2023 | 186/JSSD | 31/08/2022 | 30/09/2022 | BIMAN DAS | 4.83 | 4.82 | 99.84 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari-Kranti Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-III) | Assistant Engineer | Junior Engineer | ORD/000246/2022-2023 | 162/JSSD | 24/08/2022 | 23/09/2022 | BIMAN DAS | 4.77 | 4.76 | 99.82 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Sinking of 3 Nos. Deep Rig Bored Tube well by Odex - 165 Method of drilling for Augmentation of Oodlabari (Zone-II) Piped water supply scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000392/2022-2023 | 2527/JD | 30/12/2022 | 29/01/2023 | MS S R CONSTRUCTION CO | 16.6 | 17.1 | 102.98 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari More towards Bagrakote Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-I) | Assistant Engineer | Junior Engineer | ORD/000264/2022-2023 | 191/JSSD | 02/09/2022 | 02/10/2022 | BIMAN DAS | 3.83 | 3.81 | 99.33 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Construction of Pump House (3.60m X2.40 m) size including Sanitary and Plumbing works at 3rd Tube-Well site for Augmentation of Oodlabari (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, PH.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000656/2022-2023 | 100/JSSD | 25/07/2022 | 08/09/2022 | BIMAN DAS | 4.75 | 4.64 | 97.63 | 100
9 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Oodlabari (Zone-II) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000040/2022-2023 | 1067/JD | 28/04/2022 | 01/01/2025 | TARAKESWAR PRASAD | 84.41 | 56.54 | 66.99 | 70
10 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Soil Investigation work for 300 CuM Over Head Reservoir (OHR) for Augmentation of Oodlabari (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001072/2021-2022 | 1070/JSSD | 25/01/2022 | 14/02/2022 | SHINE ENGINEERING CONSULTANT | 1.83 | 1.51 | 82.67 | 1
11 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Construction of Pump House (3.60mx2.40m) size including sanitary and plumbing works at 2nd Tube well site for Augmentation of Oolabari (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000706/2021-2022 | .1051/JSSD | 24/01/2022 | 10/03/2022 | BIMAN DAS | 4.75 | 4.64 | 97.63 | 100
12 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Construction of Boundary Wall at 2nd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Oodlabari (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000104/2022-2023 | 80/JSSD | 22/07/2022 | 11/08/2022 | BIMAN DAS | 4.57 | 4.38 | 95.82 | 100
13 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Oodlabari (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000105/2022-2023 | 81/JSSD | 22/07/2022 | 11/08/2022 | BIMAN DAS | 4.57 | 4.39 | 96.1 | 100
14 | JALPAIGURI |  | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ODLABARI PWSS, ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000890/2022-2023 | 373/NMD | 29/03/2023 | 28/04/2023 | B.B. CONCERNED | 37.59 | 37.59 | 100 | 95
15 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Laying Rising Main from 1st, 2nd & 3rd Tubewell site to OHR for Augmentation of Oodlabari (Zone-II) PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000254/2023-2024 | 1259/JD | 13/09/2023 | 04/10/2023 | PRITAM DUTTA | 11.83 | 11.73 | 99.22 | 100
16 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 1088/JD | 24/08/2023 | 24/08/2023 | Resource Division | 100.49 | 0 | 0 | 0
17 | JALPAIGURI |  | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Infrastructure Cost for Oldabari, Zone-II, TW No. III, ODLABARI CCC, [APPLICATION NO. 100000077680, Reference ID : 860269310] |  |  | BILL/00036/2023-2024 | BP/23-24/14 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.16 | 0 | 0 | 0
18 | JALPAIGURI |  | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | New Service Connection Charge for Oldabari, Zone-II, TW No. III, ODLABARI CCC, [APPLICATION NO. 4003145978, Reference ID : 403012265] |  |  | BILL/00033/2023-2024 | BP/23-24/14 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
19 | JALPAIGURI |  | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Infrastructure Cost for Oldabari, Zone-II, TW No. I, ODLABARI CCC, [APPLICATION NO. 100000077681, Reference ID : 860269311] |  |  | BILL/00035/2023-2024 | BP/23-24/14 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0 | 0
20 | JALPAIGURI |  | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | New Service Connection Charge for Oldabari, Zone-II, TW No. I, ODLABARI CCC, [APPLICATION NO. 4003145968, Reference ID : 403012267] |  |  | BILL/00034/2023-2024 | BP/23-24/14 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
21 | JALPAIGURI |  | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Infrastructure Cost for Oldabari, Zone-II, TW No. II, ODLABARI CCC, [APPLICATION NO. 10000077682, Reference ID : 860269312] |  |  | BILL/00037/2023-2024 | BP/23-24/14 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.4 | 0 | 0 | 0
22 | JALPAIGURI |  | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | New Service Connection Charge for Oldabari, Zone-II, TW No. II, ODLABARI CCC, [APPLICATION NO. 4003145975, Reference ID : 403012266] |  |  | BILL/00032/2023-2024 | BP/23-24/14 | 24/05/2023 | 24/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
23 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
24 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Laying Water Distribution Network for Node No 200 to 130 Along the NH-17 from Ghish to Chell River for Augmentation of Odlabari PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000434/2024-2025 | 2312./JD | 11/12/2024 | 25/01/2025 | SRINIWAS AGARWAL | 16.84 | 0 | 0 | 0
25 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Facelifting and Interior furnishing works for Establishment Section and computer Room in ground floor at PHE Division Office under Jal;paiguri Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000557/2023-2024 | 504/JSSD | 02/01/2024 | 16/02/2024 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 10.3 | 9.84 | 95.5 | 100
26 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Sinking of One No Big dia tube well (200mm x 150mm) by Modified DTH - ODEX method of drilling at H/W Site in Augmentation of Oodlabari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000825/2023-2024 | 2751/JD | 14/03/2024 | 29/03/2024 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 14.01 | 84.25 | 100
27 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Construction approach with paver block inside the premises and land development at H/W site for Augmentation of Oodlabari(Zone-I) piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000809/2023-2024 | 565/JSSD | 05/03/2024 | 04/04/2024 | SUBHANKAR DEY | 2.76 | 2.73 | 98.87 | 100
28 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Balance work i.c.w Laying Rising Main from 1st, 2nd & 3rd Tubewell site to OHR for Augmentation of Oodlabari (Zone-II) PWSS in connection with Jal Jeevan Mission at Block -Mal under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000158/2024-2025 | 264/JSSD | 25/09/2024 | 25/10/2024 | PRITAM DUTTA | 2.47 | 0 | 0 | 100
29 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2024-2025 | 2220/JD | 01/12/2024 | 01/12/2024 | Resource Division | 20.62 | 0 | 0 | 0
30 | JALPAIGURI |  | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme | SM/13790 | Augmentation | Construction approach with paver block inside the premises and land development at HW site of Aug. of Oodlabari PWSS (Z-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000088/2025-2026 | 101/JSSD | 30/05/2025 | 29/06/2025 | PRIYABRATA KARMAKAR | 6.59 | 0 | 0 | 0
Total | [13 empty] | 931.59 | 440.86 | 47.32