## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Construction of different components of Madhya Daukimari PWSS i.e TW, Pump Houses, Water Distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Banarhat under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000012/2023-2024 | 28/JD | 10/04/2023 | 01/06/2025 | SUKES BASU MAJUMDAR | 506.72 | 497.83 | 98.25 | 100
2 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA DAUKIMARI PWSS, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000238/2023-2024 | 1252/NMD | 31/07/2023 | 01/02/2025 | PADMA ENGINEERING CO. | 24.51 | 17.83 | 72.74 | 100
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 1879/JD | 20/12/2023 | 20/12/2023 | Resource Division | 11.14 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 162/JD | 28/04/2023 | 28/04/2023 | Resource Division | 103.77 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | New Service Connection Charge for MADHYA DAUKIMARI, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003256198, Reference ID : 403097555] |  |  | BILL/01652/2023-2024 | 23-24/169&172 | 12/12/2023 | 12/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.83 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000030/2024-2025 | 692/JD | 19/07/2024 | 16/11/2024 | B.M CONSTRUCTION | 50.78 | 50.78 | 100 | 100
7 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. (Part- B) | Assistant Engineer,HQ | Junior Engineer | ORD/000177/2024-2025 | 1533/JD | 01/10/2024 | 15/11/2024 | SUKES BASU MAJUMDAR | 66.83 | 24.95 | 37.33 | 100
8 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Infrastructure Cost for MADHYA DAUKIMARI , T/W-I, under DHUPGURI CCC [APPLICATION NO. 4003269038 , Reference ID : 403107836] |  |  | BILL/02030/2023-2024 | BP/23-24/311 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Additional New Service Connection Charge for MADHYA DAUKIMARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 100000103797 Reference ID : 860296017 |  |  | BILL/00127/2024-2025 |  | 04/04/2024 | 04/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | New Service Connection Charge for MADHYA DAUKIMARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003388992 Reference ID : 403201630 |  |  | BILL/00292/2024-2025 |  | 06/05/2024 | 06/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Balance Laying Distribution System and Sinking of Additional Tube Well by Reverse Rotary including construction of Pump House and laying Rising Main etc. in connection with Jal Jeevan Mission of Madhya Daukimari PWSS at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000606/2024-2025 | 456/JD | 10/03/2025 | 01/04/2026 | B. M CONSTRUCTION | 71.85 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 05/02/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
13 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
14 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
15 | JALPAIGURI | Dhupguri | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME | SM/13898 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 1511.73 | 591.39 | 39.12