## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1116/JD | 24/08/2023 | 24/08/2023 | Resource Division | 23.05 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 1841/JD | 15/12/2023 | 15/12/2023 | Resource Division | 11.08 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Dhupguri block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer | Junior Engineer | ORD/000473/2023-2024 | 1293/RWS | 29/11/2023 | 29/12/2023 | B.M CONSTRUCTION | 3.89 | 0 | 0 | 100
4 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. I, under DHUPGURI CCC [APPLICATION NO. 4003332348 , Reference ID : 403156800] |  |  | BILL/01996/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.65 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003328084 , Reference ID : 403153544] |  |  | BILL/01999/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.26 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003332367 , Reference ID : 403156921] |  |  | BILL/01998/2023-2024 | BP/23-24/308 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.73 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR ALTAGRAM PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000432/2023-2024 | 1371/NMD | 09/08/2023 | 01/09/2025 | M/S SAJAHAN CHOWDHURY | 33.24 | 0 | 0 | 95
8 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 05/02/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Balance work of Distribution System for Uttar Altagram Piped Water Supply Scheme within Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000167/2025-2026 | 2002/JD | 25/09/2025 | 24/12/2025 | KAMAL DAS | 72.36 | 0 | 0 | 60
13 | JALPAIGURI | Dhupguri | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME | SM/13899 | New | Construction of different components of Uttar Altagram PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000099/2023-2024 | 351/JD | 24/05/2023 | 08/11/2024 | SUKES BASU MAJUMDAR | 446.33 | 0 | 0 | 100
Total | [13 empty] | 1256.29 | 0 | 0