## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Matiali | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 145/JD | 28/04/2023 | 28/04/2023 | Resource Division | 14.77 | 0 | 0 | 0
2 | JALPAIGURI | Matiali | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3 | JALPAIGURI | Matiali | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Balance work in connection with Laying distribution system along with providing FHTC at Zone I , II & III of Neora Majhiali Piped W/S Scheme in connection with JJM at Matiali Block, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000433/2024-2025 | 2315./JD | 11/12/2024 | 25/01/2025 | SRINIWAS AGARWAL | 55.21 | 0 | 0 | 0
4 | JALPAIGURI | Matiali | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 2030/JD | 09/01/2024 | 09/01/2024 | Resource Division | 9.41 | 0 | 0 | 0
5 | JALPAIGURI | Matiali | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
6 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "INFRA COST IRO NSC for NEORA MAJHIALI,ZIII TW NO-I,METELI CCC " APPLICATION NO.100000108813 Reference ID : 860301243 |  |  | BILL/00419/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.58 | 0 | 0 | 0
7 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,ZII TW NO-II, MAL CCC " APPLICATION NO. 100000104809 Reference ID : 860297129 |  |  | BILL/00170/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0 | 0
8 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,Z1 TW NO-I, MAL CCC APPLICATION NO. 100000104807 Reference ID : 860297127 " |  |  | BILL/00164/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.11 | 0 | 0 | 0
9 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,ZII TW NO-II, MAL CCC " APPLICATION NO. 4003377495 Reference ID : 403192837 |  |  | BILL/00169/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
10 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,Z1 TW NO-II, MAL CCC " APPLICATION NO. 4003377487 Reference ID : 403192832 |  |  | BILL/00165/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
11 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Infrastructure Cost for NEORA MAJHIALI, T/W No. I, ZONE-I, under METELLI CCC [APPLICATION NO. 100000095976 ; Reference ID : 860287636] |  |  | BILL/01732/2023-2024 | BP/23-24/231 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.58 | 0 | 0 | 0
12 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,Z1 TW NO-I, MAL CCC " APPLICATION NO. 4003377483 Reference ID : 403192834 |  |  | BILL/00163/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
13 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | New Service Connection Charge for NEORA MAJHIALI, T/W No. I, ZONE-I, under METELLI CCC [APPLICATION NO. 4003293335 ; Reference ID : 403125585] |  |  | BILL/01731/2023-2024 | BP/23-24/230 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
14 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,Z-I TW NO-II, MAL CCC " APPLICATION NO. 100000104808 Reference ID : 860297128 |  |  | BILL/00166/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.93 | 0 | 0 | 0
15 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,ZII TW NO-I, MAL CCC " APPLICATION NO. 100000104910 Reference ID : 860297130 |  |  | BILL/00168/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.81 | 0 | 0 | 0
16 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,Z II TW NO-I, MAL CCC " APPLICATION NO. 4003377491 Reference ID : 403192835 |  |  | BILL/00167/2024-2025 | BP/24-25/14 | 23/04/2024 | 23/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
17 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,ZIII TW NO-I, METELI CCC " APPLICATION NO.4003416347 Reference ID : 403224096 |  |  | BILL/00420/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
18 | JALPAIGURI | Matiali | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Construction of Different components of Neora Majhiali (Zone-I, II and III) PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Matiali under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000052/2023-2024 | 244/JD | 08/05/2023 | 03/04/2025 | SRINIWAS AGARWAL | 424.24 | 226.64 | 53.42 | 55
19 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEORA MAJHIALI PWSS, TW NO I,II,III,IV,V AND VI in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000423/2023-2024 | 1338/NMD | 08/08/2023 | 28/02/2025 | CHOWDHURY AND BASU ENTERPRISE | 73.75 | 0.88 | 1.19 | 60
20 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000883/2024-2025 | 24/NMD | 06/01/2025 | 05/02/2025 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0 | 0
21 | JALPAIGURI | Matiali | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
22 | JALPAIGURI | Matiali | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME | SM/13900 | New | Sinking of 3 (three) nos. Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling at Neora Majhiali Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000588/2023-2024 | 2333/JD | 08/02/2024 | 02/04/2025 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 61.43 | 18.66 | 30.38 | 100
Total | [13 empty] | 1303.11 | 246.18 | 18.89