## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Matiali | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Construction of Different Components of Chhaophali PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000042/2023-2024 | 138/JD | 28/04/2023 | 25/10/2023 | RANJEET SINGH BENIWAL | 131.18 | 58.34 | 44.48 | 50
2 | JALPAIGURI | Matiali | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHAOAPHALI PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000308/2023-2024 | 1273/NMD | 02/08/2023 | 01/09/2023 | M/S PALIDEB ENGINEERING WORKS | 24.43 | 21.08 | 86.27 | 75
3 | JALPAIGURI | Matiali | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1115/JD | 24/08/2023 | 24/08/2023 | Resource Division | 3.99 | 0 | 0 | 0
4 | JALPAIGURI | Matiali | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Construction of Boundary Wall with approach road at H/W site including rising main and interconnections of Chhaophali PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000699/2023-2024 | 2412/JD | 19/02/2024 | 04/04/2024 | RANJEET SINGH BENIWAL | 19.17 | 0 | 0 | 0
5 | JALPAIGURI | Matiali | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Laying of Rising Main along with pump connection for commissioning of the scheme and remaining part of laying distribution system with providing FHTC at Chhaoaphali Piped W/S Scheme in connection with JJM at Matiali Block, under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 1531/JD | 01/10/2024 | 31/10/2024 | PRIYABRATA KARMAKAR | 18.45 | 18.94 | 102.66 | 100
6 | JALPAIGURI | Matiali | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 2041/JD | 09/01/2024 | 09/01/2024 | Resource Division | 2.85 | 0 | 0 | 0
7 | JALPAIGURI | Matiali | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Infrastructure Cost for CHHAOAPHALI, T/W No. I under METELLI CCC [APPLICATION NO. 100000097045 , Reference ID : 860289125] |  |  | BILL/01802/2023-2024 | BP/23-24/271 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.12 | 0 | 0 | 0
8 | JALPAIGURI | Matiali | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | New Service Connection Charge for CHHAOAPHALI, T/W No. I under METELLI CCC [APPLICATION NO. 4003292351 , Reference ID : 403124700] |  |  | BILL/01801/2023-2024 | BP/23-24/270 | 23/01/2024 | 23/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
9 | JALPAIGURI | Matiali | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000883/2024-2025 | 24/NMD | 06/01/2025 | 05/02/2025 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0 | 0
10 | JALPAIGURI | Matiali | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME | SM/13901 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
Total | [13 empty] | 248.89 | 98.36 | 39.52