## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Matiali | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Construction of Different Components of Uttar Dhupjhora PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000446/2022-2023 | 716/JD | 20/03/2023 | 02/07/2025 | BOSE ENTERPRISE | 231.68 | 202.41 | 87.37 | 50
2 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR DHUPJHORA PWSS, TW NO- I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000312/2023-2024 | 1277/NMD | 02/08/2023 | 31/03/2025 | M/S SWAPAN BANERJEE | 24.39 | 18.51 | 75.91 | 100
3 | JALPAIGURI | Matiali | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 176/JD | 28/04/2023 | 28/04/2023 | Resource Division | 16.8 | 0 | 0 | 0
4 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | New Service Connection Charge for JOHURUL PARA UTTAR DHUPJHORA, T/W I, under METELLI CCC, [APPLICATION NO. 4003177288, Reference ID : 403033824] |  |  | BILL/00616/2023-2024 | BP/23-24/84 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Infrastructure Cost for JOHURUL PARA UTTAR DHUPJHORA, T/W II, under METELLI CCC, [APPLICATION NO. 100000082757, Reference ID : 860274517] |  |  | BILL/00619/2023-2024 | BP/23-24/84 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0 | 0
6 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | New Service Connection Charge for JOHURUL PARA UTTAR DHUPJHORA, T/W II, under METELLI CCC, [APPLICATION NO. 4003177279, Reference ID : 403033822] |  |  | BILL/00618/2023-2024 | BP/23-24/84 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
7 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Infrastructure Cost for JOHURUL PARA UTTAR DHUPJHORA, T/W I, under METELLI CCC, [APPLICATION NO. 100000082758, Reference ID : 860274518] |  |  | BILL/00617/2023-2024 | BP/23-24/84 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.77 | 0 | 0 | 0
8 | JALPAIGURI | Matiali | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 27/10/2024 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
9 | JALPAIGURI | Matiali | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Construction of IEP and Blower Room of Uttar Dhupjhora PWSS in connection with Jal Jeevan Mission at Block - Metali under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000232/2024-2025 | 2329./JD | 12/12/2024 | 02/09/2025 | BOSE ENTERPRISE | 17.26 | 0 | 0 | 20
10 | JALPAIGURI | Matiali | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Laying of Distribution pipeline at the uncovered portions within the command area of Uttar Dhupjhora Piped W/S Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000144/2024-2025 | 258/JSSD | 25/09/2024 | 17/12/2024 | TANMOY CHOUDHURY | 4.63 | 4.71 | 101.65 | 100
11 | JALPAIGURI | Matiali | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 2035/JD | 09/01/2024 | 09/01/2024 | Resource Division | 7.13 | 0 | 0 | 0
12 | JALPAIGURI | Matiali | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
13 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | "ADDITIONAL INFRA COST IRO NSC for UTTAR DHUPJHORA TW-II,METELI CCC " APPLICATION NO.100000115577 Reference ID : 860310307 |  |  | BILL/00881/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.55 | 0 | 0 | 0
14 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000883/2024-2025 | 24/NMD | 06/01/2025 | 05/02/2025 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0 | 0
15 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
16 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000095/2025-2026 | 1085/HQ/NMD | 15/05/2025 | 22/05/2025 | D.K. & SONS | 0.63 | 0 | 0 | 0
17 | JALPAIGURI | Matiali | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA | SM/13988 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 974.05 | 225.63 | 23.16