## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Construction of Different components of Upper Tandu Forest (M) i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Nagrakata under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2022-2023 | 676/JD | 16/03/2023 | 12/09/2023 | NISHITH RANJAN KARMAKAR | 96 | 76.78 | 79.99 | 100
2 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UPPER TENDU FOREST PWSS, TW No I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000881/2022-2023 | 364/NMD | 29/03/2023 | 28/04/2023 | SAIKAT SINHA | 12.05 | 12.03 | 99.88 | 100
3 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 160/JD | 28/04/2023 | 28/04/2023 | Resource Division | 2.08 | 0 | 0 | 0
4 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | New Service Connection Charge for UPPER TENDU FOREST NEW KHUNIA MAHABARI, under MATELLI CCC [APPLICATION NO. 4003177258 ; Reference ID : 403033825] |  |  | BILL/01009/2023-2024 | BP/23-24/97 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
5 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Infrastructure Cost for UPPER TENDU FOREST NEW KHUNIA MAHABARI, under MATELLI CCC [APPLICATION NO. 100000082756 ; Reference ID : 860274516] |  |  | BILL/01010/2023-2024 | BP/23-24/97 | 12/09/2023 | 12/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.11 | 0 | 0 | 0
6 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 2057/JD | 09/01/2024 | 09/01/2024 | Resource Division | 2.22 | 0 | 0 | 0
7 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
8 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 05/02/2025 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
9 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST | SM/13989 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 709.21 | 88.82 | 12.52