## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 158/JD | 28/04/2023 | 28/04/2023 | Resource Division | 2.39 | 0 | 0 | 0
2 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | Construction of different components of Tandu PWSS i.e TW Pump Houses, Water distribution Network, OHR,RISING MAIN,FHTC etc. i.c.w JAL JEEVAN MISSION at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000466/2022-2023 | 755/JD | 24/03/2023 | 02/01/2026 | PRADIP SAHA | 114.12 | 63.69 | 55.81 | 35
3 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TANDU PWSS, TW No I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000424/2023-2024 | 1339/NMD | 08/08/2023 | 07/09/2023 | BLUE PINE | 12.03 | 11.84 | 98.36 | 100
4 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 2029/JD | 09/01/2024 | 09/01/2024 | Resource Division | 2.44 | 0 | 0 | 0
5 | JALPAIGURI | Nagrakata | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 07/03/2024 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
6 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | Infrastructure Cost for TANDU TG, T/W No. I, under NAGRAKATA CCC [APPLICATION NO. 100000096118 ; Reference ID : 860288228] |  |  | BILL/01730/2023-2024 | BP/23-24/233 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.65 | 0 | 0 | 0
7 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | New Service Connection Charge for TANDU TG, T/W No. I, under NAGRAKATA CCC [APPLICATION NO. 4003285461 ; Reference ID : 403120244] |  |  | BILL/01729/2023-2024 | BP/23-24/232 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
8 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
9 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 05/02/2025 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
10 | JALPAIGURI | Nagrakata | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU | SM/13990 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 762.78 | 75.53 | 9.9