## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 1375/JD | 27/09/2023 | 27/09/2023 | Resource Division | 18.27 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1836/JD | 15/12/2023 | 15/12/2023 | Resource Division | 5.33 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Jalpaiguri Division | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Construction of different components of Niranjan Pat PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000130/2023-2024 | 406/JD | 06/06/2023 | 03/12/2023 | UNIBRO INFRASERV PRIVATE LIMITED | 231.81 | 102.99 | 44.43 | 65
4 | JALPAIGURI | Dhupguri | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Infrastructure development cost for new service connection at NIRANJANPATH PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 100000115928 Reference ID : 860309778 |  |  | BILL/00976/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0 | 0
5 | JALPAIGURI | Dhupguri | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | New Service Connection Charge for new service connection at NIRANJANPATH PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 4003470466 Reference ID : 403261884 |  |  | BILL/00977/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | New Service Connection Charge for new service connection at NIRANJANPATH PWSS,T/W-II, GAIRKATA CCC APPLICATION NO. 4003470493 Reference ID : 403261885 |  |  | BILL/00978/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Infrastructure development cost for new service connection at NIRANJANPATH PWSS,T/W-II, GAIRKATA CCC APPLICATION NO. 100000115926 Reference ID : 860309776 |  |  | BILL/00979/2024-2025 | BP/24-25/166 | 14/08/2024 | 14/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.91 | 0 | 0 | 0
8 | JALPAIGURI | Dhupguri | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001045/2024-2025 | 30/NMD | 06/01/2025 | 05/02/2025 | GEETA CONSTRUCTION | 12.33 | 0 | 0 | 0
9 | JALPAIGURI | Dhupguri | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 01/08/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
10 | JALPAIGURI | Dhupguri | Jalpaiguri Division | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Niranjanpat Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000682/2024-2025 | 632/JD | 28/03/2025 | 12/05/2025 | TIRTHANKAR CHOWDHURY | 24.06 | 0 | 0 | 0
11 | JALPAIGURI | Dhupguri | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
12 | JALPAIGURI | Dhupguri | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME | SM/13991 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 938.83 | 102.99 | 10.97