## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 154/JD | 28/04/2023 | 28/04/2023 | Resource Division | 17.1 | 0 | 0 | 0
2 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 2003/JD | 08/01/2024 | 08/01/2024 | Resource Division | 6.23 | 0 | 0 | 0
3 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Infrastructure Cost for BINNAGURI T/W-I, under HALDIBARI CCC , [APPLICATION NO. 4003341115, Reference ID : 403164679] |  |  | BILL/02031/2023-2024 | BP/23-24/313 | 28/02/2024 | 28/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.66 | 0 | 0 | 0
4 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 03/04/2024 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
5 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Infrastructure Cost for BINNAGURI T/W-II, under HALDIBARI CCC , [APPLICATION NO. 4003341205, Reference ID : 403165171] |  |  | BILL/02032/2023-2024 | BP/23-24/313 | 28/02/2024 | 28/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.38 | 0 | 0 | 0
6 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001001/2024-2025 | 22/NMD | 06/01/2025 | 05/02/2025 | SUMON ELECTRICAL | 12.23 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
8 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Balance Laying Distribution System and Functional Household Tap Connection for Binnaguri PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000599/2024-2025 | 482/JD | 11/03/2025 | 07/02/2026 | BISWANATH GHOSH | 18.65 | 0 | 0 | 0
9 | JALPAIGURI | Jalpaiguri | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
10 | JALPAIGURI | Jalpaiguri | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME | SM/14198 | New | Construction of different components of Binnaguri PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2022-2023 | 751/JD | 24/03/2023 | 18/03/2025 | BISWANATH GHOSH | 226.15 | 130.79 | 57.83 | 100
Total | [13 empty] | 938.06 | 130.79 | 13.94