## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 165/JD | 28/04/2023 | 28/04/2023 | Resource Division | 36.86 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1509/JD | 13/10/2023 | 13/10/2023 | Resource Division | 16.29 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Construction of different components of Samarnagar Pwss (Zone-I and II) i.e.TW,Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc. under Jal Jeevan Mission at Block-Rajganj under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000451/2022-2023 | 714/JD | 20/03/2023 | 16/09/2023 | SANTALALL & BROTHERS | 431.94 | 199.78 | 46.25 | 52
4 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | New Service Connection Charge for SAMAR NAGAR, T/W-III, PRADHAN NAGAR CCC APPLICATION NO. 4003420228 Reference ID : 403226828 |  |  | BILL/00475/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.37 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | New Service Connection Charge for SAMARNAGAR, T/W /W No. I, under PRADHAN NAGAR CCC [APPLICATION NO.4003283650 ; Reference ID : 403118307] |  |  | BILL/01988/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.87 | 0 | 0 | 0
6 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | New Service Connection Charge for SAMARNAGAR, T/W /W No. II, under PRADHAN NAGAR CCC [APPLICATION NO.4003283658 , Reference ID : 403118308] |  |  | BILL/01987/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.41 | 0 | 0 | 0
7 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | New Service Connection Charge for new service connection at SAMAR NAGAR, T/W-IV, PRADHAN NAGAR CCC APPLICATION NO. 4003420236 Reference ID : 403226827 |  |  | BILL/00525/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.67 | 0 | 0 | 0
8 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
9 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
10 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SAMAR NAGAR PWSS, AT TW NO-I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000885/2022-2023 | 368/NMD | 29/03/2023 | 01/05/2025 | B.B. CONCERNED | 30.72 | 28.71 | 93.46 | 100
11 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SAMAR NAGAR PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000850/2023-2024 | 1750/NMD | 31/10/2023 | 01/05/2025 | B.B. CONCERNED | 10.36 | 8.41 | 81.19 | 100
12 | JALPAIGURI | Rajganj | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Construction of Boundary wall at Head work site and 2nd TW site including Laying Rising Main and balance laying Distribution System and other allied works related to LDS at Samarnagar Piped Water Supply Scheme (Zone-I) in connection with Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000426/2024-2025 | 2265/JD | 04/12/2024 | 17/06/2025 | SANTALALL & BROTHERS | 45.73 | 0 | 0 | 75
Total | [13 empty] | 1207.33 | 236.9 | 19.62