## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 165/JD | 28/04/2023 | 28/04/2023 | Resource Division | 36.86 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1509/JD | 13/10/2023 | 13/10/2023 | Resource Division | 16.29 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Construction of different components of Samarnagar Pwss (Zone-I and II) i.e.TW,Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc. under Jal Jeevan Mission at Block-Rajganj under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000451/2022-2023 | 714/JD | 20/03/2023 | 16/09/2023 | SANTALALL & BROTHERS | 431.94 | 199.78 | 46.25 | 52
4 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | New Service Connection Charge for SAMAR NAGAR, T/W-III, PRADHAN NAGAR CCC APPLICATION NO. 4003420228 Reference ID : 403226828 |  |  | BILL/00475/2024-2025 | BP/24-25/101 | 25/06/2024 | 25/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.37 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | New Service Connection Charge for SAMARNAGAR, T/W /W No. I, under PRADHAN NAGAR CCC [APPLICATION NO.4003283650 ; Reference ID : 403118307] |  |  | BILL/01988/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.87 | 0 | 0 | 0
6 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | New Service Connection Charge for SAMARNAGAR, T/W /W No. II, under PRADHAN NAGAR CCC [APPLICATION NO.4003283658 , Reference ID : 403118308] |  |  | BILL/01987/2023-2024 | BP/23-24/306 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.41 | 0 | 0 | 0
7 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | New Service Connection Charge for new service connection at SAMAR NAGAR, T/W-IV, PRADHAN NAGAR CCC APPLICATION NO. 4003420236 Reference ID : 403226827 |  |  | BILL/00525/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.67 | 0 | 0 | 0
8 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
9 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
10 | JALPAIGURI | Rajganj | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME | SM/14200 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SAMAR NAGAR PWSS, AT TW NO-I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000885/2022-2023 | 368/NMD | 29/03/2023 | 01/05/2025 | B.B. CONCERNED | 30.72 | 28.71 | 93.46 | 100
Total | [13 empty] | 1151.24 | 228.49 | 19.85