## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | SM/14224 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 1075/JD | 24/08/2023 | 24/08/2023 | Resource Division | 1.55 | 0 | 0 | 0
2 | JALPAIGURI | Dhupguri | Jalpaiguri Division | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | SM/14224 | New | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 1835/JD | 15/12/2023 | 15/12/2023 | Resource Division | 0.71 | 0 | 0 | 0
3 | JALPAIGURI | Dhupguri | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | SM/14224 | New | New Service Connection Charge for PRAYAGPUR PWSS, TW NO I, BANARHAT CCC. APPLICATION NO. 4003506434 Reference ID : 403286480 |  |  | BILL/01351/2024-2025 | BP/24-25/244 | 14/11/2024 | 14/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.66 | 0 | 0 | 0
4 | JALPAIGURI | Dhupguri | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | SM/14224 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PRAYAGPUR PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000237/2023-2024 | 1249/NMD | 31/07/2023 | 01/09/2025 | KARMAKAR CONSTRUCTION | 10.96 | 0 | 0 | 90
5 | JALPAIGURI | Dhupguri | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | SM/14224 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
6 | JALPAIGURI | Dhupguri | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | SM/14224 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Driller-in-Charge |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 25/03/2025 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
7 | JALPAIGURI | Dhupguri | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME | SM/14224 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001041/2024-2025 | 29/NMD | 06/01/2025 | 05/02/2025 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0 | 0
Total | [13 empty] | 89.15 | 0 | 0