## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 153/JD | 28/04/2023 | 28/04/2023 | Resource Division | 38.37 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | New Service Connection Charge for MANTABARI BFP SCHOOL, SIMULGURI,ZONE III, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003227613, Reference ID : 403072694] |  |  | BILL/01164/2023-2024 | BP/23-24/144 | 06/11/2023 | 06/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | New Service Connection Charge for SIMULGURI, T/W IIZONE II under BELAKOBA CCC, [APPLICATION NO. 4003200012, Reference ID : 403051284] |  |  | BILL/00622/2023-2024 | BP/23-24/81 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.03 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | New Service Connection Charge for SHINGIVISA NEAR MASJID, SIMULGURI,ZONE II, T/W III, under BELAKOBA CCC, [APPLICATION NO. 4003227623, Reference ID : 403072705] |  |  | BILL/01165/2023-2024 | BP/23-24/144 | 06/11/2023 | 06/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.49 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | New Service Connection Charge for SIMULGURI,ZONE III, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003219227, Reference ID : 403065768] |  |  | BILL/01166/2023-2024 | BP/23-24/144 | 06/11/2023 | 06/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.74 | 0 | 0 | 0
6 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | New Service Connection Charge for SIMULGURI,ZONE II, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003219239, Reference ID : 403065766] |  |  | BILL/01167/2023-2024 | BP/23-24/144 | 06/11/2023 | 06/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.14 | 0 | 0 | 0
7 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | New Service Connection Charge for SIMULGURI, T/W II,ZONE I under BELAKOBA CCC, [APPLICATION NO. 4003200017, Reference ID : 403051285] |  |  | BILL/00621/2023-2024 | BP/23-24/81 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.04 | 0 | 0 | 0
8 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | New Service Connection Charge for SIMULGURI, T/W I,ZONE I under BELAKOBA CCC, [APPLICATION NO. 4003200020, Reference ID : 403051286] |  |  | BILL/00620/2023-2024 | BP/23-24/81 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.5 | 0 | 0 | 0
9 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SIMULGURI PWSS, ZONE-III, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000883/2022-2023 | 366/NMD | 29/03/2023 | 28/04/2023 | M/S P.P. ELECTRICALS | 21.77 | 0 | 0 | 100
10 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SIMULGURI PWSS, ZONE-I,TW NO I,II AND ZONE-II, TW NO- I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000024/2023-2024 | 466/NMD | 25/04/2023 | 25/05/2023 | WEST BENGAL ENGINEERING CO. | 61.4 | 0 | 0 | 100
11 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | Additional work in connection with Supply, installation, commissioning and trial operation of electro-mechanical components for SIMULGURI PWSS, at TW no I (Z-I),and TW NO I,II,III (Z-II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000181/2024-2025 | 693/SMSD | 14/06/2024 | 21/06/2024 | WEST BENGAL ENGINEERING CO. | 0.87 | 0 | 0 | 100
12 | JALPAIGURI | Rajganj | Jalpaiguri Division | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 2045/JD | 09/01/2024 | 09/01/2024 | Resource Division | 18.16 | 0 | 0 | 0
13 | JALPAIGURI | Rajganj | Jalpaiguri Division | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | Construction of different components of Simulguri PWSS Zone-I, II and III i.e. TW, Pump Houses, Water distribution , Water distribution Network , OHR, Rising Main , FHTC etc. Block - Rajganj under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000493/2022-2023 | 823/JD | 30/03/2023 | 01/04/2025 | S.S. CONSTRUCTION | 709.21 | 0 | 0 | 75
14 | JALPAIGURI | Rajganj | Jalpaiguri Division | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | Construction of Boundary wall with gate, Drain, Land development ,Pathway at H/W Site & 2nd T/W site at Zone-I, H/W site , 2nd T/W & 3rd T/W site at Zone-II and H/W Site & 2nd T/W site at Zone-III including balance portion of laying distribution system with providing FHTC at SIMULGURI Piped Water Supply Scheme under Jalpaiguri Division,P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000537/2024-2025 | 571/JD | 25/03/2025 | 01/04/2026 | NEW KUNDU ENTERPRISE | 165.71 | 0 | 0 | 55
15 | JALPAIGURI | Rajganj | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME | SM/14240 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
Total | [13 empty] | 1601.92 | 0 | 0