## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 146/JD | 28/04/2023 | 28/04/2023 | Resource Division | 32.86 | 0 | 0 | 0
2 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Supply and Delivery of C.I special for attending breakdown maintenance as when as required at t/w no-I (zone-II) of PANIKAURI and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  | Junior Engineer | ORD/001712/2023-2024 | 434/SMSD | 28/03/2024 | 04/04/2024 | SAHA ENTERPRISE | 0.73 | 0 | 0 | 0
3 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-III) of PANIKAURI and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  | Junior Engineer | ORD/001713/2023-2024 | 435/SMSD | 28/03/2024 | 04/04/2024 | SARKAR ELECTRIC | 0.73 | 0 | 0 | 0
4 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 2043/JD | 09/01/2024 | 09/01/2024 | Resource Division | 23.97 | 0 | 0 | 0
5 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Additional Quotation of New Service Connection Charge for PANIKAURI, T/W-II, ZONE-III, under BELAKOBA CCC APPLICATION NO. 100000121879 ; Reference ID : 860316809 |  |  | BILL/01451/2024-2025 | BP/24-25/245 | 26/11/2024 | 26/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.08 | 0 | 0 | 0
6 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | New Service Connection Charge for new service connection at PANIKOURI, T/W-I, ZONE-II, BELAKOBA CCC APPLICATION NO. 4003372650 Reference ID : 403188995 |  |  | BILL/00526/2024-2025 | BP/24-25/123 | 16/07/2024 | 16/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.49 | 0 | 0 | 0
7 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | New Service Connection Charge for PANIKAURI, T/W-I, ZONE-I, under BELAKOBA CCC APPLICATION NO. 4003372565 Reference ID : 403188998 |  |  | BILL/00124/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0 | 0
8 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Additional Quotation of New Service Connection Charge for PANIKAURI, T/W-II, ZONE-III, under BELAKOBA CCC APPLICATION NO. 100000108541 Reference ID : 860300421 |  |  | BILL/00381/2024-2025 | BP/24-25/81 | 07/06/2024 | 07/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.59 | 0 | 0 | 0
9 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | New Service Connection Charge for PANIKAURI, T/W-II, ZONE-II, under BELAKOBA CCC APPLICATION NO. 4003372528 Reference ID : 403188999 |  |  | BILL/00122/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.9 | 0 | 0 | 0
10 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | New Service Connection Charge for PANIKAURI ,ZONE:-III, T/W-I, under BELAKOBA CCC APPLICATION NO. 4003321772 Reference ID : 403174731 |  |  | BILL/00328/2024-2025 | BP/24-25/73 | 30/05/2024 | 30/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8 | 0 | 0 | 0
11 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | New Service Connection Charge for PANIKOURI, ZONE-III, T/W- II, under BELAKOBA CCC, [APPLICATION NO. 4003321779, Reference ID : 403171726] |  |  | BILL/02140/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.62 | 0 | 0 | 0
12 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | New Service Connection Charge for PANIKAURI, T/W-III, ZONE-II, under BELAKOBA CCC APPLICATION NO. 4003372640 Reference ID : 403189001 |  |  | BILL/00123/2024-2025 | BP/24-25/01 | 10/04/2024 | 10/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.08 | 0 | 0 | 0
13 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | New Service Connection Charge for PANIKOURI, ZONE-III, T/W- III, under BELAKOBA CCC, [APPLICATION NO. 4003321780, Reference ID : 403171055] |  |  | BILL/02139/2023-2024 | BP/23-24/324 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.24 | 0 | 0 | 0
14 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | New Service Connection Charge for PANIKOURI, ZONE-I, TW NO-II, BELAKOBA CCC APPLICATION NO. 4003377413 Reference ID : 403192847 |  |  | BILL/00254/2024-2025 | BP/24-25/43 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.59 | 0 | 0 | 0
15 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PANI KAURI (ZONE-I,II and III) PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000712/2023-2024 | 1512/NMD | 24/08/2023 | 01/11/2025 | ORIENTAL ENGINEERING CO. | 98.07 | 76.35 | 77.86 | 75
16 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Construction of different components of Panikauri PWSS Zone-I,II and III PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block -Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2023-2024 | 1764/JD | 08/12/2023 | 02/04/2025 | UNIBRO INFRASERV PRIVATE LIMITED | 822.43 | 219.6 | 26.7 | 25
17 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Rajgang & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000036/2025-2026 | 823/JD | 30/04/2025 | 30/06/2025 | PRADIP SAHA | 0.8 | 0 | 0 | 0
18 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Continuation order for the work of supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 01.04.2025 to 30.04.2025) | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000788/2024-2025 | 109-HQ/JD | 28/03/2025 | 28/04/2025 | MD AMIRUL ISLAM | 0.15 | 0 | 0 | 0
19 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Construction of boundary wall with gate,drain,Land development and pathway and laying pipe line at Zone- I (H/W Site , 2 nd TW site) Zone_II,(H/W Site,2nd TW Site,3rd TW Site) and Zone-III (H/W Site,2nd TW site, 3rd TW site ) of PANIKAURI piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. inconnection with JJM. | Assistant Engineer,HQ | Junior Engineer | ORD/000023/2025-2026 | 2152/JD | 17/10/2025 | 31/12/2025 | KAMAL GHOSH | 113.94 | 0 | 0 | 0
20 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Rajgang & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer 2 | ORD/000126/2025-2026 | 1502/JD | 30/06/2025 | 31/07/2025 | PRADIP SAHA | 0.4 | 0 | 0 | 0
21 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 12/11/2025 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
22 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Sub-Soil Investigation of proposed 150 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Panikauri Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000798/2024-2025 | 85-HQ/JD | 11/03/2025 | 31/03/2025 | APEX ENGINEERING | 0.98 | 0 | 0 | 0
23 | JALPAIGURI | Rajganj | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Sub-Soil Investigation of proposed 200 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Panikauri Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000799/2024-2025 | 86-HQ/JD | 11/03/2025 | 31/03/2025 | APEX ENGINEERING | 0.98 | 0 | 0 | 0
24 | JALPAIGURI | Rajganj | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME | SM/14241 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-I) of PANIKAURI and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | Assistant Engineer | Junior Engineer | ORD/001702/2023-2024 | 433/SMSD | 28/03/2024 | 04/04/2024 | B.B. CONCERNED | 0.73 | 0.48 | 65.67 | 100
Total | [13 empty] | 1697.87 | 296.44 | 17.46